## Sheet1
Activity ID | Activity Name | QTY | Unit | Original Duration | Start | Finish
Maseel Mixed Use Development Project BL Schedule Rev 04 |  |  |  | 448 | 01-Oct-25 A | 2027-03-31
Milestones |  |  |  | 96 | 2026-11-30 | 2027-03-31
Contractual Milestones |  |  |  | 0 | 2027-03-31 | 2027-03-31
MS.MS.GEN.GEN.104 | Completion Date |  |  | 0 |  | 31-Mar-27*
Control Milestones |  |  |  | 104 | 2026-11-30 | 2027-03-31
Skeleton Milestones |  |  |  | 104 | 2026-11-30 | 2027-03-31
Phase (1) |  |  |  | 97 | 2026-12-08 | 2027-03-31
MS.MS.P1.FAF.011 | Ph01 -Completion work for substructure Works |  |  | 0 |  | 2026-12-08
MS.MS.P1.FAE.001 | 6FA-E - Completion work for Skeleton |  |  | 0 |  | 2027-03-29
MS.MS.P1.FAH.001 | 6FA-H - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
MS.MS.P1.FAI.001 | 6FA-I - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
MS.MS.P1.FAG.001 | 6FA-G - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
MS.MS.P1.FAF.001 | 6FA-F - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
Phase (2) |  |  |  | 3 | 2027-03-28 | 2027-03-31
MS.MS.P2.RBB.001 | RB-B - Completion work for Skeleton |  |  | 0 |  | 2027-03-28
MS.MS.P1.FAF.11 | Ph02 -Completion work for substructure Works |  |  | 0 |  | 2027-03-29
MS.MS.P2.FBC.001 | FB-C - Completion work for Skeleton |  |  | 0 |  | 2027-03-30
MS.MS.P2.FBR.001 | FB-R - Completion work for Skeleton |  |  | 0 |  | 2027-03-30
MS.MS.P2.HO.001 | Hotel - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
Phase (3) |  |  |  | 9 | 2027-03-21 | 2027-03-31
MS.MS.P3.FAL.001 | 4FA-L - Completion work for Skeleton |  |  | 0 |  | 2027-03-21
MS.MS.P1.FAF.21 | Ph03 -Completion work for substructure Works |  |  | 0 |  | 2027-03-22
MS.MS.P3.FAM.001 | 4FA-M - Completion work for Skeleton |  |  | 0 |  | 2027-03-27
MS.MS.P3.MQ.001 | Mosque - Completion work for Skeleton |  |  | 0 |  | 2027-03-27
MS.MS.P3.FAK.001 | 4FA-K - Completion work for Skeleton |  |  | 0 |  | 2027-03-29
MS.MS.P3.FAN.001 | 4FA-N - Completion work for Skeleton |  |  | 0 |  | 2027-03-29
MS.MS.P3.FAO.001 | 4FA-O - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
Phase (4) |  |  |  | 3 | 2027-03-28 | 2027-03-31
MS.MS.P1.FAF.31 | Ph04 -Completion work for substructure Works |  |  | 0 |  | 2027-03-28
MS.MS.P4.FCQ.001 | FC-Q - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
MS.MS.P4.FCD.001 | FC-D - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
Phase (5) |  |  |  | 104 | 2026-11-30 | 2027-03-31
MS.MS.P1.FAF.41 | Ph05 -Completion work for substructure Works |  |  | 0 |  | 2026-11-30
MS.MS.P5.FA.001 | 10FA - Completion work for Skeleton |  |  | 0 |  | 2027-03-31
Pre-Construction Stage |  |  |  | 448 | 01-Oct-25 A | 2027-03-31
Mobilization Work |  |  |  | 448 | 01-Oct-25 A | 2027-03-31
MS.CO.GEN.MO.110 | Time-Related Preliminaries |  |  | 448 | 01-Oct-25 A | 2027-03-31
MS.CO.GEN.MO.160 | Tower Crane – 1st Batch Installation |  |  | 20 | 26-Apr-26 A | 2026-06-15
MS.CO.GEN.MO.170 | Tower Crane – 2st Batch Installation |  |  | 20 | 2026-06-15 | 2026-07-07
MS.CO.GEN.MO.180 | Tower Crane – 3st Batch Installation |  |  | 40 | 2026-08-04 | 2026-09-19
Engineering Works |  |  |  | 275 | 10-Jan-26 A | 2027-01-19
Shopdrawing |  |  |  | 275 | 10-Jan-26 A | 2027-01-19
Shopdrawing Ph01 |  |  |  | 194 | 10-May-26 A | 2026-12-30
MS.EN.P1.ALL.106 | Commencement of Shop Drawing Preparation for Superstructure Works |  |  | 0 | 11-Jun-26*
MS.EN.P1.ALL.109 | ACC Review for Drawing |  |  | 13 | 2026-06-11 | 2026-06-25
MS.EN.P1.ALL.111 | Issuance for IFC Drawing |  |  | 6 | 2026-06-27 | 2026-07-02
Submittal |  |  |  | 184 | 10-May-26 A | 2026-12-19
Sub-structure Drawings |  |  |  | 64 | 10-May-26 A | 2026-07-30
MS.EN.P1.ALL.110 | Submit Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 20 | 10-May-26 A | 2026-06-18
MS.EN.P1.ALL.113 | Submit Structure shop drawings ( Basement Slabs ) |  |  | 20 | 2026-06-22 | 2026-07-14
MS.ES.P01.6FA.B.Gr10 | Block Work Shopdrawing Submittal for Basement Floor |  |  | 8 | 2026-07-22 | 2026-07-30
Super structure Drawings |  |  |  | 144 | 2026-07-04 | 2026-12-19
6FA |  |  |  | 144 | 2026-07-04 | 2026-12-19
MS.ES.P01.6FA.C.LG | Column Shopdrawing Submittal for Lower Ground Floor Floor phase 01 type 6FA |  |  | 6 | 2026-07-04 | 2026-07-09
MS.ES.P01.6FA.S.LG | Slab Shopdrawing Submittal for Lower Ground Floor phase 01 type 6FA |  |  | 10 | 2026-07-11 | 2026-07-21
MS.ES.P01.6FA.C.Gr | Column Shopdrawing Submittal for Ground Floor Floor phase 01 type 6FA |  |  | 6 | 2026-07-22 | 2026-07-28
MS.ES.P01.6FA.S.Gr | Slab Shopdrawing Submittal for Ground Floor Floor phase 01 type 6FA |  |  | 10 | 2026-07-29 | 2026-08-09
MS.ES.P01.6FA.C.1s | Column Shopdrawing Submittal for First Floor Floor phase 01 type 6FA |  |  | 6 | 2026-08-10 | 2026-08-16
MS.ES.P01.6FA.S.1s | Slab Shopdrawing Submittal for First Floor Floor phase 01 type 6FA |  |  | 10 | 2026-08-17 | 2026-08-27
MS.ES.P01.6FA.C.2n | Column Shopdrawing Submittal for Second Floor Floor phase 01 type 6FA |  |  | 6 | 2026-08-29 | 2026-09-03
MS.ES.P01.6FA.S.2n | Slab Shopdrawing Submittal for Second Floor Floor phase 01 type 6FA |  |  | 10 | 2026-09-05 | 2026-09-15
MS.ES.P01.6FA.C.3d | Column Shopdrawing Submittal for Third Floor Floor phase 01 type 6FA |  |  | 6 | 2026-09-16 | 2026-09-22
MS.ES.P01.6FA.S.3d | Slab Shopdrawing Submittal for Third Floor Floor phase 01 type 6FA |  |  | 10 | 2026-09-24 | 2026-10-05
MS.ES.P01.6FA.C.4t | Column Shopdrawing Submittal for Fourth Floor Floor phase 01 type 6FA |  |  | 6 | 2026-10-06 | 2026-10-12
MS.ES.P01.6FA.B.LG | Block Work Shopdrawing Submittal for Lower Ground Floor Floor phase 01 type 6FA |  |  | 8 | 2026-10-06 | 2026-10-14
MS.ES.P01.6FA.S.4t | Slab Shopdrawing Submittal for Fourth Floor Floor phase 01 type 6FA |  |  | 10 | 2026-10-13 | 2026-10-24
MS.ES.P01.6FA.B.Gr | Block Work Shopdrawing Submittal for Ground Floor Floor phase 01 type 6FA |  |  | 8 | 2026-10-15 | 2026-10-24
MS.ES.P01.6FA.C.5t | Column Shopdrawing Submittal for Fifth Floor Floor phase 01 type 6FA |  |  | 6 | 2026-10-25 | 2026-10-31
MS.ES.P01.6FA.B.1s | Block Work Shopdrawing Submittal for First Floor Floor phase 01 type 6FA |  |  | 8 | 2026-10-25 | 2026-11-02
MS.ES.P01.6FA.S.5t | Slab Shopdrawing Submittal for Fifth Floor Floor phase 01 type 6FA |  |  | 10 | 2026-11-01 | 2026-11-11
MS.ES.P01.6FA.B.2n | Block Work Shopdrawing Submittal for Second Floor Floor phase 01 type 6FA |  |  | 8 | 2026-11-03 | 2026-11-11
MS.ES.P01.6FA.C.Pn | Column Shopdrawing Submittal for Penthouse Floor Floor phase 01 type 6FA |  |  | 6 | 2026-11-12 | 2026-11-18
MS.ES.P01.6FA.B.3d | Block Work Shopdrawing Submittal for Third Floor Floor phase 01 type 6FA |  |  | 8 | 2026-11-12 | 2026-11-21
MS.ES.P01.6FA.S.Pn | Slab Shopdrawing Submittal for Penthouse Floor Floor phase 01 type 6FA |  |  | 10 | 2026-11-19 | 2026-11-30
MS.ES.P01.6FA.B.4t | Block Work Shopdrawing Submittal for Fourth Floor Floor phase 01 type 6FA |  |  | 8 | 2026-11-22 | 2026-11-30
MS.ES.P01.6FA.B.5t | Block Work Shopdrawing Submittal for Fifth Floor Floor phase 01 type 6FA |  |  | 8 | 2026-12-01 | 2026-12-09
MS.ES.P01.6FA.B.Pn | Block Work Shopdrawing Submittal for Penthouse Floor Floor phase 01 type 6FA |  |  | 8 | 2026-12-10 | 2026-12-19
Approval |  |  |  | 187 | 23-May-26 A | 2026-12-30
Sub-structure Drawings |  |  |  | 69 | 23-May-26 A | 2026-08-13
MS.EN.P1.ALL.112 | Approval Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 18 | 23-May-26 A | 2026-06-28
MS.EN.P1.ALL.114 | Approval Structure shop drawings ( Basement Slabs ) |  |  | 20 | 2026-06-29 | 2026-07-21
MS.ES.P01.6FA.B.Gr20 | Block Work Shopdrawing Approval for Basement Floor |  |  | 12 | 2026-08-01 | 2026-08-13
Super structure Drawings |  |  |  | 148 | 2026-07-11 | 2026-12-30
6FA |  |  |  | 148 | 2026-07-11 | 2026-12-30
MS.EA.P01.6FA.C.LG | Column Shopdrawing Approval for Lower Ground Floor Floor phase 01 type 6FA |  |  | 12 | 2026-07-11 | 2026-07-23
MS.EA.P01.6FA.S.LG | Slab Shopdrawing Approval for Lower Ground Floor phase 01 type 6FA |  |  | 12 | 2026-07-18 | 2026-07-30
MS.EA.P01.6FA.C.Gr | Column Shopdrawing Approval for Ground Floor Floor phase 01 type 6FA |  |  | 12 | 2026-07-29 | 2026-08-11
MS.EA.P01.6FA.S.Gr | Slab Shopdrawing Approval for Ground Floor Floor phase 01 type 6FA |  |  | 12 | 2026-08-05 | 2026-08-18
MS.EA.P01.6FA.C.1s | Column Shopdrawing Approval for First Floor Floor phase 01 type 6FA |  |  | 12 | 2026-08-17 | 2026-08-30
MS.EA.P01.6FA.S.1s | Slab Shopdrawing Approval for First Floor Floor phase 01 type 6FA |  |  | 12 | 2026-08-24 | 2026-09-06
MS.EA.P01.6FA.C.2n | Column Shopdrawing Approval for Second Floor Floor phase 01 type 6FA |  |  | 12 | 2026-09-05 | 2026-09-17
MS.EA.P01.6FA.S.2n | Slab Shopdrawing Approval for Second Floor Floor phase 01 type 6FA |  |  | 12 | 2026-09-12 | 2026-09-26
MS.EA.P01.6FA.C.3d | Column Shopdrawing Approval for Third Floor Floor phase 01 type 6FA |  |  | 12 | 2026-09-24 | 2026-10-07
MS.EA.P01.6FA.S.3d | Slab Shopdrawing Approval for Third Floor Floor phase 01 type 6FA |  |  | 12 | 2026-10-01 | 2026-10-14
MS.EA.P01.6FA.C.4t | Column Shopdrawing Approval for Fourth Floor Floor phase 01 type 6FA |  |  | 12 | 2026-10-13 | 2026-10-26
MS.EA.P01.6FA.B.LG | Block Work Shopdrawing Approval for Lower Ground Floor Floor phase 01 type 6FA |  |  | 12 | 2026-10-13 | 2026-10-26
MS.EA.P01.6FA.S.4t | Slab Shopdrawing Approval for Fourth Floor Floor phase 01 type 6FA |  |  | 12 | 2026-10-20 | 2026-11-02
MS.EA.P01.6FA.B.Gr | Block Work Shopdrawing Approval for Ground Floor Floor phase 01 type 6FA |  |  | 12 | 2026-10-22 | 2026-11-04
MS.EA.P01.6FA.C.5t | Column Shopdrawing Approval for Fifth Floor Floor phase 01 type 6FA |  |  | 12 | 2026-11-01 | 2026-11-14
MS.EA.P01.6FA.B.1s | Block Work Shopdrawing Approval for First Floor Floor phase 01 type 6FA |  |  | 12 | 2026-11-01 | 2026-11-14
MS.EA.P01.6FA.S.5t | Slab Shopdrawing Approval for Fifth Floor Floor phase 01 type 6FA |  |  | 12 | 2026-11-08 | 2026-11-21
MS.EA.P01.6FA.B.2n | Block Work Shopdrawing Approval for Second Floor Floor phase 01 type 6FA |  |  | 12 | 2026-11-10 | 2026-11-23
MS.EA.P01.6FA.C.Pn | Column Shopdrawing Approval for Penthouse Floor Floor phase 01 type 6FA |  |  | 12 | 2026-11-19 | 2026-12-02
MS.EA.P01.6FA.B.3d | Block Work Shopdrawing Approval for Third Floor Floor phase 01 type 6FA |  |  | 12 | 2026-11-19 | 2026-12-02
MS.EA.P01.6FA.S.Pn | Slab Shopdrawing Approval for Penthouse Floor Floor phase 01 type 6FA |  |  | 12 | 2026-11-26 | 2026-12-09
MS.EA.P01.6FA.B.4t | Block Work Shopdrawing Approval for Fourth Floor Floor phase 01 type 6FA |  |  | 12 | 2026-11-29 | 2026-12-12
MS.EA.P01.6FA.B.5t | Block Work Shopdrawing Approval for Fifth Floor Floor phase 01 type 6FA |  |  | 12 | 2026-12-08 | 2026-12-21
MS.EA.P01.6FA.B.Pn | Block Work Shopdrawing Approval for Penthouse Floor Floor phase 01 type 6FA |  |  | 12 | 2026-12-17 | 2026-12-30
Shopdrawing Ph02 |  |  |  | 270 | 18-Jan-26 A | 2027-01-13
MS.EN.P2.ALL.105 | ACC Review for Drawing |  |  | 15 | 18-Jan-26 A | 2026-06-29
MS.EN.P2.ALL.102 | Commencement of Shop Drawing Preparation for Superstructure Works |  |  | 0 | 2026-06-11
MS.EN.P2.ALL.106 | Issuance for Revised Schematic Drawing |  |  | 5 | 2026-06-30 | 2026-07-05
Submittal |  |  |  | 222 | 01-Apr-26 A | 2027-01-06
Sub-structure Drawings |  |  |  | 82 | 01-Apr-26 A | 2026-07-26
MS.EN.P2.ALL.107 | Submit Structure shop drawings ( Foundation ) |  |  | 15 | 01-Apr-26 A | 2026-06-16
MS.EN.P2.ALL.110 | Submit Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 20 | 2026-06-17 | 2026-07-09
MS.ES.P02.Sub.D. | Drainage Shopdrawing Submittal for phase 02 |  |  | 12 | 2026-06-17 | 2026-06-30
MS.EN.P2.ALL.112 | Submit Structure shop drawings ( Basement Slabs ) |  |  | 20 | 2026-07-04 | 2026-07-26
Super structure Drawings |  |  |  | 140 | 2026-07-27 | 2027-01-06
FB- |  |  |  | 140 | 2026-07-27 | 2027-01-06
MS.ES.P02.FB-.C.Gr | Column Shopdrawing Submittal for Ground Floor Floor phase 02 type FB- |  |  | 8 | 2026-07-27 | 2026-08-04
MS.ES.P02.FB-.S.Gr | Slab Shopdrawing Submittal for Ground Floor Floor phase 02 type FB- |  |  | 12 | 2026-08-05 | 2026-08-18
MS.ES.P02.FB-.C.1s | Column Shopdrawing Submittal for First Floor Floor phase 02 type FB- |  |  | 8 | 2026-08-19 | 2026-08-27
MS.ES.P02.FB-.S.1s | Slab Shopdrawing Submittal for First Floor Floor phase 02 type FB- |  |  | 12 | 2026-08-29 | 2026-09-10
MS.ES.P02.FB-.C.2n | Column Shopdrawing Submittal for Second Floor Floor phase 02 type FB- |  |  | 8 | 2026-09-12 | 2026-09-20
MS.ES.P02.FB-.S.2n | Slab Shopdrawing Submittal for Second Floor Floor phase 02 type FB- |  |  | 12 | 2026-09-21 | 2026-10-05
MS.ES.P02.FB-.C.3d | Column Shopdrawing Submittal for Third Floor Floor phase 02 type FB- |  |  | 8 | 2026-10-06 | 2026-10-14
MS.ES.P02.FB-.S.3d | Slab Shopdrawing Submittal for Third Floor Floor phase 02 type FB- |  |  | 12 | 2026-10-15 | 2026-10-28
MS.ES.P02.FB-.B.Gr | Block Work Shopdrawing Submittal for Ground Floor Floor phase 02 type FB- |  |  | 8 | 2026-10-15 | 2026-10-24
MS.ES.P02.FB-.B.1s | Block Work Shopdrawing Submittal for First Floor Floor phase 02 type FB- |  |  | 8 | 2026-10-25 | 2026-11-02
MS.ES.P02.FB-.C.4t | Column Shopdrawing Submittal for Fourth Floor Floor phase 02 type FB- |  |  | 8 | 2026-10-29 | 2026-11-07
MS.ES.P02.FB-.B.2n | Block Work Shopdrawing Submittal for Second Floor Floor phase 02 type FB- |  |  | 8 | 2026-11-03 | 2026-11-11
MS.ES.P02.FB-.S.4t | Slab Shopdrawing Submittal for Fourth Floor Floor phase 02 type FB- |  |  | 12 | 2026-11-08 | 2026-11-21
MS.ES.P02.FB-.B.3d | Block Work Shopdrawing Submittal for Third Floor Floor phase 02 type FB- |  |  | 8 | 2026-11-12 | 2026-11-21
MS.ES.P02.FB-.C.5t | Column Shopdrawing Submittal for Fifth Floor Floor phase 02 type FB- |  |  | 8 | 2026-11-22 | 2026-11-30
MS.ES.P02.FB-.B.4t | Block Work Shopdrawing Submittal for Fourth Floor Floor phase 02 type FB- |  |  | 8 | 2026-11-22 | 2026-11-30
MS.ES.P02.FB-.S.5t | Slab Shopdrawing Submittal for Fifth Floor Floor phase 02 type FB- |  |  | 12 | 2026-12-01 | 2026-12-14
MS.ES.P02.FB-.B.5t | Block Work Shopdrawing Submittal for Fifth Floor Floor phase 02 type FB- |  |  | 8 | 2026-12-01 | 2026-12-09
MS.ES.P02.FB-.B.Pn | Block Work Shopdrawing Submittal for Penthouse Floor Floor phase 02 type FB- |  |  | 8 | 2026-12-10 | 2026-12-19
MS.ES.P02.FB-.C.Pn | Column Shopdrawing Submittal for Penthouse Floor Floor phase 02 type FB- |  |  | 8 | 2026-12-15 | 2026-12-23
MS.ES.P02.FB-.S.Pn | Slab Shopdrawing Submittal for Penthouse Floor Floor phase 02 type FB- |  |  | 12 | 2026-12-24 | 2027-01-06
RB |  |  |  | 120 | 2026-07-27 | 2026-12-14
MS.ES.P02.RB-.C.Gr | Column Shopdrawing Submittal for Ground Floor Floor phase 02 type RB- |  |  | 8 | 2026-07-27 | 2026-08-04
MS.ES.P02.RB-.S.Gr | Slab Shopdrawing Submittal for Ground Floor Floor phase 02 type RB- |  |  | 12 | 2026-08-05 | 2026-08-18
MS.ES.P02.RB-.C.1s | Column Shopdrawing Submittal for First Floor Floor phase 02 type RB- |  |  | 8 | 2026-08-19 | 2026-08-27
MS.ES.P02.RB-.S.1s | Slab Shopdrawing Submittal for First Floor Floor phase 02 type RB- |  |  | 12 | 2026-08-29 | 2026-09-10
MS.ES.P02.RB-.C.2n | Column Shopdrawing Submittal for Second Floor Floor phase 02 type RB- |  |  | 8 | 2026-09-12 | 2026-09-20
MS.ES.P02.RB-.S.2n | Slab Shopdrawing Submittal for Second Floor Floor phase 02 type RB- |  |  | 12 | 2026-09-21 | 2026-10-05
MS.ES.P02.RB-.C.3d | Column Shopdrawing Submittal for Third Floor Floor phase 02 type RB- |  |  | 8 | 2026-10-06 | 2026-10-14
MS.ES.P02.RB-.S.3d | Slab Shopdrawing Submittal for Third Floor Floor phase 02 type RB- |  |  | 12 | 2026-10-15 | 2026-10-28
MS.ES.P02.RB-.B.Gr | Block Work Shopdrawing Submittal for Ground Floor Floor phase 02 type RB- |  |  | 8 | 2026-10-15 | 2026-10-24
MS.ES.P02.RB-.B.1s | Block Work Shopdrawing Submittal for First Floor Floor phase 02 type RB- |  |  | 8 | 2026-10-25 | 2026-11-02
MS.ES.P02.RB-.C.4t | Column Shopdrawing Submittal for Fourth Floor Floor phase 02 type RB- |  |  | 8 | 2026-10-29 | 2026-11-07
MS.ES.P02.RB-.B.2n | Block Work Shopdrawing Submittal for Second Floor Floor phase 02 type RB- |  |  | 8 | 2026-11-03 | 2026-11-11
MS.ES.P02.RB-.S.4t | Slab Shopdrawing Submittal for Fourth Floor Floor phase 02 type RB- |  |  | 12 | 2026-11-08 | 2026-11-21
MS.ES.P02.RB-.B.3d | Block Work Shopdrawing Submittal for Third Floor Floor phase 02 type RB- |  |  | 8 | 2026-11-12 | 2026-11-21
MS.ES.P02.RB-.C.5t | Column Shopdrawing Submittal for Fifth Floor Floor phase 02 type RB- |  |  | 8 | 2026-11-22 | 2026-11-30
MS.ES.P02.RB-.B.4t | Block Work Shopdrawing Submittal for Fourth Floor Floor phase 02 type RB- |  |  | 8 | 2026-11-22 | 2026-11-30
MS.ES.P02.RB-.S.5t | Slab Shopdrawing Submittal for Fifth Floor Floor phase 02 type RB- |  |  | 12 | 2026-12-01 | 2026-12-14
MS.ES.P02.RB-.B.5t | Block Work Shopdrawing Submittal for Fifth Floor Floor phase 02 type RB- |  |  | 8 | 2026-12-01 | 2026-12-09
Hotal |  |  |  | 140 | 2026-07-27 | 2027-01-06
MS.ES.P02.Hot.C.Gr | Column Shopdrawing Submittal for Ground Floor Floor phase 02 type Hot |  |  | 8 | 2026-07-27 | 2026-08-04
MS.ES.P02.Hot.S.Gr | Slab Shopdrawing Submittal for Ground Floor Floor phase 02 type Hot |  |  | 12 | 2026-08-05 | 2026-08-18
MS.ES.P02.Hot.C.Me | Column Shopdrawing Submittal for Mezzanine Floor Floor phase 02 type Hot |  |  | 8 | 2026-08-19 | 2026-08-27
MS.ES.P02.Hot.S.Me | Slab Shopdrawing Submittal for Mezzanine Floor Floor phase 02 type Hot |  |  | 12 | 2026-08-29 | 2026-09-10
MS.ES.P02.Hot.C.1s | Column Shopdrawing Submittal for First Floor Floor phase 02 type Hot |  |  | 8 | 2026-09-12 | 2026-09-20
MS.ES.P02.Hot.S.1s | Slab Shopdrawing Submittal for First Floor Floor phase 02 type Hot |  |  | 12 | 2026-09-21 | 2026-10-05
MS.ES.P02.Hot.C.2n | Column Shopdrawing Submittal for Second Floor Floor phase 02 type Hot |  |  | 8 | 2026-10-06 | 2026-10-14
MS.ES.P02.Hot.S.2n | Slab Shopdrawing Submittal for Second Floor Floor phase 02 type Hot |  |  | 12 | 2026-10-15 | 2026-10-28
MS.ES.P02.Hot.C.3d | Column Shopdrawing Submittal for Third Floor Floor phase 02 type Hot |  |  | 8 | 2026-10-29 | 2026-11-07
MS.ES.P02.Hot.S.3d | Slab Shopdrawing Submittal for Third Floor Floor phase 02 type Hot |  |  | 12 | 2026-11-08 | 2026-11-21
MS.ES.P02.Hot.C.4t | Column Shopdrawing Submittal for Fourth Floor Floor phase 02 type Hot |  |  | 8 | 2026-11-22 | 2026-11-30
MS.ES.P02.Hot.S.4t | Slab Shopdrawing Submittal for Fourth Floor Floor phase 02 type Hot |  |  | 12 | 2026-12-01 | 2026-12-14
MS.ES.P02.Hot.C.5t | Column Shopdrawing Submittal for Fifth Floor Floor phase 02 type Hot |  |  | 8 | 2026-12-15 | 2026-12-23
MS.ES.P02.Hot.S.5t | Slab Shopdrawing Submittal for Fifth Floor Floor phase 02 type Hot |  |  | 12 | 2026-12-24 | 2027-01-06
Approval |  |  |  | 192 | 01-Apr-26 A | 2027-01-13
Sub-structure Drawings |  |  |  | 52 | 01-Apr-26 A | 2026-08-02
MS.EA.P02.Sub.E. | Earthing Shopdrawing Approval for Floor phase 02 type Sub |  |  | 12 | 01-Apr-26 A | 2026-06-14
MS.EN.P2.ALL.111 | Approval Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 20 | 2026-06-24 | 2026-07-16
MS.EA.P02.Sub.D. | Drainage Shopdrawing Approval for Floor phase 02 type Sub |  |  | 12 | 2026-06-24 | 2026-07-07
MS.EN.P2.ALL.109 | Approval Structure shop drawings ( Foundation ) |  |  | 12 | 30-Jun-26 A | 2026-06-24
MS.EN.P2.ALL.113 | Approval Structure shop drawings (Basement Slabs ) |  |  | 20 | 2026-07-11 | 2026-08-02
Super structure Drawings |  |  |  | 140 | 2026-08-03 | 2027-01-13
FB- |  |  |  | 140 | 2026-08-03 | 2027-01-13
MS.EA.P02.FB-.C.Gr | Column Shopdrawing Approval for Ground Floor Floor phase 02 type FB- |  |  | 12 | 2026-08-03 | 2026-08-16
MS.EA.P02.FB-.S.Gr | Slab Shopdrawing Approval for Ground Floor Floor phase 02 type FB- |  |  | 12 | 2026-08-12 | 2026-08-25
MS.EA.P02.FB-.C.1s | Column Shopdrawing Approval for First Floor Floor phase 02 type FB- |  |  | 12 | 2026-08-26 | 2026-09-08
MS.EA.P02.FB-.S.1s | Slab Shopdrawing Approval for First Floor Floor phase 02 type FB- |  |  | 12 | 2026-09-05 | 2026-09-17
MS.EA.P02.FB-.C.2n | Column Shopdrawing Approval for Second Floor Floor phase 02 type FB- |  |  | 12 | 2026-09-19 | 2026-10-03
MS.EA.P02.FB-.S.2n | Slab Shopdrawing Approval for Second Floor Floor phase 02 type FB- |  |  | 12 | 2026-09-29 | 2026-10-12
MS.EA.P02.FB-.C.3d | Column Shopdrawing Approval for Third Floor Floor phase 02 type FB- |  |  | 12 | 2026-10-13 | 2026-10-26
MS.EA.P02.FB-.B.Gr | Block Work Shopdrawing Approval for Ground Floor Floor phase 02 type FB- |  |  | 12 | 2026-10-18 | 2026-10-31
MS.EA.P02.FB-.S.3d | Slab Shopdrawing Approval for Third Floor Floor phase 02 type FB- |  |  | 12 | 2026-10-22 | 2026-11-04
MS.EA.P02.FB-.B.1s | Block Work Shopdrawing Approval for First Floor Floor phase 02 type FB- |  |  | 12 | 2026-11-01 | 2026-11-14
MS.EA.P02.FB-.C.4t | Column Shopdrawing Approval for Fourth Floor Floor phase 02 type FB- |  |  | 12 | 2026-11-05 | 2026-11-18
MS.EA.P02.FB-.B.2n | Block Work Shopdrawing Approval for Second Floor Floor phase 02 type FB- |  |  | 12 | 2026-11-10 | 2026-11-23
MS.EA.P02.FB-.S.4t | Slab Shopdrawing Approval for Fourth Floor Floor phase 02 type FB- |  |  | 12 | 2026-11-15 | 2026-11-28
MS.EA.P02.FB-.B.3d | Block Work Shopdrawing Approval for Third Floor Floor phase 02 type FB- |  |  | 12 | 2026-11-19 | 2026-12-02
MS.EA.P02.FB-.C.5t | Column Shopdrawing Approval for Fifth Floor Floor phase 02 type FB- |  |  | 12 | 2026-11-29 | 2026-12-12
MS.EA.P02.FB-.B.4t | Block Work Shopdrawing Approval for Fourth Floor Floor phase 02 type FB- |  |  | 12 | 2026-11-29 | 2026-12-12
MS.EA.P02.FB-.S.5t | Slab Shopdrawing Approval for Fifth Floor Floor phase 02 type FB- |  |  | 12 | 2026-12-08 | 2026-12-21
MS.EA.P02.FB-.B.5t | Block Work Shopdrawing Approval for Fifth Floor Floor phase 02 type FB- |  |  | 12 | 2026-12-08 | 2026-12-21
MS.EA.P02.FB-.B.Pn | Block Work Shopdrawing Approval for Penthouse Floor Floor phase 02 type FB- |  |  | 12 | 2026-12-17 | 2026-12-30
MS.EA.P02.FB-.C.Pn | Column Shopdrawing Approval for Penthouse Floor Floor phase 02 type FB- |  |  | 12 | 2026-12-22 | 2027-01-04
MS.EA.P02.FB-.S.Pn | Slab Shopdrawing Approval for Penthouse Floor Floor phase 02 type FB- |  |  | 12 | 2026-12-31 | 2027-01-13
RB |  |  |  | 120 | 2026-08-03 | 2026-12-21
MS.EA.P02.RB-.C.Gr | Column Shopdrawing Approval for Ground Floor Floor phase 02 type RB- |  |  | 12 | 2026-08-03 | 2026-08-16
MS.EA.P02.RB-.S.Gr | Slab Shopdrawing Approval for Ground Floor Floor phase 02 type RB- |  |  | 12 | 2026-08-12 | 2026-08-25
MS.EA.P02.RB-.C.1s | Column Shopdrawing Approval for First Floor Floor phase 02 type RB- |  |  | 12 | 2026-08-26 | 2026-09-08
MS.EA.P02.RB-.S.1s | Slab Shopdrawing Approval for First Floor Floor phase 02 type RB- |  |  | 12 | 2026-09-05 | 2026-09-17
MS.EA.P02.RB-.C.2n | Column Shopdrawing Approval for Second Floor Floor phase 02 type RB- |  |  | 12 | 2026-09-19 | 2026-10-03
MS.EA.P02.RB-.S.2n | Slab Shopdrawing Approval for Second Floor Floor phase 02 type RB- |  |  | 12 | 2026-09-29 | 2026-10-12
MS.EA.P02.RB-.C.3d | Column Shopdrawing Approval for Third Floor Floor phase 02 type RB- |  |  | 12 | 2026-10-13 | 2026-10-26
MS.EA.P02.RB-.B.Gr | Block Work Shopdrawing Approval for Ground Floor Floor phase 02 type RB- |  |  | 12 | 2026-10-18 | 2026-10-31
MS.EA.P02.RB-.S.3d | Slab Shopdrawing Approval for Third Floor Floor phase 02 type RB- |  |  | 12 | 2026-10-22 | 2026-11-04
MS.EA.P02.RB-.B.1s | Block Work Shopdrawing Approval for First Floor Floor phase 02 type RB- |  |  | 12 | 2026-11-01 | 2026-11-14
MS.EA.P02.RB-.C.4t | Column Shopdrawing Approval for Fourth Floor Floor phase 02 type RB- |  |  | 12 | 2026-11-05 | 2026-11-18
MS.EA.P02.RB-.B.2n | Block Work Shopdrawing Approval for Second Floor Floor phase 02 type RB- |  |  | 12 | 2026-11-10 | 2026-11-23
MS.EA.P02.RB-.S.4t | Slab Shopdrawing Approval for Fourth Floor Floor phase 02 type RB- |  |  | 12 | 2026-11-15 | 2026-11-28
MS.EA.P02.RB-.B.3d | Block Work Shopdrawing Approval for Third Floor Floor phase 02 type RB- |  |  | 12 | 2026-11-19 | 2026-12-02
MS.EA.P02.RB-.C.5t | Column Shopdrawing Approval for Fifth Floor Floor phase 02 type RB- |  |  | 12 | 2026-11-29 | 2026-12-12
MS.EA.P02.RB-.B.4t | Block Work Shopdrawing Approval for Fourth Floor Floor phase 02 type RB- |  |  | 12 | 2026-11-29 | 2026-12-12
MS.EA.P02.RB-.S.5t | Slab Shopdrawing Approval for Fifth Floor Floor phase 02 type RB- |  |  | 12 | 2026-12-08 | 2026-12-21
MS.EA.P02.RB-.B.5t | Block Work Shopdrawing Approval for Fifth Floor Floor phase 02 type RB- |  |  | 12 | 2026-12-08 | 2026-12-21
Hotal |  |  |  | 140 | 2026-08-03 | 2027-01-13
MS.EA.P02.Hot.C.Gr | Column Shopdrawing Approval for Ground Floor Floor phase 02 type Hot |  |  | 12 | 2026-08-03 | 2026-08-16
MS.EA.P02.Hot.S.Gr | Slab Shopdrawing Approval for Ground Floor Floor phase 02 type Hot |  |  | 12 | 2026-08-12 | 2026-08-25
MS.EA.P02.Hot.C.Me | Column Shopdrawing Approval for Mezzanine Floor Floor phase 02 type Hot |  |  | 12 | 2026-08-26 | 2026-09-08
MS.EA.P02.Hot.S.Me | Slab Shopdrawing Approval for Mezzanine Floor Floor phase 02 type Hot |  |  | 12 | 2026-09-05 | 2026-09-17
MS.EA.P02.Hot.C.1s | Column Shopdrawing Approval for First Floor Floor phase 02 type Hot |  |  | 12 | 2026-09-19 | 2026-10-03
MS.EA.P02.Hot.S.1s | Slab Shopdrawing Approval for First Floor Floor phase 02 type Hot |  |  | 12 | 2026-09-29 | 2026-10-12
MS.EA.P02.Hot.C.2n | Column Shopdrawing Approval for Second Floor Floor phase 02 type Hot |  |  | 12 | 2026-10-13 | 2026-10-26
MS.EA.P02.Hot.S.2n | Slab Shopdrawing Approval for Second Floor Floor phase 02 type Hot |  |  | 12 | 2026-10-22 | 2026-11-04
MS.EA.P02.Hot.C.3d | Column Shopdrawing Approval for Third Floor Floor phase 02 type Hot |  |  | 12 | 2026-11-05 | 2026-11-18
MS.EA.P02.Hot.S.3d | Slab Shopdrawing Approval for Third Floor Floor phase 02 type Hot |  |  | 12 | 2026-11-15 | 2026-11-28
MS.EA.P02.Hot.C.4t | Column Shopdrawing Approval for Fourth Floor Floor phase 02 type Hot |  |  | 12 | 2026-11-29 | 2026-12-12
MS.EA.P02.Hot.S.4t | Slab Shopdrawing Approval for Fourth Floor Floor phase 02 type Hot |  |  | 12 | 2026-12-08 | 2026-12-21
MS.EA.P02.Hot.C.5t | Column Shopdrawing Approval for Fifth Floor Floor phase 02 type Hot |  |  | 12 | 2026-12-22 | 2027-01-04
MS.EA.P02.Hot.S.5t | Slab Shopdrawing Approval for Fifth Floor Floor phase 02 type Hot |  |  | 12 | 2026-12-31 | 2027-01-13
Shopdrawing Ph03 |  |  |  | 198 | 30-May-26 A | 2027-01-18
MS.EN.P3.ALL.106 | Issuance for Revised Schematic Drawing |  |  | 5 | 2026-06-11 | 2026-06-16
Submittal |  |  |  | 192 | 30-May-26 A | 2027-01-11
Sub-structure Drawings |  |  |  | 48 | 30-May-26 A | 2026-07-26
MS.EN.P3.ALL.110 | Submit Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 20 | 30-May-26 A | 2026-06-22
MS.EN.P3.ALL.112 | Submit Structure shop drawings ( Basement Slabs ) |  |  | 20 | 2026-07-04 | 2026-07-26
Super structure Drawings |  |  |  | 144 | 2026-07-27 | 2027-01-11
4FA |  |  |  | 144 | 2026-07-27 | 2027-01-11
MS.ES.P03.4FA.C.LG | Column Shopdrawing Submittal for Lower Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-07-27 | 2026-08-09
MS.ES.P03.4FA.S.LG | Slab Shopdrawing Submittal for Lower Ground Floor phase 03 type 4FA |  |  | 12 | 2026-08-10 | 2026-08-23
MS.ES.P03.4FA.C.Gr | Column Shopdrawing Submittal for Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-08-24 | 2026-09-06
MS.ES.P03.4FA.S.Gr | Slab Shopdrawing Submittal for Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-09-07 | 2026-09-20
MS.ES.P03.4FA.C.1s | Column Shopdrawing Submittal for First Floor Floor phase 03 type 4FA |  |  | 12 | 2026-09-21 | 2026-10-05
MS.ES.P03.4FA.S.1s | Slab Shopdrawing Submittal for First Floor Floor phase 03 type 4FA |  |  | 12 | 2026-10-06 | 2026-10-19
MS.ES.P03.4FA.C.2n | Column Shopdrawing Submittal for Second Floor Floor phase 03 type 4FA |  |  | 12 | 2026-10-20 | 2026-11-02
MS.ES.P03.4FA.B.LG | Block Work Shopdrawing Submittal for Lower Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-10-20 | 2026-11-02
MS.ES.P03.4FA.S.2n | Slab Shopdrawing Submittal for Second Floor Floor phase 03 type 4FA |  |  | 12 | 2026-11-03 | 2026-11-16
MS.ES.P03.4FA.B.Gr | Block Work Shopdrawing Submittal for Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-11-03 | 2026-11-16
MS.ES.P03.4FA.C.3d | Column Shopdrawing Submittal for Third Floor Floor phase 03 type 4FA |  |  | 12 | 2026-11-17 | 2026-11-30
MS.ES.P03.4FA.B.1s | Block Work Shopdrawing Submittal for First Floor Floor phase 03 type 4FA |  |  | 12 | 2026-11-17 | 2026-11-30
MS.ES.P03.4FA.S.3d | Slab Shopdrawing Submittal for Third Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-01 | 2026-12-14
MS.ES.P03.4FA.B.2n | Block Work Shopdrawing Submittal for Second Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-01 | 2026-12-14
MS.ES.P03.4FA.C.Pn | Column Shopdrawing Submittal for Penthouse Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-15 | 2026-12-28
MS.ES.P03.4FA.B.3d | Block Work Shopdrawing Submittal for Third Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-15 | 2026-12-28
MS.ES.P03.4FA.S.Pn | Slab Shopdrawing Submittal for Penthouse Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-29 | 2027-01-11
MS.ES.P03.4FA.B.Pn | Block Work Shopdrawing Submittal for Penthouse Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-29 | 2027-01-11
Mosqu |  |  |  | 72 | 2026-09-21 | 2026-12-14
MS.ES.P03.MoS.C.Gr | Column Shopdrawing Submittal for Ground Floor Floor phase 03 type MoS |  |  | 12 | 2026-09-21 | 2026-10-05
MS.ES.P03.MoS.S.Gr | Slab Shopdrawing Submittal for Ground Floor Floor phase 03 type MoS |  |  | 12 | 2026-10-06 | 2026-10-19
MS.ES.P03.MoS.C.1s | Column Shopdrawing Submittal for First Floor Floor phase 03 type MoS |  |  | 12 | 2026-10-20 | 2026-11-02
MS.ES.P03.MoS.S.1s | Slab Shopdrawing Submittal for First Floor Floor phase 03 type MoS |  |  | 12 | 2026-11-03 | 2026-11-16
MS.ES.P03.MoS.B.Gr | Block Work Shopdrawing Submittal for Ground Floor Floor phase 03 type MoS |  |  | 12 | 2026-11-17 | 2026-11-30
MS.ES.P03.MoS.B.1s | Block Work Shopdrawing Submittal for First Floor Floor phase 03 type MoS |  |  | 12 | 2026-12-01 | 2026-12-14
Approval |  |  |  | 195 | 31-May-26 A | 2027-01-18
Sub-structure Drawings |  |  |  | 51 | 31-May-26 A | 2026-08-02
MS.EN.P3.ALL.111 | Approval Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 20 | 31-May-26 A | 2026-06-28
MS.EN.P3.ALL.113 | Approval Structure shop drawings ( Slabs ) |  |  | 20 | 2026-07-11 | 2026-08-02
Super structure Drawings |  |  |  | 144 | 2026-08-03 | 2027-01-18
4FA |  |  |  | 144 | 2026-08-03 | 2027-01-18
MS.EA.P03.4FA.C.LG | Column Shopdrawing Approval for Lower Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-08-03 | 2026-08-16
MS.EA.P03.4FA.S.LG | Slab Shopdrawing Approval for Lower Ground Floor phase 03 type 4FA |  |  | 12 | 2026-08-17 | 2026-08-30
MS.EA.P03.4FA.C.Gr | Column Shopdrawing Approval for Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-08-31 | 2026-09-13
MS.EA.P03.4FA.S.Gr | Slab Shopdrawing Approval for Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-09-14 | 2026-09-28
MS.EA.P03.4FA.C.1s | Column Shopdrawing Approval for First Floor Floor phase 03 type 4FA |  |  | 12 | 2026-09-29 | 2026-10-12
MS.EA.P03.4FA.S.1s | Slab Shopdrawing Approval for First Floor Floor phase 03 type 4FA |  |  | 12 | 2026-10-13 | 2026-10-26
MS.EA.P03.4FA.C.2n | Column Shopdrawing Approval for Second Floor Floor phase 03 type 4FA |  |  | 12 | 2026-10-27 | 2026-11-09
MS.EA.P03.4FA.B.LG | Block Work Shopdrawing Approval for Lower Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-10-27 | 2026-11-09
MS.EA.P03.4FA.S.2n | Slab Shopdrawing Approval for Second Floor Floor phase 03 type 4FA |  |  | 12 | 2026-11-10 | 2026-11-23
MS.EA.P03.4FA.B.Gr | Block Work Shopdrawing Approval for Ground Floor Floor phase 03 type 4FA |  |  | 12 | 2026-11-10 | 2026-11-23
MS.EA.P03.4FA.C.3d | Column Shopdrawing Approval for Third Floor Floor phase 03 type 4FA |  |  | 12 | 2026-11-24 | 2026-12-07
MS.EA.P03.4FA.B.1s | Block Work Shopdrawing Approval for First Floor Floor phase 03 type 4FA |  |  | 12 | 2026-11-24 | 2026-12-07
MS.EA.P03.4FA.S.3d | Slab Shopdrawing Approval for Third Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-08 | 2026-12-21
MS.EA.P03.4FA.B.2n | Block Work Shopdrawing Approval for Second Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-08 | 2026-12-21
MS.EA.P03.4FA.C.Pn | Column Shopdrawing Approval for Penthouse Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-22 | 2027-01-04
MS.EA.P03.4FA.B.3d | Block Work Shopdrawing Approval for Third Floor Floor phase 03 type 4FA |  |  | 12 | 2026-12-22 | 2027-01-04
MS.EA.P03.4FA.S.Pn | Slab Shopdrawing Approval for Penthouse Floor Floor phase 03 type 4FA |  |  | 12 | 2027-01-05 | 2027-01-18
MS.EA.P03.4FA.B.Pn | Block Work Shopdrawing Approval for Penthouse Floor Floor phase 03 type 4FA |  |  | 12 | 2027-01-05 | 2027-01-18
Mosqu |  |  |  | 72 | 2026-09-29 | 2026-12-21
MS.EA.P03.MoS.C.Gr | Column Shopdrawing Approval for Ground Floor Floor phase 03 type MoS |  |  | 12 | 2026-09-29 | 2026-10-12
MS.EA.P03.MoS.S.Gr | Slab Shopdrawing Approval for Ground Floor Floor phase 03 type MoS |  |  | 12 | 2026-10-13 | 2026-10-26
MS.EA.P03.MoS.C.1s | Column Shopdrawing Approval for First Floor Floor phase 03 type MoS |  |  | 12 | 2026-10-27 | 2026-11-09
MS.EA.P03.MoS.S.1s | Slab Shopdrawing Approval for First Floor Floor phase 03 type MoS |  |  | 12 | 2026-11-10 | 2026-11-23
MS.EA.P03.MoS.B.Gr | Block Work Shopdrawing Approval for Ground Floor Floor phase 03 type MoS |  |  | 12 | 2026-11-24 | 2026-12-07
MS.EA.P03.MoS.B.1s | Block Work Shopdrawing Approval for First Floor Floor phase 03 type MoS |  |  | 12 | 2026-12-08 | 2026-12-21
Shopdrawing Ph04 |  |  |  | 185 | 2026-06-11 | 2027-01-13
MS.EN.P4.ALL.101 | Commencement of Shop Drawing Preparation for Superstructure Works |  |  | 0 | 2026-06-11
MS.EN.P4.ALL.103 | ACC Review for Drawing |  |  | 11 | 2026-06-11 | 2026-06-23
MS.EN.P4.ALL.105 | Issuance for Revised Schematic Drawing |  |  | 7 | 2026-06-24 | 2026-07-01
Submittal |  |  |  | 175 | 2026-06-11 | 2027-01-02
Sub-structure Drawings |  |  |  | 75 | 2026-06-11 | 2026-09-06
MS.ES.P04.Sub.E. | Earthing Shopdrawing Submittal for phase 04 |  |  | 12 | 2026-06-11 | 2026-06-24
MS.EN.P4.ALL.106 | Submit Structure shop drawings ( Foundation ) |  |  | 19 | 2026-07-02 | 2026-07-23
MS.ES.P04.Sub.D. | Drainage Shopdrawing Submittal for phase 04 |  |  | 12 | 2026-07-25 | 2026-08-06
MS.EN.P4.ALL.108 | Submit Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 20 | 2026-08-08 | 2026-08-30
MS.EN.P4.ALL.110 | Submit Structure shop drawings ( Basement Slabs ) |  |  | 20 | 2026-08-15 | 2026-09-06
Super structure Drawings |  |  |  | 100 | 2026-09-07 | 2027-01-02
FC |  |  |  | 100 | 2026-09-07 | 2027-01-02
MS.ES.P04.FC-.C.Gr | Column Shopdrawing Submittal for Ground Floor Floor phase 04 type FC- |  |  | 10 | 2026-09-07 | 2026-09-17
MS.ES.P04.FC-.S.Gr | Slab Shopdrawing Submittal for Ground Floor Floor phase 04 type FC- |  |  | 10 | 2026-09-19 | 2026-09-30
MS.ES.P04.FC-.C.1s | Column Shopdrawing Submittal for First Floor Floor phase 04 type FC- |  |  | 10 | 2026-10-01 | 2026-10-12
MS.ES.P04.FC-.S.1s | Slab Shopdrawing Submittal for First Floor Floor phase 04 type FC- |  |  | 10 | 2026-10-13 | 2026-10-24
MS.ES.P04.FC-.C.2n | Column Shopdrawing Submittal for Second Floor Floor phase 04 type FC- |  |  | 10 | 2026-10-25 | 2026-11-04
MS.ES.P04.FC-.B.Gr | Block Work Shopdrawing Submittal for Ground Floor Floor phase 04 type FC- |  |  | 10 | 2026-10-25 | 2026-11-04
MS.ES.P04.FC-.S.2n | Slab Shopdrawing Submittal for Second Floor Floor phase 04 type FC- |  |  | 10 | 2026-11-05 | 2026-11-16
MS.ES.P04.FC-.B.1s | Block Work Shopdrawing Submittal for First Floor Floor phase 04 type FC- |  |  | 10 | 2026-11-05 | 2026-11-16
MS.ES.P04.FC-.C.3d | Column Shopdrawing Submittal for Third Floor Floor phase 04 type FC- |  |  | 10 | 2026-11-17 | 2026-11-28
MS.ES.P04.FC-.B.2n | Block Work Shopdrawing Submittal for Second Floor Floor phase 04 type FC- |  |  | 10 | 2026-11-17 | 2026-11-28
MS.ES.P04.FC-.S.3d | Slab Shopdrawing Submittal for Third Floor Floor phase 04 type FC- |  |  | 10 | 2026-11-29 | 2026-12-09
MS.ES.P04.FC-.B.3d | Block Work Shopdrawing Submittal for Third Floor Floor phase 04 type FC- |  |  | 10 | 2026-11-29 | 2026-12-09
MS.ES.P04.FC-.C.Pn | Column Shopdrawing Submittal for Penthouse Floor Floor phase 04 type FC- |  |  | 10 | 2026-12-10 | 2026-12-21
MS.ES.P04.FC-.B.Pn | Block Work Shopdrawing Submittal for Penthouse Floor Floor phase 04 type FC- |  |  | 10 | 2026-12-10 | 2026-12-21
MS.ES.P04.FC-.S.Pn | Slab Shopdrawing Submittal for Penthouse Floor Floor phase 04 type FC- |  |  | 10 | 2026-12-22 | 2027-01-02
Approval |  |  |  | 179 | 2026-06-18 | 2027-01-13
Sub-structure Drawings |  |  |  | 86 | 2026-06-18 | 2026-09-28
MS.EA.P04.Sub.E. | Earthing Shopdrawing Approval for Floor phase 04 type Sub |  |  | 12 | 2026-06-18 | 2026-07-01
MS.EN.P4.ALL.107 | Approval Structure shop drawings ( Foundation ) |  |  | 19 | 2026-07-13 | 2026-08-03
MS.EA.P04.Sub.D. | Drainage Shopdrawing Approval for Floor phase 04 type Sub |  |  | 12 | 2026-08-01 | 2026-08-13
MS.EN.P4.ALL.109 | Approval Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 19 | 2026-08-16 | 2026-09-06
MS.EN.P4.ALL.112 | Approval Structure shop drawings ( Slabs ) |  |  | 31 | 2026-08-22 | 2026-09-28
Super structure Drawings |  |  |  | 104 | 2026-09-14 | 2027-01-13
FC |  |  |  | 104 | 2026-09-14 | 2027-01-13
MS.EA.P04.FC-.C.Gr | Column Shopdrawing Approval for Ground Floor Floor phase 04 type FC- |  |  | 12 | 2026-09-14 | 2026-09-28
MS.EA.P04.FC-.S.Gr | Slab Shopdrawing Approval for Ground Floor Floor phase 04 type FC- |  |  | 12 | 2026-09-27 | 2026-10-10
MS.EA.P04.FC-.C.1s | Column Shopdrawing Approval for First Floor Floor phase 04 type FC- |  |  | 12 | 2026-10-08 | 2026-10-21
MS.EA.P04.FC-.S.1s | Slab Shopdrawing Approval for First Floor Floor phase 04 type FC- |  |  | 12 | 2026-10-20 | 2026-11-02
MS.EA.P04.FC-.C.2n | Column Shopdrawing Approval for Second Floor Floor phase 04 type FC- |  |  | 12 | 2026-11-01 | 2026-11-14
MS.EA.P04.FC-.B.Gr | Block Work Shopdrawing Approval for Ground Floor Floor phase 04 type FC- |  |  | 12 | 2026-11-01 | 2026-11-14
MS.EA.P04.FC-.S.2n | Slab Shopdrawing Approval for Second Floor Floor phase 04 type FC- |  |  | 12 | 2026-11-12 | 2026-11-25
MS.EA.P04.FC-.B.1s | Block Work Shopdrawing Approval for First Floor Floor phase 04 type FC- |  |  | 12 | 2026-11-12 | 2026-11-25
MS.EA.P04.FC-.C.3d | Column Shopdrawing Approval for Third Floor Floor phase 04 type FC- |  |  | 12 | 2026-11-24 | 2026-12-07
MS.EA.P04.FC-.B.2n | Block Work Shopdrawing Approval for Second Floor Floor phase 04 type FC- |  |  | 12 | 2026-11-24 | 2026-12-07
MS.EA.P04.FC-.S.3d | Slab Shopdrawing Approval for Third Floor Floor phase 04 type FC- |  |  | 12 | 2026-12-06 | 2026-12-19
MS.EA.P04.FC-.B.3d | Block Work Shopdrawing Approval for Third Floor Floor phase 04 type FC- |  |  | 12 | 2026-12-06 | 2026-12-19
MS.EA.P04.FC-.C.Pn | Column Shopdrawing Approval for Penthouse Floor Floor phase 04 type FC- |  |  | 12 | 2026-12-17 | 2026-12-30
MS.EA.P04.FC-.B.Pn | Block Work Shopdrawing Approval for Penthouse Floor Floor phase 04 type FC- |  |  | 12 | 2026-12-17 | 2026-12-30
MS.EA.P04.FC-.S.Pn | Slab Shopdrawing Approval for Penthouse Floor Floor phase 04 type FC- |  |  | 12 | 2026-12-31 | 2027-01-13
Shopdrawing Ph05 |  |  |  | 270 | 10-Jan-26 A | 2027-01-19
MS.EN.P5.ALL.105 | ACC Review for Drawing |  |  | 3 | 10-Jan-26 A | 2026-06-15
MS.EN.P5.ALL.108 | Issuance for Revised Schematic Drawing |  |  | 5 | 2026-06-16 | 2026-06-21
Submittal |  |  |  | 182 | 2026-06-11 | 2027-01-10
Sub-structure Drawings |  |  |  | 40 | 2026-06-11 | 2026-07-27
MS.EN.P5.ALL.112 | Submit Structure shop drawings ( Vertical Elements - Walls & Columns) For Sub-structure Works |  |  | 20 | 2026-06-11 | 2026-07-04
MS.EN.P5.ALL.114 | Submit Structure shop drawings ( Basement Slabs ) |  |  | 20 | 2026-07-05 | 2026-07-27
Super structure Drawings |  |  |  | 142 | 2026-07-28 | 2027-01-10
FAJ |  |  |  | 142 | 2026-07-28 | 2027-01-10
MS.ES.P05.FAJ.C.LG | Column Shopdrawing Submittal for Lower Ground Floor Floor phase 05 type FAJ |  |  | 6 | 2026-07-28 | 2026-08-03
MS.ES.P05.FAJ.S.LG | Slab Shopdrawing Submittal for Lower Ground Floor phase 05 type FAJ |  |  | 8 | 2026-08-04 | 2026-08-12
MS.ES.P05.FAJ.C.Gr | Column Shopdrawing Submittal for Ground Floor Floor phase 05 type FAJ |  |  | 6 | 2026-08-13 | 2026-08-19
MS.ES.P05.FAJ.S.Gr | Slab Shopdrawing Submittal for Ground Floor Floor phase 05 type FAJ |  |  | 8 | 2026-08-20 | 2026-08-29
MS.ES.P05.FAJ.C.1s | Column Shopdrawing Submittal for First Floor Floor phase 05 type FAJ |  |  | 6 | 2026-08-30 | 2026-09-05
MS.ES.P05.FAJ.S.1s | Slab Shopdrawing Submittal for First Floor Floor phase 05 type FAJ |  |  | 8 | 2026-09-06 | 2026-09-14
MS.ES.P05.FAJ.B.LG | Block Work Shopdrawing Submittal for Lower Ground Floor Floor phase 05 type FAJ |  |  | 6 | 2026-09-06 | 2026-09-12
MS.ES.P05.FAJ.B.Gr | Block Work Shopdrawing Submittal for Ground Floor Floor phase 05 type FAJ |  |  | 6 | 2026-09-13 | 2026-09-19
MS.ES.P05.FAJ.C.2n | Column Shopdrawing Submittal for Second Floor Floor phase 05 type FAJ |  |  | 6 | 2026-09-15 | 2026-09-21
MS.ES.P05.FAJ.B.1s | Block Work Shopdrawing Submittal for First Floor Floor phase 05 type FAJ |  |  | 6 | 2026-09-20 | 2026-09-27
MS.ES.P05.FAJ.S.2n | Slab Shopdrawing Submittal for Second Floor Floor phase 05 type FAJ |  |  | 8 | 2026-09-22 | 2026-10-01
MS.ES.P05.FAJ.B.2n | Block Work Shopdrawing Submittal for Second Floor Floor phase 05 type FAJ |  |  | 6 | 2026-09-28 | 2026-10-04
MS.ES.P05.FAJ.C.3d | Column Shopdrawing Submittal for Third Floor Floor phase 05 type FAJ |  |  | 6 | 2026-10-03 | 2026-10-08
MS.ES.P05.FAJ.B.3d | Block Work Shopdrawing Submittal for Third Floor Floor phase 05 type FAJ |  |  | 6 | 2026-10-05 | 2026-10-11
MS.ES.P05.FAJ.S.3d | Slab Shopdrawing Submittal for Third Floor Floor phase 05 type FAJ |  |  | 8 | 2026-10-10 | 2026-10-18
MS.ES.P05.FAJ.B.4t | Block Work Shopdrawing Submittal for Fourth Floor Floor phase 05 type FAJ |  |  | 6 | 2026-10-12 | 2026-10-18
MS.ES.P05.FAJ.C.4t | Column Shopdrawing Submittal for Fourth Floor Floor phase 05 type FAJ |  |  | 6 | 2026-10-19 | 2026-10-25
MS.ES.P05.FAJ.B.5t | Block Work Shopdrawing Submittal for Fifth Floor Floor phase 05 type FAJ |  |  | 6 | 2026-10-19 | 2026-10-25
MS.ES.P05.FAJ.S.4t | Slab Shopdrawing Submittal for Fourth Floor Floor phase 05 type FAJ |  |  | 8 | 2026-10-26 | 2026-11-03
MS.ES.P05.FAJ.B.6t | Block Work Shopdrawing Submittal for Sixth Floor Floor phase 05 type FAJ |  |  | 6 | 2026-10-26 | 2026-11-01
MS.ES.P05.FAJ.B.7t | Block Work Shopdrawing Submittal for Seventh Floor Floor phase 05 type FAJ |  |  | 6 | 2026-11-02 | 2026-11-08
MS.ES.P05.FAJ.C.5t | Column Shopdrawing Submittal for Fifth Floor Floor phase 05 type FAJ |  |  | 6 | 2026-11-04 | 2026-11-10
MS.ES.P05.FAJ.B.8t | Block Work Shopdrawing Submittal for Eight Floor Floor phase 05 type FAJ |  |  | 6 | 2026-11-09 | 2026-11-15
MS.ES.P05.FAJ.S.5t | Slab Shopdrawing Submittal for Fifth Floor Floor phase 05 type FAJ |  |  | 8 | 2026-11-11 | 2026-11-19
MS.ES.P05.FAJ.B.9t | Block Work Shopdrawing Submittal for Nine Floor Floor phase 05 type FAJ |  |  | 6 | 2026-11-16 | 2026-11-22
MS.ES.P05.FAJ.C.6t | Column Shopdrawing Submittal for Sixth Floor Floor phase 05 type FAJ |  |  | 6 | 2026-11-21 | 2026-11-26
MS.ES.P05.FAJ.B.Pn | Block Work Shopdrawing Submittal for Penthouse Floor Floor phase 05 type FAJ |  |  | 6 | 2026-11-23 | 2026-11-29
MS.ES.P05.FAJ.S.6t | Slab Shopdrawing Submittal for Sixth Floor Floor phase 05 type FAJ |  |  | 6 | 2026-11-28 | 2026-12-03
MS.ES.P05.FAJ.C.7t | Column Shopdrawing Submittal for Seventh Floor Floor phase 05 type FAJ |  |  | 4 | 2026-12-05 | 2026-12-08
MS.ES.P05.FAJ.S.7t | Slab Shopdrawing Submittal for Seventh Floor Floor phase 05 type FAJ |  |  | 4 | 2026-12-09 | 2026-12-13
MS.ES.P05.FAJ.C.8t | Column Shopdrawing Submittal for Eight Floor Floor phase 05 type FAJ |  |  | 4 | 2026-12-14 | 2026-12-17
MS.ES.P05.FAJ.S.8t | Slab Shopdrawing Submittal for Eight Floor Floor phase 05 type FAJ |  |  | 4 | 2026-12-19 | 2026-12-22
MS.ES.P05.FAJ.C.9t | Column Shopdrawing Submittal for Nine Floor Floor phase 05 type FAJ |  |  | 4 | 2026-12-23 | 2026-12-27
MS.ES.P05.FAJ.S.9t | Slab Shopdrawing Submittal for Nine Floor Floor phase 05 type FAJ |  |  | 4 | 2026-12-28 | 2026-12-31
MS.ES.P05.FAJ.C.Pn | Column Shopdrawing Submittal for Penthouse Floor Floor phase 05 type FAJ |  |  | 4 | 2027-01-02 | 2027-01-05
MS.ES.P05.FAJ.S.Pn | Slab Shopdrawing Submittal for Penthouse Floor Floor phase 05 type FAJ |  |  | 4 | 2027-01-06 | 2027-01-10
Approval |  |  |  | 217 | 10-Mar-26 A | 2027-01-19
Sub-structure Drawings |  |  |  | 73 | 10-Mar-26 A | 2026-08-03
MS.EN.P5.ALL.111 | Approval Structure shop drawings ( Foundation ) |  |  | 14 | 10-Mar-26 A | 2026-06-27
MS.EN.P5.ALL.113 | Approval Structure shop drawings ( Vertical Elements - Walls & Columns) |  |  | 20 | 2026-06-22 | 2026-07-14
MS.EN.P5.ALL.115 | Approval Structure shop drawings ( Slabs ) |  |  | 20 | 2026-07-12 | 2026-08-03
Super structure Drawings |  |  |  | 144 | 2026-08-04 | 2027-01-19
FA-J |  |  |  | 144 | 2026-08-04 | 2027-01-19
MS.EA.P05.FAJ.C.LG | Column Shopdrawing Approval for Lower Ground Floor Floor phase 05 type FAJ |  |  | 12 | 2026-08-04 | 2026-08-17
MS.EA.P05.FAJ.S.LG | Slab Shopdrawing Approval for Lower Ground Floor phase 05 type FAJ |  |  | 12 | 2026-08-11 | 2026-08-24
MS.EA.P05.FAJ.C.Gr | Column Shopdrawing Approval for Ground Floor Floor phase 05 type FAJ |  |  | 12 | 2026-08-20 | 2026-09-02
MS.EA.P05.FAJ.S.Gr | Slab Shopdrawing Approval for Ground Floor Floor phase 05 type FAJ |  |  | 12 | 2026-08-27 | 2026-09-09
MS.EA.P05.FAJ.C.1s | Column Shopdrawing Approval for First Floor Floor phase 05 type FAJ |  |  | 12 | 2026-09-06 | 2026-09-19
MS.EA.P05.FAJ.S.1s | Slab Shopdrawing Approval for First Floor Floor phase 05 type FAJ |  |  | 12 | 2026-09-13 | 2026-09-27
MS.EA.P05.FAJ.B.LG | Block Work Shopdrawing Approval for Lower Ground Floor Floor phase 05 type FAJ |  |  | 12 | 2026-09-13 | 2026-09-27
MS.EA.P05.FAJ.B.Gr | Block Work Shopdrawing Approval for Ground Floor Floor phase 05 type FAJ |  |  | 12 | 2026-09-20 | 2026-10-04
MS.EA.P05.FAJ.C.2n | Column Shopdrawing Approval for Second Floor Floor phase 05 type FAJ |  |  | 12 | 2026-09-22 | 2026-10-06
MS.EA.P05.FAJ.B.1s | Block Work Shopdrawing Approval for First Floor Floor phase 05 type FAJ |  |  | 12 | 2026-09-28 | 2026-10-11
MS.EA.P05.FAJ.S.2n | Slab Shopdrawing Approval for Second Floor Floor phase 05 type FAJ |  |  | 12 | 2026-09-30 | 2026-10-13
MS.EA.P05.FAJ.B.2n | Block Work Shopdrawing Approval for Second Floor Floor phase 05 type FAJ |  |  | 12 | 2026-10-05 | 2026-10-18
MS.EA.P05.FAJ.C.3d | Column Shopdrawing Approval for Third Floor Floor phase 05 type FAJ |  |  | 12 | 2026-10-10 | 2026-10-22
MS.EA.P05.FAJ.B.3d | Block Work Shopdrawing Approval for Third Floor Floor phase 05 type FAJ |  |  | 12 | 2026-10-12 | 2026-10-25
MS.EA.P05.FAJ.S.3d | Slab Shopdrawing Approval for Third Floor Floor phase 05 type FAJ |  |  | 12 | 2026-10-17 | 2026-10-29
MS.EA.P05.FAJ.B.4t | Block Work Shopdrawing Approval for Fourth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-10-19 | 2026-11-01
MS.EA.P05.FAJ.C.4t | Column Shopdrawing Approval for Fourth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-10-26 | 2026-11-08
MS.EA.P05.FAJ.B.5t | Block Work Shopdrawing Approval for Fifth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-10-26 | 2026-11-08
MS.EA.P05.FAJ.S.4t | Slab Shopdrawing Approval for Fourth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-02 | 2026-11-15
MS.EA.P05.FAJ.B.6t | Block Work Shopdrawing Approval for Sixth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-02 | 2026-11-15
MS.EA.P05.FAJ.B.7t | Block Work Shopdrawing Approval for Seventh Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-09 | 2026-11-22
MS.EA.P05.FAJ.C.5t | Column Shopdrawing Approval for Fifth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-11 | 2026-11-24
MS.EA.P05.FAJ.B.8t | Block Work Shopdrawing Approval for Eight Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-16 | 2026-11-29
MS.EA.P05.FAJ.S.5t | Slab Shopdrawing Approval for Fifth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-18 | 2026-12-01
MS.EA.P05.FAJ.B.9t | Block Work Shopdrawing Approval for Nine Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-23 | 2026-12-06
MS.EA.P05.FAJ.C.6t | Column Shopdrawing Approval for Sixth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-28 | 2026-12-10
MS.EA.P05.FAJ.B.Pn | Block Work Shopdrawing Approval for Penthouse Floor Floor phase 05 type FAJ |  |  | 12 | 2026-11-30 | 2026-12-13
MS.EA.P05.FAJ.S.6t | Slab Shopdrawing Approval for Sixth Floor Floor phase 05 type FAJ |  |  | 12 | 2026-12-05 | 2026-12-17
MS.EA.P05.FAJ.C.7t | Column Shopdrawing Approval for Seventh Floor Floor phase 05 type FAJ |  |  | 12 | 2026-12-12 | 2026-12-24
MS.EA.P05.FAJ.S.7t | Slab Shopdrawing Approval for Seventh Floor Floor phase 05 type FAJ |  |  | 12 | 2026-12-16 | 2026-12-29
MS.EA.P05.FAJ.C.8t | Column Shopdrawing Approval for Eight Floor Floor phase 05 type FAJ |  |  | 6 | 2026-12-21 | 2026-12-27
MS.EA.P05.FAJ.S.8t | Slab Shopdrawing Approval for Eight Floor Floor phase 05 type FAJ |  |  | 6 | 2026-12-26 | 2026-12-31
MS.EA.P05.FAJ.C.9t | Column Shopdrawing Approval for Nine Floor Floor phase 05 type FAJ |  |  | 6 | 2026-12-30 | 2027-01-05
MS.EA.P05.FAJ.S.9t | Slab Shopdrawing Approval for Nine Floor Floor phase 05 type FAJ |  |  | 6 | 2027-01-04 | 2027-01-10
MS.EA.P05.FAJ.C.Pn | Column Shopdrawing Approval for Penthouse Floor Floor phase 05 type FAJ |  |  | 6 | 2027-01-09 | 2027-01-14
MS.EA.P05.FAJ.S.Pn | Slab Shopdrawing Approval for Penthouse Floor Floor phase 05 type FAJ |  |  | 6 | 2027-01-13 | 2027-01-19
Procurement |  |  |  | 300 | 21-Jan-26 A | 2027-01-25
Pre-Qualifications |  |  |  | 9 | 2026-06-11 | 2026-06-21
Submittals |  |  |  | 3 | 2026-06-11 | 2026-06-14
A1520 | Pre-Qualifications Submittal – Post-Tensioning System |  |  | 3 | 2026-06-11 | 2026-06-14
Approvals |  |  |  | 6 | 2026-06-15 | 2026-06-21
A1530 | Pre-Qualifications Approval – Post-Tensioning System |  |  | 6 | 2026-06-15 | 2026-06-21
Material Submittal |  |  |  | 9 | 2026-06-15 | 2026-06-24
Submittals |  |  |  | 3 | 2026-06-15 | 2026-06-17
A1540 | Material Submittal – Post-Tensioning System |  |  | 3 | 2026-06-15 | 2026-06-17
Approvals |  |  |  | 6 | 2026-06-18 | 2026-06-24
A1550 | Material Approval – Post-Tensioning System |  |  | 6 | 2026-06-18 | 2026-06-24
Purchase Order |  |  |  | 5 | 2026-06-22 | 2026-06-27
Issue PO |  |  |  | 5 | 2026-06-22 | 2026-06-27
A1300 | Purchase Order – Post-Tensioning System |  |  | 5 | 2026-06-22 | 2026-06-27
Material Delivery |  |  |  | 300 | 21-Jan-26 A | 2027-01-25
Delivery |  |  |  | 300 | 21-Jan-26 A | 2027-01-25
A1320 | Delivery – Reinforcement Steel |  |  | 300 | 21-Jan-26 A | 2027-01-25
A1350 | Delivery – CMU Blocks |  |  | 180 | 2026-06-11 | 2027-01-07
A1560 | Delivery – Post-Tensioning System |  |  | 5 | 2026-06-28 | 2026-07-02
Construction Stage |  |  |  | 315 | 21-Dec-25 A | 2027-03-31
Con.Phase (1) |  |  |  | 298 | 05-Apr-26 A | 2027-03-31
Sub-structure Works |  |  |  | 209 | 05-Apr-26 A | 2026-12-08
Foundation |  |  |  | 75 | 05-Apr-26 A | 2026-07-04
Part 1 |  |  |  | 3 | 12-May-26 A | 2026-06-14
Raft Foundation Works |  | 3749 | M2 | 3 | 12-May-26 A | 2026-06-14
MS.CO.P1.FO.110 | Foundations Concrete Pouring | 3749 | M2 | 3 | 12-May-26 A | 2026-06-14
Part 3 |  |  |  | 28 | 25-Apr-26 A | 2026-06-20
Raft Foundation Works |  | 3528 | M2 | 28 | 25-Apr-26 A | 2026-06-20
MS.CO.P1.FO.118 | Formwork for Foundations | 3528 | M2 | 8 | 25-Apr-26 A | 2026-06-20
MS.CO.P1.FO.120 | Foundations Concrete Pouring | 3528 | M2 | 3 | 14-May-26 A | 2026-06-14
Part 4 |  |  |  | 3 | 24-May-26 A | 2026-06-14
Raft Foundation Works |  | 2632 | M2 | 3 | 24-May-26 A | 2026-06-14
MS.CO.P1.FO.125 | Foundations Concrete Pouring | 2632 | M2 | 3 | 24-May-26 A | 2026-06-14
Part 5 |  |  |  | 75 | 05-Apr-26 A | 2026-07-04
Excavation, Blinding & Waterproofing Works |  | 2126 | M2 | 9 | 05-Apr-26 A | 2026-06-14
MS.CO.P1.FO.200 | Blinding concrete for Upper Part | 2126 | M2 | 2 | 05-Apr-26 A | 2026-06-11
MS.CO.P1.FO.210 | Surface preparation and Angle filet at RW Edge | 2126 | M2 | 1 | 09-Apr-26 A | 2026-06-11
MS.CO.P1.FO.220 | Water Proofing Membrane under Raft Foundation | 2126 | M2 | 4 | 11-Apr-26 A | 2026-06-14
Raft Foundation Works |  | 3148 | M2 | 20 | 2026-06-11 | 2026-07-04
MS.CO.P1.FO.126 | Rebars for 1st layer for Foundation | 3148 | M2 | 8 | 2026-06-11 | 2026-06-20
MS.CO.P1.FO.127 | Installation for Mechanical and Electrical Embeds | 3148 | M2 | 4 | 2026-06-23 | 2026-06-27
MS.CO.P1.FO.128 | Formwork for Foundations | 3148 | M2 | 5 | 2026-06-27 | 2026-07-01
MS.CO.P1.FO.129 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 3148 | M2 | 5 | 2026-06-27 | 2026-07-01
MS.CO.P1.FO.130 | Foundations Concrete Pouring | 3148 | M2 | 2 | 2026-07-02 | 2026-07-04
Basement 2 |  |  |  | 116 | 01-Jun-26 A | 2026-10-20
Skeleton Works |  |  |  | 74 | 01-Jun-26 A | 2026-08-31
Vertical Element |  |  |  | 37 | 01-Jun-26 A | 2026-07-19
Part 1 |  |  |  | 26 | 01-Jun-26 A | 2026-07-06
MS.CO.P1.B2.100 | B2 - Columns Steel Fix | 58 | PCS | 12 | 01-Jun-26 A | 2026-06-17
MS.CO.P1.B2.101 | B2 - Columns Formwork | 58 | PCS | 12 | 2026-06-11 | 2026-06-24
MS.CO.P1.B2.145 | B2 - Walls Steel Fix | 605 | m2 | 12 | 2026-06-15 | 2026-06-28
MS.CO.P1.B2.155 | B2 - Walls Formwork | 605 | m2 | 12 | 2026-06-20 | 2026-07-02
MS.CO.P1.B2.102 | B2 - Columns Concreting work | 58 | PCS | 1 | 2026-06-25 | 2026-06-25
MS.CO.P1.B2.165 | B2 - Walls Concreting work | 605 | m2 | 3 | 2026-07-04 | 2026-07-06
Part 2 |  |  |  | 19 | 2026-06-11 | 2026-07-02
MS.CO.P1.B2.103 | B2 - Columns Steel Fix | 60 | PCS | 12 | 2026-06-11 | 2026-06-24
MS.CO.P1.B2.175 | B2 - Walls Steel Fix | 605 | m2 | 12 | 2026-06-11 | 2026-06-24
MS.CO.P1.B2.104 | B2 - Columns Formwork | 60 | PCS | 12 | 2026-06-15 | 2026-06-28
MS.CO.P1.B2.185 | B2 - Walls Formwork | 605 | m2 | 12 | 2026-06-16 | 2026-06-29
MS.CO.P1.B2.105 | B2 - Columns Concreting work | 60 | PCS | 1 | 2026-06-29 | 2026-06-29
MS.CO.P1.B2.195 | B2 - Walls Concreting work | 605 | m2 | 3 | 2026-06-30 | 2026-07-02
Part 3 |  |  |  | 19 | 2026-06-15 | 2026-07-06
MS.CO.P1.B2.106 | B2 - Columns Steel Fix | 53 | PCS | 12 | 2026-06-15 | 2026-06-28
MS.CO.P1.B2.205 | B2 - Walls Steel Fix | 605 | m2 | 12 | 2026-06-15 | 2026-06-28
MS.CO.P1.B2.107 | B2 - Columns Formwork |  |  | 12 | 2026-06-18 | 2026-07-01
MS.CO.P1.B2.215 | B2 - Walls Formwork |  |  | 12 | 2026-06-20 | 2026-07-02
MS.CO.P1.B2.109 | B2 - Columns Concreting work |  |  | 1 | 2026-07-02 | 2026-07-02
MS.CO.P1.B2.225 | B2 - Walls Concreting work |  |  | 3 | 2026-07-04 | 2026-07-06
Part 4 |  |  |  | 19 | 2026-06-18 | 2026-07-09
MS.CO.P1.B2.113 | B2 - Columns Steel Fix | 34 | PCS | 12 | 2026-06-18 | 2026-07-01
MS.CO.P1.B2.235 | B2 - Walls Steel Fix | 605 | m2 | 12 | 2026-06-18 | 2026-07-01
MS.CO.P1.B2.116 | B2 - Columns Formwork | 34 | PCS | 12 | 2026-06-21 | 2026-07-04
MS.CO.P1.B2.245 | B2 - Walls Formwork | 605 | m2 | 12 | 2026-06-23 | 2026-07-06
MS.CO.P1.B2.118 | B2 - Columns Concreting work | 34 | PCS | 1 | 2026-07-05 | 2026-07-05
MS.CO.P1.B2.255 | B2 - Walls Concreting work | 605 | m2 | 3 | 2026-07-07 | 2026-07-09
Part 5 |  |  |  | 13 | 2026-07-05 | 2026-07-19
MS.CO.P1.B2.119 | B2 - Columns Steel Fix | 34 | PCS | 6 | 2026-07-05 | 2026-07-11
MS.CO.P1.B2.265 | B2 - Walls Steel Fix | 605 | m2 | 6 | 2026-07-05 | 2026-07-11
MS.CO.P1.B2.122 | B2 - Columns Formwork | 34 | PCS | 6 | 2026-07-08 | 2026-07-14
MS.CO.P1.B2.275 | B2 - Walls Formwork | 605 | m2 | 6 | 2026-07-09 | 2026-07-15
MS.CO.P1.B2.123 | B2 - Columns Concreting work | 34 | PCS | 1 | 2026-07-15 | 2026-07-15
MS.CO.P1.B2.285 | B2 - Walls Concreting work | 605 | m2 | 3 | 2026-07-16 | 2026-07-19
Slab |  |  |  | 50 | 2026-07-05 | 2026-08-31
Part 1 |  |  |  | 42 | 2026-07-05 | 2026-08-22
MS.CO.P1.B2.108 | B2 - Beams and Slab Formwork | 4716 | m2 | 12 | 2026-07-05 | 2026-07-18
MS.CO.P1.B2.110 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 10 | 2026-07-16 | 2026-07-27
MS.CO.P1.B2.111 | B2 - Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-07-28 | 2026-07-28
MS.CO.P1.B2.124 | B2 - DE shuttering for Slab | 4716 | m2 | 2 | 2026-08-20 | 2026-08-22
Part 2 |  |  |  | 39 | 2026-07-06 | 2026-08-19
MS.CO.P1.B2.112 | B2 - Beams and Slab Formwork | 4716 | m2 | 12 | 2026-07-06 | 2026-07-19
MS.CO.P1.B2.114 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 10 | 2026-07-15 | 2026-07-26
MS.CO.P1.B2.115 | B2 - Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-07-27 | 2026-07-27
MS.CO.P1.B2.126 | B2 - DE shuttering for Slab | 4716 | m2 | 1 | 2026-08-19 | 2026-08-19
Part 3 |  |  |  | 43 | 2026-07-09 | 2026-08-27
MS.CO.P1.B2.117 | B2 - Beams and Slab Formwork | 4716 | m2 | 12 | 2026-07-09 | 2026-07-22
MS.CO.P1.B2.120 | B2 - Beams and Slab Steel Fix | 4716 | m2 |  | 2026-07-23 | 2026-08-03
MS.CO.P1.B2.121 | B2 - Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-08-04 | 2026-08-04
MS.CO.P1.B2.130 | B2 - DE shuttering for Slab | 4716 | m2 | 1 | 2026-08-27 | 2026-08-27
Part 4 |  |  |  | 43 | 2026-07-13 | 2026-08-31
MS.CO.P1.B2.125 | B2 - Beams and Slab Formwork | 4716 | m2 | 12 | 2026-07-13 | 2026-07-26
MS.CO.P1.B2.127 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 10 | 2026-07-27 | 2026-08-06
MS.CO.P1.B2.128 | B2 - Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-08-08 | 2026-08-08
MS.CO.P1.B2.133 | B2 - DE shuttering for Slab | 4716 | m2 | 1 | 2026-08-31 | 2026-08-31
Part 5 |  |  |  | 38 | 2026-07-16 | 2026-08-29
MS.CO.P1.B2.129 | B2 - Beams and Slab Formwork | 4716 | m2 | 8 | 2026-07-16 | 2026-07-25
MS.CO.P1.B2.131 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 8 | 2026-07-26 | 2026-08-03
MS.CO.P1.B2.132 | B2 - Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-08-04 | 2026-08-04
MS.CO.P1.B2.134 | B2 - DE shuttering for Slab | 4716 | m2 | 2 | 2026-08-27 | 2026-08-29
Masonry Works |  |  |  | 42 | 2026-09-01 | 2026-10-20
MS.CO.P1.B2.135 | B2 - Block Works |  |  | 42 | 2026-09-01 | 2026-10-20
Basement 1 |  |  |  | 114 | 2026-07-28 | 2026-12-08
Skeleton Works |  |  |  | 68 | 2026-07-28 | 2026-10-15
Vertical Element |  |  |  | 25 | 2026-07-28 | 2026-08-25
Part 1 |  |  |  | 15 | 2026-07-29 | 2026-08-15
MS.CO.P1.B1.100 | B1 - Columns Steel Fix | 58 | PCS | 7 | 2026-07-29 | 2026-08-05
MS.CO.P1.B1.200 | B1 - Walls Steel Fix | 605 | m2 | 7 | 2026-07-29 | 2026-08-05
MS.CO.P1.B1.101 | B1 - Columns Formwork | 58 | PCS | 7 | 2026-08-03 | 2026-08-10
MS.CO.P1.B1.201 | B1 - Walls Formwork | 605 | m2 | 7 | 2026-08-03 | 2026-08-10
MS.CO.P1.B1.103 | B1 - Columns Concreting work | 58 | PCS | 7 | 2026-08-08 | 2026-08-15
MS.CO.P1.B1.203 | B1 - Walls Concreting work | 605 | m2 | 7 | 2026-08-08 | 2026-08-15
Part 2 |  |  |  | 15 | 2026-07-28 | 2026-08-13
MS.CO.P1.B1.102 | B1 - Columns Steel Fix | 60 | PCS | 7 | 2026-07-28 | 2026-08-04
MS.CO.P1.B1.202 | B1 - Walls Steel Fix | 605 | m2 | 7 | 2026-07-28 | 2026-08-04
MS.CO.P1.B1.104 | B1 - Columns Formwork | 60 | PCS | 7 | 2026-08-02 | 2026-08-09
MS.CO.P1.B1.204 | B1 - Walls Formwork | 605 | m2 | 7 | 2026-08-02 | 2026-08-09
MS.CO.P1.B1.105 | B1 - Columns Concreting work | 60 | PCS | 7 | 2026-08-06 | 2026-08-13
MS.CO.P1.B1.205 | B1 - Walls Concreting work | 605 | m2 | 7 | 2026-08-06 | 2026-08-13
Part 3 |  |  |  | 15 | 2026-08-05 | 2026-08-22
MS.CO.P1.B1.106 | B1 - Columns Steel Fix | 53 | PCS | 7 | 2026-08-05 | 2026-08-12
MS.CO.P1.B1.206 | B1 - Walls Steel Fix | 605 | m2 | 7 | 2026-08-05 | 2026-08-12
MS.CO.P1.B1.107 | B1 - Columns Formwork | 53 | PCS | 7 | 2026-08-10 | 2026-08-17
MS.CO.P1.B1.207 | B1 - Walls Formwork | 605 | m2 | 7 | 2026-08-10 | 2026-08-17
MS.CO.P1.B1.109 | B1 - Columns Concreting work | 53 | PCS | 7 | 2026-08-15 | 2026-08-22
MS.CO.P1.B1.209 | B1 - Walls Concreting work | 605 | m2 | 7 | 2026-08-15 | 2026-08-22
Part 4 |  |  |  | 15 | 2026-08-09 | 2026-08-25
MS.CO.P1.B1.113 | B1 - Columns Steel Fix | 34 | PCS | 7 | 2026-08-09 | 2026-08-16
MS.CO.P1.B1.213 | B1 - Walls Steel Fix | 605 | m2 | 7 | 2026-08-09 | 2026-08-16
MS.CO.P1.B1.116 | B1 - Columns Formwork | 34 | PCS | 7 | 2026-08-13 | 2026-08-20
MS.CO.P1.B1.216 | B1 - Walls Formwork | 605 | m2 | 7 | 2026-08-13 | 2026-08-20
MS.CO.P1.B1.118 | B2 - Columns Concreting work | 34 | PCS | 7 | 2026-08-18 | 2026-08-25
MS.CO.P1.B1.218 | B2 - Walls Concreting work | 605 | m2 | 7 | 2026-08-18 | 2026-08-25
Part 5 |  |  |  | 14 | 2026-08-05 | 2026-08-20
MS.CO.P1.B1.119 | B1 - Columns Steel Fix | 34 | PCS | 6 | 2026-08-05 | 2026-08-11
MS.CO.P1.B1.219 | B1 - Walls Steel Fix | 605 | m2 | 6 | 2026-08-05 | 2026-08-11
MS.CO.P1.B1.122 | B1 - Columns Formwork | 34 | PCS | 6 | 2026-08-10 | 2026-08-16
MS.CO.P1.B1.222 | B1 - Walls Formwork | 605 | m2 | 6 | 2026-08-10 | 2026-08-16
MS.CO.P1.B1.123 | B1 - Columns Concreting work | 34 | PCS | 6 | 2026-08-15 | 2026-08-20
MS.CO.P1.B1.223 | B1 - Walls Concreting work | 605 | m2 | 6 | 2026-08-15 | 2026-08-20
Slab |  |  |  | 48 | 2026-08-20 | 2026-10-15
Part 1 |  |  |  | 37 | 2026-08-23 | 2026-10-05
MS.CO.P1.B1.108 | B2 - Beams and Slab Formwork | 4716 | m2 | 10 | 2026-08-23 | 2026-09-02
MS.CO.P1.B1.110 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 6 | 2026-09-03 | 2026-09-09
MS.CO.P1.B1.111 | Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-09-10 | 2026-09-10
MS.CO.P1.B1.124 | B2 - DE shuttering for Slab | 4716 | m2 | 1 | 2026-10-05 | 2026-10-05
Part 2 |  |  |  | 38 | 2026-08-20 | 2026-10-04
MS.CO.P1.B1.112 | B2 - Beams and Slab Formwork | 4716 | m2 | 10 | 2026-08-20 | 2026-08-31
MS.CO.P1.B1.114 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 7 | 2026-09-01 | 2026-09-08
MS.CO.P1.B1.115 | Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-09-09 | 2026-09-09
MS.CO.P1.B1.126 | B2 - DE shuttering for Slab | 4716 | m2 | 1 | 2026-10-04 | 2026-10-04
Part 3 |  |  |  | 37 | 2026-08-29 | 2026-10-11
MS.CO.P1.B1.117 | B2 - Beams and Slab Formwork | 4716 | m2 | 9 | 2026-08-29 | 2026-09-07
MS.CO.P1.B1.120 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 7 | 2026-09-08 | 2026-09-15
MS.CO.P1.B1.121 | Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-09-16 | 2026-09-16
MS.CO.P1.B1.130 | B2 - DE shuttering for Slab | 4716 | m2 | 1 | 2026-10-11 | 2026-10-11
Part 4 |  |  |  | 38 | 2026-09-01 | 2026-10-15
MS.CO.P1.B1.125 | B2 - Beams and Slab Formwork | 4716 | m2 | 9 | 2026-09-01 | 2026-09-10
MS.CO.P1.B1.127 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 7 | 2026-09-12 | 2026-09-19
MS.CO.P1.B1.128 | Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-09-20 | 2026-09-20
MS.CO.P1.B1.133 | B2 - DE shuttering for Slab | 4716 | m2 | 2 | 2026-10-14 | 2026-10-15
Part 5 |  |  |  | 36 | 2026-08-30 | 2026-10-11
MS.CO.P1.B1.129 | B2 - Beams and Slab Formwork | 4716 | m2 | 8 | 2026-08-30 | 2026-09-07
MS.CO.P1.B1.131 | B2 - Beams and Slab Steel Fix | 4716 | m2 | 6 | 2026-09-08 | 2026-09-14
MS.CO.P1.B1.132 | Beams and Slab Concreting work | 4716 | m2 | 1 | 2026-09-15 | 2026-09-15
MS.CO.P1.B1.134 | B2 - DE shuttering for Slab | 4716 | m2 | 2 | 2026-10-10 | 2026-10-11
Masonry Works |  |  |  | 42 | 2026-10-21 | 2026-12-08
MS.CO.P1.B1.135 | B2 - Block Works |  |  | 42 | 2026-10-21 | 2026-12-08
Super Structure Works |  |  |  | 165 | 2026-09-10 | 2027-03-31
6FA-I |  |  |  | 164 | 2026-09-12 | 2027-03-31
Lower Ground Floor |  |  |  | 98 | 2026-09-12 | 2027-01-04
Vertical Element |  | 57 | PCS | 14 | 2026-09-12 | 2026-09-28
MS.CO.P1.FAI.100 | Columns & Walls Steel Fix | 57 | PCS | 6 | 2026-09-12 | 2026-09-17
MS.CO.P1.FAI.101 | Columns & Walls Formwork | 57 | PCS | 6 | 2026-09-16 | 2026-09-22
MS.CO.P1.FAI.102 | Columns & Walls Concreting work | 57 | PCS | 6 | 2026-09-21 | 2026-09-28
Slab |  | 2705.93 | M2 | 33 | 2026-10-06 | 2026-11-12
MS.CO.P1.FAI.103 | Beams and Slab Formwork | 2705.93 | M2 | 6 | 2026-10-06 | 2026-10-12
MS.CO.P1.FAI.104 | Beams and Slab Steel Fix | 2705.93 | M2 | 5 | 2026-10-13 | 2026-10-18
MS.CO.P1.FAI.105 | Beams and Slab Concreting work | 2705.93 | M2 | 1 | 2026-10-19 | 2026-10-19
MS.CO.P1.FAI.109 | DE shuttering for Slab | 2705.93 | M2 | 2 | 2026-11-11 | 2026-11-12
Masonry Works |  |  |  | 23 | 2026-12-09 | 2027-01-04
MS.CO.P1.FAI.113 | External Block Work |  |  | 14 | 2026-12-09 | 2026-12-24
MS.CO.P1.FAI.116 | Internal Block Work |  |  | 14 | 2026-12-20 | 2027-01-04
Ground Floor |  |  |  | 80 | 2026-10-20 | 2027-01-20
Vertical Element |  | 57 | PCS | 10 | 2026-10-20 | 2026-10-31
MS.CO.P1.FAI.106 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-10-20 | 2026-10-24
MS.CO.P1.FAI.107 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-10-24 | 2026-10-27
MS.CO.P1.FAI.108 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-10-27 | 2026-10-31
Slab |  | 2330.55 | M2 | 31 | 2026-10-28 | 2026-12-02
MS.CO.P1.FAI.110 | Beams and Slab Formwork | 2330.55 | M2 | 5 | 2026-10-28 | 2026-11-02
MS.CO.P1.FAI.111 | Beams and Slab Steel Fix | 2330.55 | M2 | 4 | 2026-11-03 | 2026-11-07
MS.CO.P1.FAI.112 | Beams and Slab Concreting work | 2330.55 | M2 | 1 | 2026-11-08 | 2026-11-08
MS.CO.P1.FAI.118 | DE shuttering for Slab | 2330.55 | M2 | 2 | 2026-12-01 | 2026-12-02
Masonry Works |  |  |  | 23 | 2026-12-26 | 2027-01-20
MS.CO.P1.FAI.122 | External Block Work |  |  | 14 | 2026-12-26 | 2027-01-10
MS.CO.P1.FAI.125 | Internal Block Work |  |  | 14 | 2027-01-05 | 2027-01-20
First Floor |  |  |  | 77 | 2026-11-09 | 2027-02-06
Vertical Element |  | 57 | PCS | 8 | 2026-11-09 | 2026-11-17
MS.CO.P1.FAI.114 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-11-09 | 2026-11-12
MS.CO.P1.FAI.115 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-11-11 | 2026-11-15
MS.CO.P1.FAI.117 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-11-14 | 2026-11-17
Slab |  | 2297.15 | M2 | 31 | 2026-11-15 | 2026-12-20
MS.CO.P1.FAI.119 | Beams and Slab Formwork | 2297.15 | M2 | 5 | 2026-11-15 | 2026-11-19
MS.CO.P1.FAI.120 | Beams and Slab Steel Fix | 2297.15 | M2 | 4 | 2026-11-21 | 2026-11-24
MS.CO.P1.FAI.121 | Beams and Slab Concreting work | 2297.15 | M2 | 1 | 2026-11-25 | 2026-11-25
MS.CO.P1.FAI.127 | DE shuttering for Slab | 2297.15 | M2 | 2 | 2026-12-19 | 2026-12-20
Masonry Works |  |  |  | 23 | 2027-01-11 | 2027-02-06
MS.CO.P1.FAI.131 | External Block Work |  |  | 14 | 2027-01-11 | 2027-01-26
MS.CO.P1.FAI.134 | Internal Block Work |  |  | 14 | 2027-01-21 | 2027-02-06
Second Floor |  |  |  | 76 | 2026-11-26 | 2027-02-25
Vertical Element |  | 57 | PCS | 8 | 2026-11-26 | 2026-12-05
MS.CO.P1.FAI.123 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-11-26 | 2026-11-30
MS.CO.P1.FAI.124 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-11-29 | 2026-12-02
MS.CO.P1.FAI.126 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-12-01 | 2026-12-05
Slab |  | 2295.17 | M2 | 31 | 2026-12-03 | 2027-01-07
MS.CO.P1.FAI.128 | Beams and Slab Formwork | 2295.17 | M2 | 5 | 2026-12-03 | 2026-12-08
MS.CO.P1.FAI.129 | Beams and Slab Steel Fix | 2295.17 | M2 | 4 | 2026-12-09 | 2026-12-13
MS.CO.P1.FAI.130 | Beams and Slab Concreting work | 2295.17 | M2 | 1 | 2026-12-14 | 2026-12-14
MS.CO.P1.FAI.136 | DE shuttering for Slab | 2295.17 | M2 | 2 | 2027-01-06 | 2027-01-07
Masonry Works |  |  |  | 23 | 2027-01-27 | 2027-02-25
MS.CO.P1.FAI.140 | External Block Work |  |  | 14 | 2027-01-27 | 2027-02-11
MS.CO.P1.FAI.143 | Internal Block Work |  |  | 14 | 2027-02-07 | 2027-02-25
Third Floor |  |  |  | 72 | 2026-12-15 | 2027-03-17
Vertical Element |  | 57 | PCS | 8 | 2026-12-15 | 2026-12-23
MS.CO.P1.FAI.132 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-12-15 | 2026-12-19
MS.CO.P1.FAI.133 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-12-17 | 2026-12-21
MS.CO.P1.FAI.135 | Columns & Walls Concreting work |  |  | 4 | 2026-12-20 | 2026-12-23
Slab |  | 2291.65 | M2 | 31 | 2026-12-21 | 2027-01-25
MS.CO.P1.FAI.137 | Beams and Slab Formwork | 2291.65 | M2 | 5 | 2026-12-21 | 2026-12-26
MS.CO.P1.FAI.138 | Beams and Slab Steel Fix | 2291.65 | M2 | 4 | 2026-12-27 | 2026-12-30
MS.CO.P1.FAI.139 | Beams and Slab Concreting work | 2291.65 | M2 | 1 | 2026-12-31 | 2026-12-31
MS.CO.P1.FAI.145 | DE shuttering for Slab | 2291.65 | M2 | 2 | 2027-01-24 | 2027-01-25
Masonry Works |  |  |  | 21 | 2027-02-14 | 2027-03-17
MS.CO.P1.FAI.149 | External Block Work |  |  | 12 | 2027-02-14 | 2027-03-02
MS.CO.P1.FAI.152 | Internal Block Work |  |  | 12 | 2027-02-28 | 2027-03-17
Fourth Floor |  |  |  | 69 | 2027-01-02 | 2027-03-31
Vertical Element |  | 57 | PCS | 8 | 2027-01-02 | 2027-01-10
MS.CO.P1.FAI.141 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2027-01-02 | 2027-01-05
MS.CO.P1.FAI.142 | Columns & Walls Formwork | 57 | PCS | 4 | 2027-01-04 | 2027-01-07
MS.CO.P1.FAI.144 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-01-06 | 2027-01-10
Slab |  | 2297.31 | M2 | 31 | 2027-01-07 | 2027-02-11
MS.CO.P1.FAI.146 | Beams and Slab Formwork | 2297.31 | M2 | 5 | 2027-01-07 | 2027-01-12
MS.CO.P1.FAI.147 | Beams and Slab Steel Fix | 2297.31 | M2 | 4 | 2027-01-13 | 2027-01-17
MS.CO.P1.FAI.148 | Beams and Slab Concreting work | 2297.31 | M2 | 1 | 2027-01-18 | 2027-01-18
MS.CO.P1.FAI.154 | DE shuttering for Slab | 2297.31 | M2 | 2 | 2027-02-10 | 2027-02-11
Masonry Works |  |  |  | 21 | 2027-03-03 | 2027-03-31
MS.CO.P1.FAI.158 | External Block Work |  |  | 14 | 2027-03-03 | 2027-03-23
MS.CO.P1.FAI.161 | Internal Block Work |  |  | 12 | 2027-03-18 | 2027-03-31
Fifth Floor |  |  |  | 53 | 2027-01-19 | 2027-03-30
Vertical Element |  | 57 | PCS | 8 | 2027-01-19 | 2027-01-27
MS.CO.P1.FAI.150 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2027-01-19 | 2027-01-23
MS.CO.P1.FAI.151 | Columns & Walls Formwork | 57 | PCS | 4 | 2027-01-21 | 2027-01-25
MS.CO.P1.FAI.153 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-01-24 | 2027-01-27
Slab |  | 2327.59 | M2 | 30 | 2027-01-25 | 2027-03-06
MS.CO.P1.FAI.155 | Beams and Slab Formwork | 2327.59 | M2 | 5 | 2027-01-25 | 2027-01-30
MS.CO.P1.FAI.156 | Beams and Slab Steel Fix | 2327.59 | M2 | 4 | 2027-01-31 | 2027-02-03
MS.CO.P1.FAI.157 | Beams and Slab Concreting work | 2327.59 | M2 | 1 | 2027-02-04 | 2027-02-04
MS.CO.P1.FAI.164 | DE shuttering for Slab | 2327.59 | M2 | 2 | 2027-03-04 | 2027-03-06
Masonry Works |  |  |  | 18 | 2027-03-07 | 2027-03-30
MS.CO.P1.FAI.167 | External Block Work |  |  | 12 | 2027-03-07 | 2027-03-23
MS.CO.P1.FAI.169 | Internal Block Work |  |  | 12 | 2027-03-17 | 2027-03-30
Penthouse Floor |  |  |  | 31 | 2027-02-06 | 2027-03-22
Vertical Element |  | 45 | PCS | 5 | 2027-02-06 | 2027-02-10
MS.CO.P1.FAI.159 | Columns & Walls Steel Fix | 45 | PCS | 3 | 2027-02-06 | 2027-02-08
MS.CO.P1.FAI.160 | Columns & Walls Formwork | 45 | PCS | 3 | 2027-02-07 | 2027-02-09
MS.CO.P1.FAI.162 | Columns & Walls Concreting work | 45 | PCS | 3 | 2027-02-08 | 2027-02-10
Slab |  | 563.66 | M2 | 20 | 2027-02-09 | 2027-03-11
MS.CO.P1.FAI.163 | Beams and Slab Formwork | 563.66 | M2 | 4 | 2027-02-09 | 2027-02-14
MS.CO.P1.FAI.165 | Beams and Slab Steel Fix | 563.66 | M2 | 3 | 2027-02-15 | 2027-02-17
MS.CO.P1.FAI.166 | Beams and Slab Concreting work | 563.66 | M2 | 1 | 2027-02-18 | 2027-02-18
MS.CO.P1.FAI.168 | DE shuttering for Slab | 563.66 | M2 | 2 | 2027-03-10 | 2027-03-11
Masonry Works |  |  |  | 8 | 2027-03-14 | 2027-03-22
MS.CO.P1.FAI.170 | External Block Work |  |  | 8 | 2027-03-14 | 2027-03-22
MS.CO.P1.FAI.171 | Internal Block Work |  |  | 8 | 2027-03-14 | 2027-03-22
6FA-H |  |  |  | 165 | 2026-09-10 | 2027-03-31
Lower Ground Floor |  |  |  | 71 | 2026-09-10 | 2026-12-02
Vertical Element |  | 57 | PCS | 14 | 2026-09-10 | 2026-09-27
MS.CO.P1.FAH.100 | Columns & Walls Steel Fix | 57 | PCS | 6 | 2026-09-10 | 2026-09-16
MS.CO.P1.FAH.101 | Columns & Walls Formwork | 57 | PCS | 6 | 2026-09-15 | 2026-09-21
MS.CO.P1.FAH.102 | Columns & Walls Concreting work | 57 | PCS | 6 | 2026-09-20 | 2026-09-27
Slab |  | 2705.93 | M2 | 31 | 2026-09-24 | 2026-10-29
MS.CO.P1.FAH.103 | Beams and Slab Formwork | 2705.93 | M2 | 5 | 2026-09-24 | 2026-09-29
MS.CO.P1.FAH.104 | Beams and Slab Steel Fix | 2705.93 | M2 | 4 | 2026-09-30 | 2026-10-04
MS.CO.P1.FAH.105 | Beams and Slab Concreting work | 2705.93 | M2 | 1 | 2026-10-05 | 2026-10-05
MS.CO.P1.FAH.109 | DE shuttering for Slab | 2705.93 | M2 | 2 | 2026-10-28 | 2026-10-29
Masonry Works |  |  |  | 29 | 2026-10-31 | 2026-12-02
MS.CO.P1.FAH.113 | External Block Work |  |  | 20 | 2026-10-31 | 2026-11-22
MS.CO.P1.FAH.116 | Internal Block Work |  |  | 20 | 2026-11-10 | 2026-12-02
Ground Floor |  |  |  | 70 | 2026-10-06 | 2026-12-26
Vertical Element |  | 57 | PCS | 9 | 2026-10-06 | 2026-10-15
MS.CO.P1.FAH.106 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-10-06 | 2026-10-11
MS.CO.P1.FAH.107 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-10-08 | 2026-10-13
MS.CO.P1.FAH.108 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-10-11 | 2026-10-15
Slab |  | 2330.55 | M2 | 31 | 2026-10-13 | 2026-11-17
MS.CO.P1.FAH.110 | Beams and Slab Formwork | 2330.55 | M2 | 5 | 2026-10-13 | 2026-10-18
MS.CO.P1.FAH.111 | Beams and Slab Steel Fix | 2330.55 | M2 | 4 | 2026-10-19 | 2026-10-22
MS.CO.P1.FAH.112 | Beams and Slab Concreting work | 2330.55 | M2 | 1 | 2026-10-24 | 2026-10-24
MS.CO.P1.FAH.118 | DE shuttering for Slab | 2330.55 | M2 | 2 | 2026-11-16 | 2026-11-17
Masonry Works |  |  |  | 29 | 2026-11-23 | 2026-12-26
MS.CO.P1.FAH.122 | External Block Work |  |  | 14 | 2026-11-23 | 2026-12-08
MS.CO.P1.FAH.125 | Internal Block Work |  |  | 20 | 2026-12-03 | 2026-12-26
First Floor |  |  |  | 74 | 2026-10-25 | 2027-01-18
Vertical Element |  | 57 | PCS | 8 | 2026-10-25 | 2026-11-02
MS.CO.P1.FAH.114 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-10-25 | 2026-10-29
MS.CO.P1.FAH.115 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-10-27 | 2026-11-01
MS.CO.P1.FAH.117 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-10-29 | 2026-11-02
Slab |  | 2297.15 | M2 | 31 | 2026-10-31 | 2026-12-05
MS.CO.P1.FAH.119 | Beams and Slab Formwork | 2297.15 | M2 | 5 | 2026-10-31 | 2026-11-04
MS.CO.P1.FAH.120 | Beams and Slab Steel Fix | 2297.15 | M2 | 4 | 2026-11-05 | 2026-11-09
MS.CO.P1.FAH.121 | Beams and Slab Concreting work | 2297.15 | M2 | 1 | 2026-11-10 | 2026-11-10
MS.CO.P1.FAH.127 | DE shuttering for Slab | 2297.15 | M2 | 2 | 2026-12-03 | 2026-12-05
Masonry Works |  |  |  | 35 | 2026-12-09 | 2027-01-18
MS.CO.P1.FAH.131 | External Block Work |  |  | 14 | 2026-12-09 | 2026-12-24
MS.CO.P1.FAH.134 | Internal Block Work |  |  | 20 | 2026-12-27 | 2027-01-18
Second Floor |  |  |  | 73 | 2026-11-11 | 2027-02-03
Vertical Element |  | 57 | PCS | 9 | 2026-11-11 | 2026-11-21
MS.CO.P1.FAH.123 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-11-11 | 2026-11-16
MS.CO.P1.FAH.124 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-11-14 | 2026-11-18
MS.CO.P1.FAH.126 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-11-16 | 2026-11-21
Slab |  | 2295.17 | M2 | 31 | 2026-11-18 | 2026-12-23
MS.CO.P1.FAH.128 | Beams and Slab Formwork | 2295.17 | M2 | 5 | 2026-11-18 | 2026-11-23
MS.CO.P1.FAH.129 | Beams and Slab Steel Fix | 2295.17 | M2 | 4 | 2026-11-24 | 2026-11-28
MS.CO.P1.FAH.130 | Beams and Slab Concreting work | 2295.17 | M2 | 1 | 2026-11-29 | 2026-11-29
MS.CO.P1.FAH.136 | DE shuttering for Slab | 2295.17 | M2 | 2 | 2026-12-22 | 2026-12-23
Masonry Works |  |  |  | 35 | 2026-12-26 | 2027-02-03
MS.CO.P1.FAH.140 | External Block Work |  |  | 14 | 2026-12-26 | 2027-01-10
MS.CO.P1.FAH.143 | Internal Block Work |  |  | 14 | 2027-01-19 | 2027-02-03
Third Floor |  |  |  | 71 | 2026-11-30 | 2027-02-23
Vertical Element |  | 57 | PCS | 9 | 2026-11-30 | 2026-12-09
MS.CO.P1.FAH.132 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-11-30 | 2026-12-05
MS.CO.P1.FAH.133 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-12-02 | 2026-12-07
MS.CO.P1.FAH.135 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-12-05 | 2026-12-09
Slab |  | 2291.65 | M2 | 31 | 2026-12-07 | 2027-01-11
MS.CO.P1.FAH.137 | Beams and Slab Formwork | 2291.65 | M2 | 5 | 2026-12-07 | 2026-12-12
MS.CO.P1.FAH.138 | Beams and Slab Steel Fix | 2291.65 | M2 | 4 | 2026-12-13 | 2026-12-16
MS.CO.P1.FAH.139 | Beams and Slab Concreting work | 2291.65 | M2 | 1 | 2026-12-17 | 2026-12-17
MS.CO.P1.FAH.145 | DE shuttering for Slab | 2291.65 | M2 | 2 | 2027-01-10 | 2027-01-11
Masonry Works |  |  |  | 34 | 2027-01-12 | 2027-02-23
MS.CO.P1.FAH.149 | External Block Work |  |  | 14 | 2027-01-12 | 2027-01-27
MS.CO.P1.FAH.152 | Internal Block Work |  |  | 14 | 2027-02-04 | 2027-02-23
Fourth Floor |  |  |  | 69 | 2026-12-19 | 2027-03-17
Vertical Element |  | 57 | PCS | 9 | 2026-12-19 | 2026-12-28
MS.CO.P1.FAH.141 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-12-19 | 2026-12-23
MS.CO.P1.FAH.142 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-12-21 | 2026-12-26
MS.CO.P1.FAH.144 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-12-23 | 2026-12-28
Slab |  | 2297.31 | M2 | 31 | 2026-12-26 | 2027-01-30
MS.CO.P1.FAH.146 | Beams and Slab Formwork | 2297.31 | M2 | 5 | 2026-12-26 | 2026-12-30
MS.CO.P1.FAH.147 | Beams and Slab Steel Fix | 2297.31 | M2 | 4 | 2026-12-31 | 2027-01-04
MS.CO.P1.FAH.148 | Beams and Slab Concreting work | 2297.31 | M2 | 1 | 2027-01-05 | 2027-01-05
MS.CO.P1.FAH.154 | DE shuttering for Slab | 2297.31 | M2 | 2 | 2027-01-28 | 2027-01-30
Masonry Works |  |  |  | 32 | 2027-01-31 | 2027-03-17
MS.CO.P1.FAH.158 | External Block Work |  |  | 14 | 2027-01-31 | 2027-02-16
MS.CO.P1.FAH.162 | Internal Block Work |  |  | 14 | 2027-02-24 | 2027-03-17
Fifth Floor |  |  |  | 65 | 2027-01-06 | 2027-03-31
Vertical Element |  | 57 | PCS | 9 | 2027-01-06 | 2027-01-16
MS.CO.P1.FAH.150 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2027-01-06 | 2027-01-11
MS.CO.P1.FAH.151 | Columns & Walls Formwork | 57 | PCS | 5 | 2027-01-09 | 2027-01-13
MS.CO.P1.FAH.153 | Columns & Walls Concreting work | 57 | PCS | 5 | 2027-01-11 | 2027-01-16
Slab |  | 2327.59 | M2 | 31 | 2027-01-13 | 2027-02-18
MS.CO.P1.FAH.155 | Beams and Slab Formwork | 2327.59 | M2 | 5 | 2027-01-13 | 2027-01-18
MS.CO.P1.FAH.156 | Beams and Slab Steel Fix | 2327.59 | M2 | 4 | 2027-01-19 | 2027-01-23
MS.CO.P1.FAH.157 | Beams and Slab Concreting work | 2327.59 | M2 | 1 | 2027-01-24 | 2027-01-24
MS.CO.P1.FAH.164 | DE shuttering for Slab | 2327.59 | M2 | 2 | 2027-02-17 | 2027-02-18
Masonry Works |  |  |  | 28 | 2027-02-21 | 2027-03-31
MS.CO.P1.FAH.167 | External Block Work |  |  | 19 | 2027-02-21 | 2027-03-21
MS.CO.P1.FAH.169 | Internal Block Work |  |  | 14 | 2027-03-15 | 2027-03-31
Penthouse Floor |  |  |  | 46 | 2027-01-25 | 2027-03-28
Vertical Element |  | 45 | PCS | 5 | 2027-01-25 | 2027-01-30
MS.CO.P1.FAH.159 | Columns & Walls Steel Fix | 45 | PCS | 2 | 2027-01-25 | 2027-01-26
MS.CO.P1.FAH.160 | Columns & Walls Formwork | 45 | PCS | 2 | 2027-01-27 | 2027-01-28
MS.CO.P1.FAH.161 | Columns & Walls Concreting work | 45 | PCS | 1 | 2027-01-30 | 2027-01-30
Slab |  | 563.66 | M2 | 20 | 2027-01-31 | 2027-02-27
MS.CO.P1.FAH.163 | Beams and Slab Formwork | 563.66 | M2 | 3 | 2027-01-31 | 2027-02-02
MS.CO.P1.FAH.165 | Beams and Slab Steel Fix | 563.66 | M2 | 3 | 2027-02-03 | 2027-02-06
MS.CO.P1.FAH.166 | Beams and Slab Concreting work | 563.66 | M2 | 1 | 2027-02-07 | 2027-02-07
MS.CO.P1.FAH.168 | DE shuttering for Slab | 563.66 | M2 | 2 | 2027-02-25 | 2027-02-27
Masonry Works |  |  |  | 6 | 2027-03-21 | 2027-03-28
MS.CO.P1.FAH.170 | External Block Work |  |  | 6 | 2027-03-21 | 2027-03-28
MS.CO.P1.FAH.171 | Internal Block Work |  |  | 6 | 2027-03-21 | 2027-03-28
6FA-G |  |  |  | 159 | 2026-09-17 | 2027-03-31
Lower Ground Floor |  |  |  | 80 | 2026-09-17 | 2026-12-20
Vertical Element |  | 57 | PCS | 14 | 2026-09-17 | 2026-10-04
MS.CO.P1.FAG.100 | Columns & Walls Steel Fix | 57 | PCS | 6 | 2026-09-17 | 2026-09-24
MS.CO.P1.FAG.101 | Columns & Walls Formwork | 57 | PCS | 6 | 2026-09-22 | 2026-09-29
MS.CO.P1.FAG.102 | Columns & Walls Concreting work | 57 | PCS | 6 | 2026-09-28 | 2026-10-04
Slab |  | 2705.93 | M2 | 31 | 2026-10-12 | 2026-11-16
MS.CO.P1.FAG.103 | Beams and Slab Formwork | 2705.93 | M2 | 5 | 2026-10-12 | 2026-10-17
MS.CO.P1.FAG.104 | Beams and Slab Steel Fix | 2705.93 | M2 | 4 | 2026-10-18 | 2026-10-21
MS.CO.P1.FAG.105 | Beams and Slab Concreting work | 2705.93 | M2 | 1 | 2026-10-22 | 2026-10-22
MS.CO.P1.FAG.109 | DE shuttering for Slab | 2705.93 | M2 | 2 | 2026-11-15 | 2026-11-16
Masonry Works |  |  |  | 29 | 2026-11-17 | 2026-12-20
MS.CO.P1.FAG.113 | External Block Work |  |  | 20 | 2026-11-17 | 2026-12-09
MS.CO.P1.FAG.116 | Internal Block Work |  |  | 20 | 2026-11-28 | 2026-12-20
Ground Floor |  |  |  | 64 | 2026-10-24 | 2027-01-05
Vertical Element |  | 57 | PCS | 9 | 2026-10-24 | 2026-11-02
MS.CO.P1.FAG.106 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-10-24 | 2026-10-28
MS.CO.P1.FAG.107 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-10-26 | 2026-10-31
MS.CO.P1.FAG.108 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-10-28 | 2026-11-02
Slab |  | 2330.55 | M2 | 31 | 2026-10-31 | 2026-12-05
MS.CO.P1.FAG.110 | Beams and Slab Formwork | 2330.55 | M2 | 5 | 2026-10-31 | 2026-11-04
MS.CO.P1.FAG.111 | Beams and Slab Steel Fix | 2330.55 | M2 | 4 | 2026-11-05 | 2026-11-09
MS.CO.P1.FAG.112 | Beams and Slab Concreting work | 2330.55 | M2 | 1 | 2026-11-10 | 2026-11-10
MS.CO.P1.FAG.118 | DE shuttering for Slab | 2330.55 | M2 | 2 | 2026-12-03 | 2026-12-05
Masonry Works |  |  |  | 23 | 2026-12-10 | 2027-01-05
MS.CO.P1.FAG.122 | External Block Work |  |  | 14 | 2026-12-10 | 2026-12-26
MS.CO.P1.FAG.125 | Internal Block Work |  |  | 14 | 2026-12-21 | 2027-01-05
First Floor |  |  |  | 62 | 2026-11-11 | 2027-01-21
Vertical Element |  | 57 | PCS | 9 | 2026-11-11 | 2026-11-21
MS.CO.P1.FAG.114 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-11-11 | 2026-11-16
MS.CO.P1.FAG.115 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-11-14 | 2026-11-18
MS.CO.P1.FAG.117 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-11-16 | 2026-11-21
Slab |  | 2297.15 | M2 | 31 | 2026-11-18 | 2026-12-23
MS.CO.P1.FAG.119 | Beams and Slab Formwork | 2297.15 | M2 | 5 | 2026-11-18 | 2026-11-23
MS.CO.P1.FAG.120 | Beams and Slab Steel Fix | 2297.15 | M2 | 4 | 2026-11-24 | 2026-11-28
MS.CO.P1.FAG.121 | Beams and Slab Concreting work | 2297.15 | M2 | 1 | 2026-11-29 | 2026-11-29
MS.CO.P1.FAG.127 | DE shuttering for Slab | 2297.15 | M2 | 2 | 2026-12-22 | 2026-12-23
Masonry Works |  |  |  | 23 | 2026-12-27 | 2027-01-21
MS.CO.P1.FAG.131 | External Block Work |  |  | 14 | 2026-12-27 | 2027-01-11
MS.CO.P1.FAG.134 | Internal Block Work |  |  | 14 | 2027-01-06 | 2027-01-21
Second Floor |  |  |  | 61 | 2026-11-30 | 2027-02-08
Vertical Element |  | 57 | PCS | 9 | 2026-11-30 | 2026-12-09
MS.CO.P1.FAG.123 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-11-30 | 2026-12-05
MS.CO.P1.FAG.124 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-12-02 | 2026-12-07
MS.CO.P1.FAG.126 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-12-05 | 2026-12-09
Slab |  | 2295.17 | M2 | 31 | 2026-12-08 | 2027-01-12
MS.CO.P1.FAG.128 | Beams and Slab Formwork | 2295.17 | M2 | 5 | 2026-12-08 | 2026-12-13
MS.CO.P1.FAG.129 | Beams and Slab Steel Fix | 2295.17 | M2 | 4 | 2026-12-14 | 2026-12-17
MS.CO.P1.FAG.130 | Beams and Slab Concreting work | 2295.17 | M2 | 1 | 2026-12-19 | 2026-12-19
MS.CO.P1.FAG.136 | DE shuttering for Slab | 2295.17 | M2 | 2 | 2027-01-11 | 2027-01-12
Masonry Works |  |  |  | 23 | 2027-01-13 | 2027-02-08
MS.CO.P1.FAG.140 | External Block Work |  |  | 14 | 2027-01-13 | 2027-01-28
MS.CO.P1.FAG.143 | Internal Block Work |  |  | 14 | 2027-01-24 | 2027-02-08
Third Floor |  |  |  | 61 | 2026-12-20 | 2027-03-04
Vertical Element |  | 57 | PCS | 9 | 2026-12-20 | 2026-12-29
MS.CO.P1.FAG.132 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-12-20 | 2026-12-24
MS.CO.P1.FAG.133 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-12-22 | 2026-12-27
MS.CO.P1.FAG.135 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-12-24 | 2026-12-29
Slab |  | 2291.65 | M2 | 31 | 2026-12-28 | 2027-02-01
MS.CO.P1.FAG.137 | Beams and Slab Formwork | 2291.65 | M2 | 5 | 2026-12-28 | 2027-01-02
MS.CO.P1.FAG.138 | Beams and Slab Steel Fix | 2291.65 | M2 | 4 | 2027-01-03 | 2027-01-06
MS.CO.P1.FAG.139 | Beams and Slab Concreting work | 2291.65 | M2 | 1 | 2027-01-07 | 2027-01-07
MS.CO.P1.FAG.145 | DE shuttering for Slab | 2291.65 | M2 | 2 | 2027-01-31 | 2027-02-01
Masonry Works |  |  |  | 23 | 2027-02-02 | 2027-03-04
MS.CO.P1.FAG.149 | External Block Work |  |  | 14 | 2027-02-02 | 2027-02-18
MS.CO.P1.FAG.152 | Internal Block Work |  |  | 14 | 2027-02-14 | 2027-03-04
Fourth Floor |  |  |  | 56 | 2027-01-09 | 2027-03-23
Vertical Element |  | 57 | PCS | 7 | 2027-01-09 | 2027-01-16
MS.CO.P1.FAG.141 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2027-01-09 | 2027-01-12
MS.CO.P1.FAG.142 | Columns & Walls Formwork | 57 | PCS | 4 | 2027-01-10 | 2027-01-13
MS.CO.P1.FAG.144 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-01-12 | 2027-01-16
Slab |  | 2297.31 | M2 | 30 | 2027-01-16 | 2027-02-21
MS.CO.P1.FAG.146 | Beams and Slab Formwork | 2297.31 | M2 | 5 | 2027-01-16 | 2027-01-20
MS.CO.P1.FAG.147 | Beams and Slab Steel Fix | 2297.31 | M2 | 4 | 2027-01-21 | 2027-01-25
MS.CO.P1.FAG.148 | Beams and Slab Concreting work | 2297.31 | M2 | 1 | 2027-01-26 | 2027-01-26
MS.CO.P1.FAG.154 | DE shuttering for Slab | 2297.31 | M2 | 2 | 2027-02-20 | 2027-02-21
Masonry Works |  |  |  | 20 | 2027-02-23 | 2027-03-23
MS.CO.P1.FAG.158 | External Block Work |  |  | 12 | 2027-02-23 | 2027-03-14
MS.CO.P1.FAG.161 | Internal Block Work |  |  | 12 | 2027-03-07 | 2027-03-23
Fifth Floor |  |  |  | 47 | 2027-01-27 | 2027-03-31
Vertical Element |  | 57 | PCS | 7 | 2027-01-27 | 2027-02-03
MS.CO.P1.FAG.150 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2027-01-27 | 2027-02-01
MS.CO.P1.FAG.151 | Columns & Walls Formwork | 57 | PCS | 5 | 2027-01-28 | 2027-02-02
MS.CO.P1.FAG.153 | Columns & Walls Concreting work | 57 | PCS | 5 | 2027-01-30 | 2027-02-03
Slab |  | 2327.59 | M2 | 31 | 2027-02-01 | 2027-03-17
MS.CO.P1.FAG.155 | Beams and Slab Formwork | 2327.59 | M2 | 5 | 2027-02-01 | 2027-02-06
MS.CO.P1.FAG.156 | Beams and Slab Steel Fix | 2327.59 | M2 | 4 | 2027-02-07 | 2027-02-10
MS.CO.P1.FAG.157 | Beams and Slab Concreting work | 2327.59 | M2 | 1 | 2027-02-11 | 2027-02-11
MS.CO.P1.FAG.164 | DE shuttering for Slab | 2327.59 | M2 | 2 | 2027-03-16 | 2027-03-17
Masonry Works |  |  |  | 12 | 2027-03-18 | 2027-03-31
MS.CO.P1.FAG.167 | External Block Work |  |  | 10 | 2027-03-18 | 2027-03-29
MS.CO.P1.FAG.169 | Internal Block Work |  |  | 10 | 2027-03-21 | 2027-03-31
Penthouse Floor |  |  |  | 32 | 2027-02-14 | 2027-03-30
Vertical Element |  | 45 | PCS | 5 | 2027-02-14 | 2027-02-18
MS.CO.P1.FAG.159 | Columns & Walls Steel Fix | 45 | PCS | 3 | 2027-02-14 | 2027-02-16
MS.CO.P1.FAG.160 | Columns & Walls Formwork | 45 | PCS | 3 | 2027-02-15 | 2027-02-17
MS.CO.P1.FAG.162 | Columns & Walls Concreting work | 45 | PCS | 1 | 2027-02-18 | 2027-02-18
Slab |  | 563.66 | M2 | 21 | 2027-02-21 | 2027-03-23
MS.CO.P1.FAG.163 | Beams and Slab Formwork | 563.66 | M2 | 3 | 2027-02-21 | 2027-02-24
MS.CO.P1.FAG.165 | Beams and Slab Steel Fix | 563.66 | M2 | 3 | 2027-02-25 | 2027-03-01
MS.CO.P1.FAG.166 | Beams and Slab Concreting work | 563.66 | M2 | 1 | 2027-03-02 | 2027-03-02
MS.CO.P1.FAG.168 | DE shuttering for Slab | 563.66 | M2 | 2 | 2027-03-22 | 2027-03-23
Masonry Works |  |  |  | 6 | 2027-03-24 | 2027-03-30
MS.CO.P1.FAG.170 | External Block Work |  |  | 6 | 2027-03-24 | 2027-03-30
MS.CO.P1.FAG.171 | Internal Block Work |  |  | 6 | 2027-03-24 | 2027-03-30
6FA-F |  |  |  | 156 | 2026-09-21 | 2027-03-31
Lower Ground Floor |  |  |  | 67 | 2026-09-21 | 2026-12-08
Vertical Element |  | 57 | PCS | 7 | 2026-09-21 | 2026-09-29
MS.CO.P1.FAF.100 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-09-21 | 2026-09-26
MS.CO.P1.FAF.101 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-09-24 | 2026-09-28
MS.CO.P1.FAF.102 | Columns & Walls Concreting work | 57 | PCS | 1 | 2026-09-29 | 2026-09-29
Slab |  | 2705.93 | M2 | 31 | 2026-09-30 | 2026-11-04
MS.CO.P1.FAF.103 | Beams and Slab Formwork | 2705.93 | M2 | 5 | 2026-09-30 | 2026-10-05
MS.CO.P1.FAF.104 | Beams and Slab Steel Fix | 2705.93 | M2 | 4 | 2026-10-06 | 2026-10-10
MS.CO.P1.FAF.105 | Beams and Slab Concreting work | 2705.93 | M2 | 1 | 2026-10-11 | 2026-10-11
MS.CO.P1.FAF.109 | DE shuttering for Slab | 2705.93 | M2 | 2 | 2026-11-03 | 2026-11-04
Masonry Works |  |  |  | 29 | 2026-11-05 | 2026-12-08
MS.CO.P1.FAF.113 | External Block Work |  |  | 14 | 2026-11-05 | 2026-11-21
MS.CO.P1.FAF.116 | Internal Block Work |  |  | 20 | 2026-11-16 | 2026-12-08
Ground Floor |  |  |  | 64 | 2026-10-12 | 2026-12-24
Vertical Element |  | 57 | PCS | 8 | 2026-10-12 | 2026-10-20
MS.CO.P1.FAF.106 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-10-12 | 2026-10-17
MS.CO.P1.FAF.107 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-10-14 | 2026-10-19
MS.CO.P1.FAF.108 | Columns & Walls Concreting work | 57 | PCS | 1 | 2026-10-20 | 2026-10-20
Slab |  | 2330.55 | M2 | 31 | 2026-10-21 | 2026-11-25
MS.CO.P1.FAF.110 | Beams and Slab Formwork | 2330.55 | M2 | 5 | 2026-10-21 | 2026-10-26
MS.CO.P1.FAF.111 | Beams and Slab Steel Fix | 2330.55 | M2 | 4 | 2026-10-27 | 2026-10-31
MS.CO.P1.FAF.112 | Beams and Slab Concreting work | 2330.55 | M2 | 1 | 2026-11-01 | 2026-11-01
MS.CO.P1.FAF.118 | DE shuttering for Slab | 2330.55 | M2 | 2 | 2026-11-24 | 2026-11-25
Masonry Works |  |  |  | 25 | 2026-11-26 | 2026-12-24
MS.CO.P1.FAF.122 | External Block Work |  |  | 14 | 2026-11-26 | 2026-12-12
MS.CO.P1.FAF.125 | Internal Block Work |  |  | 14 | 2026-12-09 | 2026-12-24
First Floor |  |  |  | 60 | 2026-11-02 | 2027-01-10
Vertical Element |  | 57 | PCS | 9 | 2026-11-02 | 2026-11-11
MS.CO.P1.FAF.114 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-11-02 | 2026-11-07
MS.CO.P1.FAF.115 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-11-04 | 2026-11-09
MS.CO.P1.FAF.117 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-11-07 | 2026-11-11
Slab |  | 2297.15 | M2 | 31 | 2026-11-09 | 2026-12-14
MS.CO.P1.FAF.119 | Beams and Slab Formwork | 2297.15 | M2 | 5 | 2026-11-09 | 2026-11-14
MS.CO.P1.FAF.120 | Beams and Slab Steel Fix | 2297.15 | M2 | 4 | 2026-11-15 | 2026-11-18
MS.CO.P1.FAF.121 | Beams and Slab Concreting work | 2297.15 | M2 | 1 | 2026-11-19 | 2026-11-19
MS.CO.P1.FAF.127 | DE shuttering for Slab | 2297.15 | M2 | 2 | 2026-12-13 | 2026-12-14
Masonry Works |  |  |  | 23 | 2026-12-15 | 2027-01-10
MS.CO.P1.FAF.131 | External Block Work |  |  | 14 | 2026-12-15 | 2026-12-30
MS.CO.P1.FAF.134 | Internal Block Work |  |  | 14 | 2026-12-26 | 2027-01-10
Second Floor |  |  |  | 67 | 2026-11-21 | 2027-02-06
Vertical Element |  | 57 | PCS | 10 | 2026-11-21 | 2026-12-01
MS.CO.P1.FAF.123 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-11-21 | 2026-11-24
MS.CO.P1.FAF.124 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-11-24 | 2026-11-28
MS.CO.P1.FAF.126 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-11-28 | 2026-12-01
Slab |  | 2295.17 | M2 | 31 | 2026-11-29 | 2027-01-03
MS.CO.P1.FAF.128 | Beams and Slab Formwork | 2295.17 | M2 | 5 | 2026-11-29 | 2026-12-03
MS.CO.P1.FAF.129 | Beams and Slab Steel Fix | 2295.17 | M2 | 4 | 2026-12-05 | 2026-12-08
MS.CO.P1.FAF.130 | Beams and Slab Concreting work | 2295.17 | M2 | 1 | 2026-12-09 | 2026-12-09
MS.CO.P1.FAF.136 | DE shuttering for Slab | 2295.17 | M2 | 2 | 2027-01-02 | 2027-01-03
Masonry Works |  |  |  | 29 | 2027-01-04 | 2027-02-06
MS.CO.P1.FAF.140 | External Block Work |  |  | 14 | 2027-01-04 | 2027-01-19
MS.CO.P1.FAF.143 | Internal Block Work |  |  | 20 | 2027-01-14 | 2027-02-06
Third Floor |  |  |  | 64 | 2026-12-10 | 2027-02-25
Vertical Element |  | 57 | PCS | 8 | 2026-12-10 | 2026-12-19
MS.CO.P1.FAF.132 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-12-10 | 2026-12-14
MS.CO.P1.FAF.133 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-12-13 | 2026-12-16
MS.CO.P1.FAF.135 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-12-15 | 2026-12-19
Slab |  | 2291.65 | M2 | 31 | 2026-12-16 | 2027-01-20
MS.CO.P1.FAF.137 | Beams and Slab Formwork | 2291.65 | M2 | 5 | 2026-12-16 | 2026-12-21
MS.CO.P1.FAF.138 | Beams and Slab Steel Fix | 2291.65 | M2 | 4 | 2026-12-22 | 2026-12-26
MS.CO.P1.FAF.139 | Beams and Slab Concreting work | 2291.65 | M2 | 1 | 2026-12-27 | 2026-12-27
MS.CO.P1.FAF.145 | DE shuttering for Slab | 2291.65 | M2 | 2 | 2027-01-19 | 2027-01-20
Masonry Works |  |  |  | 28 | 2027-01-21 | 2027-02-25
MS.CO.P1.FAF.149 | External Block Work |  |  | 14 | 2027-01-21 | 2027-02-06
MS.CO.P1.FAF.152 | Internal Block Work |  |  | 14 | 2027-02-07 | 2027-02-25
Fourth Floor |  |  |  | 63 | 2026-12-28 | 2027-03-20
Vertical Element |  | 57 | PCS | 7 | 2026-12-28 | 2027-01-04
MS.CO.P1.FAF.141 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-12-28 | 2026-12-31
MS.CO.P1.FAF.142 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-12-30 | 2027-01-03
MS.CO.P1.FAF.144 | Columns & Walls Concreting work | 57 | PCS | 1 | 2027-01-04 | 2027-01-04
Slab |  | 2297.31 | M2 | 32 | 2027-01-05 | 2027-02-10
MS.CO.P1.FAF.146 | Beams and Slab Formwork | 2297.31 | M2 | 5 | 2027-01-05 | 2027-01-10
MS.CO.P1.FAF.147 | Beams and Slab Steel Fix | 2297.31 | M2 | 4 | 2027-01-11 | 2027-01-14
MS.CO.P1.FAF.148 | Beams and Slab Concreting work | 2297.31 | M2 | 4 | 2027-01-16 | 2027-01-19
MS.CO.P1.FAF.154 | DE shuttering for Slab | 2297.31 | M2 | 2 | 2027-02-09 | 2027-02-10
Masonry Works |  |  |  | 24 | 2027-02-11 | 2027-03-20
MS.CO.P1.FAF.158 | External Block Work |  |  | 14 | 2027-02-11 | 2027-03-03
MS.CO.P1.FAF.161 | Internal Block Work |  |  | 14 | 2027-02-28 | 2027-03-20
Fifth Floor |  |  |  | 53 | 2027-01-20 | 2027-03-31
Vertical Element |  | 57 | PCS | 8 | 2027-01-20 | 2027-01-28
MS.CO.P1.FAF.150 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2027-01-20 | 2027-01-25
MS.CO.P1.FAF.151 | Columns & Walls Formwork | 57 | PCS | 5 | 2027-01-23 | 2027-01-27
MS.CO.P1.FAF.153 | Columns & Walls Concreting work | 57 | PCS | 1 | 2027-01-28 | 2027-01-28
Slab |  | 2327.59 | M2 | 29 | 2027-01-30 | 2027-03-11
MS.CO.P1.FAF.155 | Beams and Slab Formwork | 2327.59 | M2 | 5 | 2027-01-30 | 2027-02-03
MS.CO.P1.FAF.156 | Beams and Slab Steel Fix | 2327.59 | M2 | 4 | 2027-02-04 | 2027-02-08
MS.CO.P1.FAF.157 | Beams and Slab Concreting work | 2327.59 | M2 | 1 | 2027-02-09 | 2027-02-09
MS.CO.P1.FAF.164 | DE shuttering for Slab | 2327.59 | M2 | 2 | 2027-03-10 | 2027-03-11
Masonry Works |  |  |  | 16 | 2027-03-14 | 2027-03-31
MS.CO.P1.FAF.167 | External Block Work |  |  | 12 | 2027-03-14 | 2027-03-27
MS.CO.P1.FAF.169 | Internal Block Work |  |  | 10 | 2027-03-21 | 2027-03-31
Penthouse Floor |  |  |  | 30 | 2027-02-10 | 2027-03-25
Vertical Element |  | 45 | PCS | 4 | 2027-02-10 | 2027-02-15
MS.CO.P1.FAF.159 | Columns & Walls Steel Fix | 45 | PCS | 2 | 2027-02-10 | 2027-02-11
MS.CO.P1.FAF.160 | Columns & Walls Formwork | 45 | PCS | 2 | 2027-02-11 | 2027-02-14
MS.CO.P1.FAF.162 | Columns & Walls Concreting work | 45 | PCS | 1 | 2027-02-15 | 2027-02-15
Slab |  | 563.66 | M2 | 20 | 2027-02-16 | 2027-03-18
MS.CO.P1.FAF.163 | Beams and Slab Formwork | 563.66 | M2 | 3 | 2027-02-16 | 2027-02-18
MS.CO.P1.FAF.165 | Beams and Slab Steel Fix | 563.66 | M2 | 3 | 2027-02-21 | 2027-02-24
MS.CO.P1.FAF.166 | Beams and Slab Concreting work | 563.66 | M2 | 1 | 2027-02-25 | 2027-02-25
MS.CO.P1.FAF.168 | DE shuttering for Slab | 563.66 | M2 | 1 | 2027-03-18 | 2027-03-18
Masonry Works |  |  |  | 6 | 2027-03-20 | 2027-03-25
MS.CO.P1.FAF.170 | External Block Work |  |  | 6 | 2027-03-20 | 2027-03-25
MS.CO.P1.FAF.171 | Internal Block Work |  |  | 6 | 2027-03-20 | 2027-03-25
6FA-E |  |  |  | 158 | 2026-09-16 | 2027-03-29
Lower Ground Floor |  |  |  | 69 | 2026-09-16 | 2026-12-06
Vertical Element |  | 57 | PCS | 9 | 2026-09-16 | 2026-09-27
MS.CO.P1.FAE.100 | Columns & Walls Steel Fix | 57 | PCS | 6 | 2026-09-16 | 2026-09-22
MS.CO.P1.FAE.101 | Columns & Walls Formwork | 57 | PCS | 6 | 2026-09-19 | 2026-09-26
MS.CO.P1.FAE.102 | Columns & Walls Concreting work | 57 | PCS | 1 | 2026-09-27 | 2026-09-27
Slab |  | 2705.93 | M2 | 31 | 2026-09-28 | 2026-11-02
MS.CO.P1.FAE.103 | Beams and Slab Formwork | 2705.93 | M2 | 5 | 2026-09-28 | 2026-10-03
MS.CO.P1.FAE.104 | Beams and Slab Steel Fix | 2705.93 | M2 | 4 | 2026-10-04 | 2026-10-07
MS.CO.P1.FAE.105 | Beams and Slab Concreting work | 2705.93 | M2 | 1 | 2026-10-08 | 2026-10-08
MS.CO.P1.FAE.109 | DE shuttering for Slab | 2705.93 | M2 | 2 | 2026-11-01 | 2026-11-02
Masonry Works |  |  |  | 29 | 2026-11-03 | 2026-12-06
MS.CO.P1.FAE.113 | External Block Work |  |  | 14 | 2026-11-03 | 2026-11-18
MS.CO.P1.FAE.116 | Internal Block Work |  |  | 20 | 2026-11-14 | 2026-12-06
Ground Floor |  |  |  | 72 | 2026-10-10 | 2026-12-31
Vertical Element |  | 57 | PCS | 9 | 2026-10-10 | 2026-10-19
MS.CO.P1.FAE.106 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-10-10 | 2026-10-14
MS.CO.P1.FAE.107 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-10-13 | 2026-10-18
MS.CO.P1.FAE.108 | Columns & Walls Concreting work | 57 | PCS | 1 | 2026-10-19 | 2026-10-19
Slab |  | 2330.55 | M2 | 34 | 2026-10-20 | 2026-11-28
MS.CO.P1.FAE.110 | Beams and Slab Formwork | 2330.55 | M2 | 7 | 2026-10-20 | 2026-10-27
MS.CO.P1.FAE.111 | Beams and Slab Steel Fix | 2330.55 | M2 | 5 | 2026-10-28 | 2026-11-02
MS.CO.P1.FAE.112 | Beams and Slab Concreting work | 2330.55 | M2 | 1 | 2026-11-03 | 2026-11-03
MS.CO.P1.FAE.118 | DE shuttering for Slab | 2330.55 | M2 | 2 | 2026-11-26 | 2026-11-28
Masonry Works |  |  |  | 29 | 2026-11-29 | 2026-12-31
MS.CO.P1.FAE.122 | External Block Work |  |  | 14 | 2026-11-29 | 2026-12-14
MS.CO.P1.FAE.125 | Internal Block Work |  |  | 20 | 2026-12-09 | 2026-12-31
First Floor |  |  |  | 70 | 2026-11-04 | 2027-01-24
Vertical Element |  | 57 | PCS | 6 | 2026-11-04 | 2026-11-10
MS.CO.P1.FAE.114 | Columns & Walls Steel Fix | 57 | PCS | 3 | 2026-11-04 | 2026-11-07
MS.CO.P1.FAE.115 | Columns & Walls Formwork | 57 | PCS | 3 | 2026-11-07 | 2026-11-09
MS.CO.P1.FAE.117 | Columns & Walls Concreting work | 57 | PCS | 1 | 2026-11-10 | 2026-11-10
Slab |  | 2297.15 | M2 | 31 | 2026-11-11 | 2026-12-16
MS.CO.P1.FAE.119 | Beams and Slab Formwork | 2297.15 | M2 | 5 | 2026-11-11 | 2026-11-16
MS.CO.P1.FAE.120 | Beams and Slab Steel Fix | 2297.15 | M2 | 4 | 2026-11-17 | 2026-11-21
MS.CO.P1.FAE.121 | Beams and Slab Concreting work | 2297.15 | M2 | 1 | 2026-11-22 | 2026-11-22
MS.CO.P1.FAE.127 | DE shuttering for Slab | 2297.15 | M2 | 2 | 2026-12-15 | 2026-12-16
Masonry Works |  |  |  | 33 | 2026-12-17 | 2027-01-24
MS.CO.P1.FAE.131 | External Block Work |  |  | 14 | 2026-12-17 | 2027-01-02
MS.CO.P1.FAE.134 | Internal Block Work |  |  | 20 | 2027-01-02 | 2027-01-24
Second Floor |  |  |  | 68 | 2026-11-23 | 2027-02-09
Vertical Element |  | 57 | PCS | 6 | 2026-11-23 | 2026-11-29
MS.CO.P1.FAE.123 | Columns & Walls Steel Fix | 57 | PCS | 3 | 2026-11-23 | 2026-11-25
MS.CO.P1.FAE.124 | Columns & Walls Formwork | 57 | PCS | 3 | 2026-11-25 | 2026-11-28
MS.CO.P1.FAE.126 | Columns & Walls Concreting work | 57 | PCS | 1 | 2026-11-29 | 2026-11-29
Slab |  | 2295.17 | M2 | 31 | 2026-11-30 | 2027-01-04
MS.CO.P1.FAE.128 | Beams and Slab Formwork | 2295.17 | M2 | 5 | 2026-11-30 | 2026-12-05
MS.CO.P1.FAE.129 | Beams and Slab Steel Fix | 2295.17 | M2 | 4 | 2026-12-06 | 2026-12-09
MS.CO.P1.FAE.130 | Beams and Slab Concreting work | 2295.17 | M2 | 1 | 2026-12-10 | 2026-12-10
MS.CO.P1.FAE.136 | DE shuttering for Slab | 2295.17 | M2 | 2 | 2027-01-03 | 2027-01-04
Masonry Works |  |  |  | 31 | 2027-01-05 | 2027-02-09
MS.CO.P1.FAE.140 | External Block Work |  |  | 14 | 2027-01-05 | 2027-01-20
MS.CO.P1.FAE.143 | Internal Block Work |  |  | 14 | 2027-01-25 | 2027-02-09
Third Floor |  |  |  | 66 | 2026-12-12 | 2027-03-02
Vertical Element |  | 57 | PCS | 5 | 2026-12-12 | 2026-12-16
MS.CO.P1.FAE.132 | Columns & Walls Steel Fix | 57 | PCS | 3 | 2026-12-12 | 2026-12-14
MS.CO.P1.FAE.133 | Columns & Walls Formwork | 57 | PCS | 3 | 2026-12-13 | 2026-12-15
MS.CO.P1.FAE.135 | Columns & Walls Concreting work | 57 | PCS | 1 | 2026-12-16 | 2026-12-16
Slab |  | 2291.65 | M2 | 31 | 2026-12-17 | 2027-01-21
MS.CO.P1.FAE.137 | Beams and Slab Formwork | 2291.65 | M2 | 5 | 2026-12-17 | 2026-12-22
MS.CO.P1.FAE.138 | Beams and Slab Steel Fix | 2291.65 | M2 | 4 | 2026-12-23 | 2026-12-27
MS.CO.P1.FAE.139 | Beams and Slab Concreting work | 2291.65 | M2 | 1 | 2026-12-28 | 2026-12-28
MS.CO.P1.FAE.145 | DE shuttering for Slab | 2291.65 | M2 | 2 | 2027-01-20 | 2027-01-21
Masonry Works |  |  |  | 30 | 2027-01-23 | 2027-03-02
MS.CO.P1.FAE.149 | External Block Work |  |  | 14 | 2027-01-23 | 2027-02-07
MS.CO.P1.FAE.152 | Internal Block Work |  |  | 14 | 2027-02-10 | 2027-03-02
Fourth Floor |  |  |  | 65 | 2026-12-29 | 2027-03-23
Vertical Element |  | 57 | PCS | 9 | 2026-12-29 | 2027-01-07
MS.CO.P1.FAE.141 | Columns & Walls Steel Fix | 57 | PCS | 3 | 2026-12-29 | 2026-12-31
MS.CO.P1.FAE.142 | Columns & Walls Formwork | 57 | PCS | 3 | 2027-01-02 | 2027-01-04
MS.CO.P1.FAE.144 | Columns & Walls Concreting work | 57 | PCS | 3 | 2027-01-05 | 2027-01-07
Slab |  | 2297.31 | M2 | 31 | 2027-01-07 | 2027-02-11
MS.CO.P1.FAE.146 | Beams and Slab Formwork | 2297.31 | M2 | 5 | 2027-01-07 | 2027-01-12
MS.CO.P1.FAE.147 | Beams and Slab Steel Fix | 2297.31 | M2 | 4 | 2027-01-13 | 2027-01-17
MS.CO.P1.FAE.148 | Beams and Slab Concreting work | 2297.31 | M2 | 1 | 2027-01-18 | 2027-01-18
MS.CO.P1.FAE.154 | DE shuttering for Slab | 2297.31 | M2 | 2 | 2027-02-10 | 2027-02-11
Masonry Works |  |  |  | 26 | 2027-02-14 | 2027-03-23
MS.CO.P1.FAE.158 | External Block Work |  |  | 14 | 2027-02-14 | 2027-03-04
MS.CO.P1.FAE.162 | Internal Block Work |  |  | 14 | 2027-03-03 | 2027-03-23
Fifth Floor |  |  |  | 51 | 2027-01-19 | 2027-03-28
Vertical Element |  | 57 | PCS | 10 | 2027-01-19 | 2027-01-30
MS.CO.P1.FAE.150 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2027-01-19 | 2027-01-23
MS.CO.P1.FAE.151 | Columns & Walls Formwork | 57 | PCS | 4 | 2027-01-23 | 2027-01-26
MS.CO.P1.FAE.153 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-01-26 | 2027-01-30
Slab |  | 2327.59 | M2 | 31 | 2027-01-27 | 2027-03-09
MS.CO.P1.FAE.155 | Beams and Slab Formwork | 2327.59 | M2 | 5 | 2027-01-27 | 2027-02-01
MS.CO.P1.FAE.156 | Beams and Slab Steel Fix | 2327.59 | M2 | 4 | 2027-02-02 | 2027-02-06
MS.CO.P1.FAE.157 | Beams and Slab Concreting work | 2327.59 | M2 | 1 | 2027-02-07 | 2027-02-07
MS.CO.P1.FAE.164 | DE shuttering for Slab | 2327.59 | M2 | 2 | 2027-03-08 | 2027-03-09
Masonry Works |  |  |  | 13 | 2027-03-14 | 2027-03-28
MS.CO.P1.FAE.167 | External Block Work |  |  | 10 | 2027-03-14 | 2027-03-24
MS.CO.P1.FAE.169 | Internal Block Work |  |  | 10 | 2027-03-17 | 2027-03-28
Penthouse Floor |  |  |  | 35 | 2027-02-08 | 2027-03-29
Vertical Element |  | 45 | PCS | 4 | 2027-02-08 | 2027-02-11
MS.CO.P1.FAE.159 | Columns & Walls Steel Fix | 45 | PCS | 2 | 2027-02-08 | 2027-02-09
MS.CO.P1.FAE.160 | Columns & Walls Formwork | 45 | PCS | 2 | 2027-02-09 | 2027-02-10
MS.CO.P1.FAE.161 | Columns & Walls Concreting work | 45 | PCS | 1 | 2027-02-11 | 2027-02-11
Slab |  | 563.66 | M2 | 17 | 2027-02-14 | 2027-03-11
MS.CO.P1.FAE.163 | Beams and Slab Formwork | 563.66 | M2 | 3 | 2027-02-14 | 2027-02-16
MS.CO.P1.FAE.165 | Beams and Slab Steel Fix | 563.66 | M2 | 2 | 2027-02-18 | 2027-02-21
MS.CO.P1.FAE.166 | Beams and Slab Concreting work | 563.66 | M2 | 1 | 2027-02-23 | 2027-02-23
MS.CO.P1.FAE.168 | DE shuttering for Slab | 563.66 | M2 | 2 | 2027-03-10 | 2027-03-11
Masonry Works |  |  |  | 14 | 2027-03-14 | 2027-03-29
MS.CO.P1.FAE.170 | External Block Work |  |  | 6 | 2027-03-14 | 2027-03-20
MS.CO.P1.FAE.171 | Internal Block Work |  |  | 6 | 2027-03-23 | 2027-03-29
Con.Phase (2) |  |  |  | 315 | 21-Dec-25 A | 2027-03-31
Soil Improvement |  |  |  | 72 | 21-Dec-25 A | 2026-06-29
MS.EN.P2.ALL.108 | Soil Improvement (By Other) |  |  | 22 | 21-Dec-25 A | 2026-06-22
A1070 | Post-Grouting Verification Test |  |  | 5 | 31-May-26 A | 2026-06-29
Sub-structure Works |  |  |  | 250 | 01-Jun-26 A | 2027-03-29
Foundation |  |  |  | 126 | 01-Jun-26 A | 2026-10-26
Part 01 |  |  |  | 55 | 01-Jun-26 A | 2026-08-03
Excavation, Blinding & Waterproofing Works |  | 1800 | M2 | 32 | 01-Jun-26 A | 2026-07-07
MS.CO.P2.FO.320 | Excavation for drop Panels and Trenches | 1800 | M2 | 7 | 01-Jun-26 A | 2026-06-15
MS.CO.P1.FO.540 | Earthing and Lightning Protection System | 1800 | M2 | 4 | 2026-06-16 | 2026-06-20
MS.CO.P2.FO.330 | Blinding concrete for lower Part of Foundation | 1800 | M2 | 3 | 2026-06-21 | 2026-06-23
MS.CO.P2.FO.340 | Block work for Drop Panels | 1800 | M2 | 1 | 2026-06-24 | 2026-06-24
MS.CO.P2.FO.350 | Blinding concrete for Upper Part | 1800 | M2 | 1 | 2026-06-25 | 2026-06-25
MS.CO.P2.FO.360 | Surface preparation and Angle filet at RW Edge | 1800 | M2 | 4 | 2026-06-27 | 2026-06-30
MS.CO.P2.FO.370 | Water Proofing Membrane under Raft Foundation | 1800 | M2 | 6 | 2026-07-01 | 2026-07-07
Raft Foundation Works |  | 3824 | M2 | 23 | 2026-07-08 | 2026-08-03
MS.CO.P2.FO.118 | Rebars for 1st layer for Foundation | 3824 | M2 | 8 | 2026-07-08 | 2026-07-16
MS.CO.P2.FO.124 | Installation for Mechanical and Electrical Embeds | 3824 | M2 | 7 | 2026-07-14 | 2026-07-21
MS.CO.P2.FO.126 | Formwork for Foundations | 3824 | M2 | 7 | 2026-07-15 | 2026-07-22
MS.CO.P2.FO.128 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 3824 | M2 | 8 | 2026-07-23 | 2026-08-01
MS.CO.P2.FO.130 | Foundations Concrete Pouring | 3824 | M2 | 2 | 2026-08-02 | 2026-08-03
Part 2 |  |  |  | 42 | 2026-06-16 | 2026-08-03
Excavation, Blinding & Waterproofing Works |  | 1800 | M2 | 25 | 2026-06-16 | 2026-07-14
MS.CO.P2.FO.100 | Excavation for drop Panels and Trenches | 1800 | M2 | 5 | 2026-06-16 | 2026-06-21
MS.CO.P1.FO.250 | Earthing and Lightning Protection System | 1800 | M2 | 3 | 2026-06-22 | 2026-06-24
MS.CO.P2.FO.101 | Blinding concrete for lower Part of Foundation | 1800 | M2 | 3 | 2026-06-25 | 2026-06-28
MS.CO.P2.FO.102 | Block work for Drop Panels | 1800 | M2 | 2 | 2026-06-29 | 2026-06-30
MS.CO.P2.FO.103 | Blinding concrete for Upper Part | 1800 | M2 | 2 | 2026-07-01 | 2026-07-02
MS.CO.P2.FO.104 | Surface preparation and Angle filet at RW Edge | 1800 | M2 | 4 | 2026-07-04 | 2026-07-07
MS.CO.P2.FO.105 | Water Proofing Membrane under Raft Foundation | 1800 | M2 | 6 | 2026-07-08 | 2026-07-14
Raft Foundation Works |  | 3824 | M2 | 15 | 2026-07-18 | 2026-08-03
MS.CO.P2.FO.106 | Rebars for 1st layer for Foundation | 3824 | M2 | 7 | 2026-07-18 | 2026-07-25
MS.CO.P2.FO.107 | Installation for Mechanical and Electrical Embeds | 3824 | M2 | 5 | 2026-07-25 | 2026-07-29
MS.CO.P2.FO.108 | Formwork for Foundations | 3824 | M2 | 4 | 2026-07-27 | 2026-07-30
MS.CO.P2.FO.110 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 3824 | M2 | 4 | 2026-07-28 | 2026-08-01
MS.CO.P2.FO.113 | Foundations Concrete Pouring | 3824 | M2 | 2 | 2026-08-02 | 2026-08-03
Part 3 |  |  |  | 46 | 2026-06-22 | 2026-08-13
Excavation, Blinding & Waterproofing Works |  | 1800 | M2 | 28 | 2026-06-22 | 2026-07-23
MS.CO.P2.FO.140 | Excavation for drop Panels and Trenches | 1800 | M2 | 7 | 2026-06-22 | 2026-06-29
MS.CO.P1.FO.480 | Earthing and Lightning Protection System | 1800 | M2 | 3 | 2026-06-30 | 2026-07-02
MS.CO.P2.FO.150 | Blinding concrete for lower Part of Foundation | 1800 | M2 | 3 | 2026-07-04 | 2026-07-06
MS.CO.P2.FO.160 | Block work for Drop Panels | 1800 | M2 | 2 | 2026-07-07 | 2026-07-08
MS.CO.P2.FO.170 | Blinding concrete for Upper Part | 1800 | M2 | 2 | 2026-07-09 | 2026-07-11
MS.CO.P2.FO.180 | Surface preparation and Angle filet at RW Edge | 1800 | M2 | 5 | 2026-07-12 | 2026-07-16
MS.CO.P2.FO.190 | Water Proofing Membrane under Raft Foundation | 1800 | M2 | 6 | 2026-07-18 | 2026-07-23
Raft Foundation Works |  | 3824 | M2 | 17 | 2026-07-26 | 2026-08-13
MS.CO.P2.FO.109 | Rebars for 1st layer for Foundation | 3824 | M2 | 7 | 2026-07-26 | 2026-08-02
MS.CO.P2.FO.111 | Installation for Mechanical and Electrical Embeds | 3824 | M2 | 7 | 2026-07-30 | 2026-08-06
MS.CO.P2.FO.114 | Formwork for Foundations | 3824 | M2 | 4 | 2026-08-04 | 2026-08-08
MS.CO.P2.FO.116 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 3824 | M2 | 4 | 2026-08-08 | 2026-08-11
MS.CO.P2.FO.121 | Foundations Concrete Pouring | 3824 | M2 | 2 | 2026-08-12 | 2026-08-13
Part 4 |  |  |  | 50 | 2026-06-30 | 2026-08-26
Excavation, Blinding & Waterproofing Works |  | 1800 | M2 | 28 | 2026-06-30 | 2026-08-01
MS.CO.P2.FO.200 | Excavation for drop Panels and Trenches | 1800 | M2 | 7 | 2026-06-30 | 2026-07-07
MS.CO.P1.FO.490 | Earthing and Lightning Protection System | 1800 | M2 | 3 | 2026-07-08 | 2026-07-11
MS.CO.P2.FO.210 | Blinding concrete for lower Part of Foundation | 1800 | M2 | 3 | 2026-07-12 | 2026-07-14
MS.CO.P2.FO.220 | Block work for Drop Panels | 1800 | M2 | 2 | 2026-07-15 | 2026-07-16
MS.CO.P2.FO.230 | Blinding concrete for Upper Part | 1800 | M2 | 2 | 2026-07-18 | 2026-07-19
MS.CO.P2.FO.240 | Surface preparation and Angle filet at RW Edge | 1800 | M2 | 5 | 2026-07-20 | 2026-07-25
MS.CO.P2.FO.250 | Water Proofing Membrane under Raft Foundation | 1800 | M2 | 6 | 2026-07-26 | 2026-08-01
Raft Foundation Works |  | 3824 | M2 | 21 | 2026-08-03 | 2026-08-26
MS.CO.P2.FO.115 | Rebars for 1st layer for Foundation | 3824 | M2 | 7 | 2026-08-03 | 2026-08-10
MS.CO.P2.FO.119 | Installation for Mechanical and Electrical Embeds | 3824 | M2 | 6 | 2026-08-13 | 2026-08-19
MS.CO.P2.FO.122 | Formwork for Foundations | 3824 | M2 | 4 | 2026-08-17 | 2026-08-20
MS.CO.P2.FO.125 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 3824 | M2 | 4 | 2026-08-20 | 2026-08-24
MS.CO.P2.FO.129 | Foundations Concrete Pouring | 3824 | M2 | 2 | 2026-08-25 | 2026-08-26
Part 5 |  |  |  | 51 | 2026-08-27 | 2026-10-26
Excavation, Blinding & Waterproofing Works |  | 1800 | M2 | 29 | 2026-08-27 | 2026-09-30
MS.CO.P2.FO.260 | Excavation for drop Panels and Trenches | 1800 | M2 | 5 | 2026-08-27 | 2026-09-01
MS.CO.P1.FO.500 | Earthing and Lightning Protection System | 1800 | M2 | 4 | 2026-09-02 | 2026-09-06
MS.CO.P2.FO.270 | Blinding concrete for lower Part of Foundation | 1800 | M2 | 4 | 2026-09-07 | 2026-09-10
MS.CO.P2.FO.280 | Block work for Drop Panels | 1800 | M2 | 4 | 2026-09-12 | 2026-09-15
MS.CO.P2.FO.290 | Blinding concrete for Upper Part | 1800 | M2 | 2 | 2026-09-16 | 2026-09-17
MS.CO.P2.FO.300 | Surface preparation and Angle filet at RW Edge | 1800 | M2 | 4 | 2026-09-19 | 2026-09-22
MS.CO.P2.FO.310 | Water Proofing Membrane under Raft Foundation | 1800 | M2 | 6 | 2026-09-24 | 2026-09-30
Raft Foundation Works |  | 3824 | M2 | 22 | 2026-10-01 | 2026-10-26
MS.CO.P2.FO.112 | Rebars for 1st layer for Foundation | 3824 | M2 | 8 | 2026-10-01 | 2026-10-10
MS.CO.P2.FO.117 | Installation for Mechanical and Electrical Embeds | 3824 | M2 | 9 | 2026-10-05 | 2026-10-14
MS.CO.P2.FO.120 | Formwork for Foundations | 3824 | M2 | 9 | 2026-10-06 | 2026-10-15
MS.CO.P2.FO.123 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 3824 | M2 | 9 | 2026-10-14 | 2026-10-24
MS.CO.P2.FO.127 | Foundations Concrete Pouring | 3824 | M2 | 2 | 2026-10-25 | 2026-10-26
Basement 3 |  |  |  | 115 | 2026-08-05 | 2026-12-17
Skeleton Works |  |  |  | 115 | 2026-08-05 | 2026-12-17
Vertical Element |  |  |  | 84 | 2026-08-05 | 2026-11-11
Part 1 |  |  |  | 12 | 2026-08-05 | 2026-08-18
MS.CO.P2.B3.107 | B3 - Columns Steel Fix | 40 | PCS | 6 | 2026-08-05 | 2026-08-11
MS.CO.P2.B3.207 | B3 - Walls Steel Fix | 427 | m2 | 6 | 2026-08-05 | 2026-08-11
MS.CO.P2.B3.111 | B3 - Columns Formwork | 40 | PCS | 6 | 2026-08-09 | 2026-08-15
MS.CO.P2.B3.211 | B3 - Walls Formwork | 427 | m2 | 6 | 2026-08-09 | 2026-08-15
MS.CO.P2.B3.114 | B3 - Columns Concreting work | 40 | PCS | 6 | 2026-08-12 | 2026-08-18
MS.CO.P2.B3.214 | B3 - Walls Concreting work | 427 | m2 | 6 | 2026-08-12 | 2026-08-18
Part 2 |  |  |  | 12 | 2026-08-05 | 2026-08-18
MS.CO.P2.B3.100 | B3 - Columns Steel Fix | 40 | PCS | 6 | 2026-08-05 | 2026-08-11
MS.CO.P2.B3.200 | B3 - Walls Steel Fix | 427 | m2 | 6 | 2026-08-05 | 2026-08-11
MS.CO.P2.B3.101 | B3 - Columns Formwork | 40 | PCS | 6 | 2026-08-09 | 2026-08-15
MS.CO.P2.B3.201 | B3 - Walls Formwork | 427 | m2 | 6 | 2026-08-09 | 2026-08-15
MS.CO.P2.B3.103 | B3 - Columns Concreting work | 40 | PCS | 6 | 2026-08-12 | 2026-08-18
MS.CO.P2.B3.203 | B3 - Walls Concreting work | 427 | m2 | 6 | 2026-08-12 | 2026-08-18
Part 3 |  |  |  | 12 | 2026-08-17 | 2026-08-30
MS.CO.P2.B3.102 | B3 - Columns Steel Fix | 40 | PCS | 6 | 2026-08-17 | 2026-08-23
MS.CO.P2.B3.202 | B3 - Walls Steel Fix | 427 | m2 | 6 | 2026-08-17 | 2026-08-23
MS.CO.P2.B3.104 | B3 - Columns Formwork | 40 | PCS | 6 | 2026-08-20 | 2026-08-26
MS.CO.P2.B3.204 | B3 - Walls Formwork | 427 | m2 | 6 | 2026-08-20 | 2026-08-26
MS.CO.P2.B3.108 | B3 - Columns Concreting work | 40 | PCS | 6 | 2026-08-24 | 2026-08-30
MS.CO.P2.B3.208 | B3 - Walls Concreting work | 427 | m2 | 6 | 2026-08-24 | 2026-08-30
Part 4 |  |  |  | 12 | 2026-08-30 | 2026-09-12
MS.CO.P2.B3.106 | B3 - Columns Steel Fix | 40 | PCS | 6 | 2026-08-30 | 2026-09-05
MS.CO.P2.B3.206 | B3 - Walls Steel Fix | 427 | m2 | 6 | 2026-08-30 | 2026-09-05
MS.CO.P2.B3.110 | B3 - Columns Formwork | 40 | PCS | 6 | 2026-09-02 | 2026-09-08
MS.CO.P2.B3.210 | B3 - Walls Formwork | 427 | m2 | 6 | 2026-09-02 | 2026-09-08
MS.CO.P2.B3.113 | B3 - Columns Concreting work | 40 | PCS | 6 | 2026-09-06 | 2026-09-12
MS.CO.P2.B3.213 | B3 - Walls Concreting work | 427 | m2 | 6 | 2026-09-06 | 2026-09-12
Part 5 |  |  |  | 12 | 2026-10-29 | 2026-11-11
MS.CO.P2.B3.105 | B3 - Columns Steel Fix | 40 | PCS | 6 | 2026-10-29 | 2026-11-04
MS.CO.P2.B3.205 | B3 - Walls Steel Fix | 427 | m2 | 6 | 2026-10-29 | 2026-11-04
MS.CO.P2.B3.109 | B3 - Columns Formwork | 40 | PCS | 6 | 2026-11-02 | 2026-11-08
MS.CO.P2.B3.209 | B3 - Walls Formwork | 427 | m2 | 6 | 2026-11-02 | 2026-11-08
MS.CO.P2.B3.112 | B3 - Columns Concreting work | 40 | PCS | 6 | 2026-11-05 | 2026-11-11
MS.CO.P2.B3.212 | B3 - Walls Concreting work | 427 | m2 | 6 | 2026-11-05 | 2026-11-11
Slab |  | 4663 | m2 | 107 | 2026-08-15 | 2026-12-17
Part 1 |  |  |  | 35 | 2026-08-15 | 2026-09-24
MS.CO.P2.B3.122 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-08-15 | 2026-08-23
MS.CO.P2.B3.124 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-08-24 | 2026-08-30
MS.CO.P2.B3.129 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-08-31 | 2026-08-31
MS.CO.P2.B3.134 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-09-23 | 2026-09-24
Part 2 |  |  |  | 36 | 2026-08-16 | 2026-09-27
MS.CO.P2.B3.115 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-08-16 | 2026-08-24
MS.CO.P2.B3.117 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-08-25 | 2026-08-31
MS.CO.P2.B3.125 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-09-01 | 2026-09-01
MS.CO.P2.B3.130 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-09-26 | 2026-09-27
Part 3 |  |  |  | 36 | 2026-08-26 | 2026-10-07
MS.CO.P2.B3.116 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-08-26 | 2026-09-03
MS.CO.P2.B3.119 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-09-05 | 2026-09-10
MS.CO.P2.B3.126 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-09-12 | 2026-09-12
MS.CO.P2.B3.131 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-10-06 | 2026-10-07
Part 4 |  |  |  | 36 | 2026-09-08 | 2026-10-20
MS.CO.P2.B3.120 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-09-08 | 2026-09-16
MS.CO.P2.B3.123 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-09-17 | 2026-09-24
MS.CO.P2.B3.128 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-09-26 | 2026-09-26
MS.CO.P2.B3.133 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-10-19 | 2026-10-20
Part 5 |  |  |  | 36 | 2026-11-07 | 2026-12-17
MS.CO.P2.B3.118 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-11-07 | 2026-11-15
MS.CO.P2.B3.121 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-11-16 | 2026-11-22
MS.CO.P2.B3.127 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-11-23 | 2026-11-23
MS.CO.P2.B3.132 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-12-16 | 2026-12-17
Basement 2 |  |  |  | 162 | 2026-09-01 | 2027-03-18
Skeleton Works |  |  |  | 129 | 2026-09-01 | 2027-01-30
Vertical Element |  |  |  | 83 | 2026-09-01 | 2026-12-07
Part 1 |  |  |  | 12 | 2026-09-01 | 2026-09-14
MS.CO.P2.B2.108 | B2 - Columns Steel Fix | 40 | PCS | 6 | 2026-09-01 | 2026-09-07
MS.CO.P2.B2.208 | B2 - Walls Steel Fix | 617 | m2 | 6 | 2026-09-01 | 2026-09-07
MS.CO.P2.B2.112 | B2 - Columns Formwork | 40 | PCS | 6 | 2026-09-05 | 2026-09-10
MS.CO.P2.B2.212 | B2 - Walls Formwork | 617 | m2 | 6 | 2026-09-05 | 2026-09-10
MS.CO.P2.B2.114 | B2 - Columns Concreting work | 40 | PCS | 6 | 2026-09-08 | 2026-09-14
MS.CO.P2.B2.214 | B2 - Walls Concreting work | 617 | m2 | 6 | 2026-09-08 | 2026-09-14
Part 2 |  |  |  | 12 | 2026-09-02 | 2026-09-15
MS.CO.P2.B2.100 | B2 - Columns Steel Fix | 40 | PCS | 6 | 2026-09-02 | 2026-09-08
MS.CO.P2.B2.200 | B2 - Walls Steel Fix | 617 | m2 | 6 | 2026-09-02 | 2026-09-08
MS.CO.P2.B2.102 | B2 - Columns Formwork | 40 | PCS | 6 | 2026-09-06 | 2026-09-12
MS.CO.P2.B2.202 | B2 - Walls Formwork | 617 | m2 | 6 | 2026-09-06 | 2026-09-12
MS.CO.P2.B2.106 | B2 - Columns Concreting work | 40 | PCS | 6 | 2026-09-09 | 2026-09-15
MS.CO.P2.B2.206 | B2 - Walls Concreting work | 617 | m2 | 6 | 2026-09-09 | 2026-09-15
Part 3 |  |  |  | 12 | 2026-09-13 | 2026-09-27
MS.CO.P2.B2.101 | B2 - Columns Steel Fix | 40 | PCS | 6 | 2026-09-13 | 2026-09-19
MS.CO.P2.B2.201 | B2 - Walls Steel Fix | 617 | m2 | 6 | 2026-09-13 | 2026-09-19
MS.CO.P2.B2.104 | B2 - Columns Formwork | 40 | PCS | 6 | 2026-09-16 | 2026-09-22
MS.CO.P2.B2.204 | B2 - Walls Formwork | 617 | m2 | 6 | 2026-09-16 | 2026-09-22
MS.CO.P2.B2.109 | B2 - Columns Concreting work | 40 | PCS | 6 | 2026-09-20 | 2026-09-27
MS.CO.P2.B2.209 | B2 - Walls Concreting work | 617 | m2 | 6 | 2026-09-20 | 2026-09-27
Part 4 |  |  |  | 12 | 2026-09-27 | 2026-10-10
MS.CO.P2.B2.105 | B2 - Columns Steel Fix | 40 | PCS | 6 | 2026-09-27 | 2026-10-03
MS.CO.P2.B2.205 | B2 - Walls Steel Fix | 617 | m2 | 6 | 2026-09-27 | 2026-10-03
MS.CO.P2.B2.110 | B2 - Columns Formwork | 40 | PCS | 6 | 2026-09-30 | 2026-10-06
MS.CO.P2.B2.210 | B2 - Walls Formwork | 617 | m2 | 6 | 2026-09-30 | 2026-10-06
MS.CO.P2.B2.113 | B2 - Columns Concreting work | 40 | PCS | 6 | 2026-10-04 | 2026-10-10
MS.CO.P2.B2.213 | B2 - Walls Concreting work | 617 | m2 | 6 | 2026-10-04 | 2026-10-10
Part 5 |  |  |  | 12 | 2026-11-24 | 2026-12-07
MS.CO.P2.B2.103 | B2 - Columns Steel Fix | 40 | PCS | 6 | 2026-11-24 | 2026-11-30
MS.CO.P2.B2.203 | B2 - Walls Steel Fix | 617 | m2 | 6 | 2026-11-24 | 2026-11-30
MS.CO.P2.B2.107 | B2 - Columns Formwork | 40 | PCS | 6 | 2026-11-28 | 2026-12-03
MS.CO.P2.B2.207 | B2 - Walls Formwork | 617 | m2 | 6 | 2026-11-28 | 2026-12-03
MS.CO.P2.B2.111 | B2 - Columns Concreting work | 40 | PCS | 6 | 2026-12-01 | 2026-12-07
MS.CO.P2.B2.211 | B2 - Walls Concreting work | 617 | m2 | 6 | 2026-12-01 | 2026-12-07
Slab |  | 4663 | m2 | 122 | 2026-09-09 | 2027-01-30
Part 1 |  |  |  | 39 | 2026-09-09 | 2026-10-25
MS.CO.P2.B2.124 | Beams and Slab Formwork | 4663 | m2 | 10 | 2026-09-09 | 2026-09-20
MS.CO.P2.B2.128 | Beams and Slab Steel Fix | 4663 | m2 | 7 | 2026-09-21 | 2026-09-29
MS.CO.P2.B2.129 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-09-30 | 2026-09-30
MS.CO.P2.B2.134 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-10-24 | 2026-10-25
Part 2 |  |  |  | 39 | 2026-09-10 | 2026-10-26
MS.CO.P2.B2.115 | Beams and Slab Formwork | 4663 | m2 | 10 | 2026-09-10 | 2026-09-21
MS.CO.P2.B2.117 | Beams and Slab Steel Fix | 4663 | m2 | 7 | 2026-09-22 | 2026-09-30
MS.CO.P2.B2.119 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-10-01 | 2026-10-01
MS.CO.P2.B2.130 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-10-25 | 2026-10-26
Part 3 |  |  |  | 39 | 2026-09-21 | 2026-11-05
MS.CO.P2.B2.116 | Beams and Slab Formwork | 4663 | m2 | 10 | 2026-09-21 | 2026-10-03
MS.CO.P2.B2.120 | Beams and Slab Steel Fix | 4663 | m2 | 7 | 2026-10-04 | 2026-10-11
MS.CO.P2.B2.122 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-10-12 | 2026-10-12
MS.CO.P2.B2.131 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-11-04 | 2026-11-05
Part 4 |  |  |  | 39 | 2026-10-05 | 2026-11-18
MS.CO.P2.B2.121 | Beams and Slab Formwork | 4663 | m2 | 10 | 2026-10-05 | 2026-10-15
MS.CO.P2.B2.125 | Beams and Slab Steel Fix | 4663 | m2 | 7 | 2026-10-17 | 2026-10-24
MS.CO.P2.B2.127 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-10-25 | 2026-10-25
MS.CO.P2.B2.133 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-11-17 | 2026-11-18
Part 5 |  |  |  | 37 | 2026-12-19 | 2027-01-30
MS.CO.P2.B2.118 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-12-19 | 2026-12-27
MS.CO.P2.B2.123 | Beams and Slab Steel Fix | 4663 | m2 | 7 | 2026-12-28 | 2027-01-04
MS.CO.P2.B2.126 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2027-01-05 | 2027-01-05
MS.CO.P2.B2.132 | DE shuttering for Slab | 4663 | m2 | 2 | 2027-01-28 | 2027-01-30
Masonry Works |  |  |  | 33 | 2027-01-31 | 2027-03-18
MS.CO.P2.B2.135 | B2 - Block Works |  |  | 33 | 2027-01-31 | 2027-03-18
Basement 1 |  |  |  | 146 | 2026-10-01 | 2027-03-29
Skeleton Works |  |  |  | 136 | 2026-10-01 | 2027-03-17
Vertical Element |  |  |  | 95 | 2026-10-01 | 2027-01-19
Part 1 (4,931.90 M2) |  |  |  | 12 | 2026-10-01 | 2026-10-14
MS.CO.P2.B1.108 | B1 - Columns Steel Fix | 40 | PCS | 6 | 2026-10-01 | 2026-10-07
MS.CO.P2.B1.208 | B1 - Walls Steel Fix | 617 | m2 | 6 | 2026-10-01 | 2026-10-07
MS.CO.P2.B1.112 | B1 - Columns Formwork | 40 | PCS | 6 | 2026-10-05 | 2026-10-11
MS.CO.P2.B1.212 | B1 - Walls Formwork | 617 | m2 | 6 | 2026-10-05 | 2026-10-11
MS.CO.P2.B1.114 | B1 - Columns Concreting work | 40 | PCS | 6 | 2026-10-08 | 2026-10-14
MS.CO.P2.B1.214 | B1 - Walls Concreting work | 617 | m2 | 6 | 2026-10-08 | 2026-10-14
Part 2 (4,931.90 M2) |  |  |  | 12 | 2026-10-03 | 2026-10-15
MS.CO.P2.B1.100 | B1 - Columns Steel Fix | 40 | PCS | 6 | 2026-10-03 | 2026-10-08
MS.CO.P2.B1.200 | B1 - Walls Steel Fix | 617 | m2 | 6 | 2026-10-03 | 2026-10-08
MS.CO.P2.B1.102 | B1 - Columns Formwork | 40 | PCS | 6 | 2026-10-06 | 2026-10-12
MS.CO.P2.B1.202 | B1 - Walls Formwork | 617 | m2 | 6 | 2026-10-06 | 2026-10-12
MS.CO.P2.B1.106 | B1 - Columns Concreting work | 40 | PCS | 6 | 2026-10-10 | 2026-10-15
MS.CO.P2.B1.206 | B1 - Walls Concreting work | 617 | m2 | 6 | 2026-10-10 | 2026-10-15
Part 3 (4,931.90 M2) |  |  |  | 12 | 2026-10-13 | 2026-10-26
MS.CO.P2.B1.101 | B1 - Columns Steel Fix | 40 | PCS | 6 | 2026-10-13 | 2026-10-19
MS.CO.P2.B1.201 | B1 - Walls Steel Fix | 617 | m2 | 6 | 2026-10-13 | 2026-10-19
MS.CO.P2.B1.104 | B1 - Columns Formwork | 40 | PCS | 6 | 2026-10-17 | 2026-10-22
MS.CO.P2.B1.204 | B1 - Walls Formwork | 617 | m2 | 6 | 2026-10-17 | 2026-10-22
MS.CO.P2.B1.109 | B1 - Columns Concreting work | 40 | PCS | 6 | 2026-10-20 | 2026-10-26
MS.CO.P2.B1.209 | B1 - Walls Concreting work | 617 | m2 | 6 | 2026-10-20 | 2026-10-26
Part 4 (4,931.90 M2) |  |  |  | 12 | 2026-10-26 | 2026-11-08
MS.CO.P2.B1.105 | B1 - Columns Steel Fix | 40 | PCS | 6 | 2026-10-26 | 2026-11-01
MS.CO.P2.B1.205 | B1 - Walls Steel Fix | 617 | m2 | 6 | 2026-10-26 | 2026-11-01
MS.CO.P2.B1.110 | B1 - Columns Formwork | 40 | PCS | 6 | 2026-10-29 | 2026-11-04
MS.CO.P2.B1.210 | B1 - Walls Formwork | 617 | m2 | 6 | 2026-10-29 | 2026-11-04
MS.CO.P2.B1.113 | B1 - Columns Concreting work | 40 | PCS | 6 | 2026-11-02 | 2026-11-08
MS.CO.P2.B1.213 | B1 - Walls Concreting work | 617 | m2 | 6 | 2026-11-02 | 2026-11-08
Part 5 (4,931.90 M2) |  |  |  | 12 | 2027-01-06 | 2027-01-19
MS.CO.P2.B1.103 | B1 - Columns Steel Fix | 40 | PCS | 6 | 2027-01-06 | 2027-01-12
MS.CO.P2.B1.203 | B1 - Walls Steel Fix | 617 | m2 | 6 | 2027-01-06 | 2027-01-12
MS.CO.P2.B1.107 | B1 - Columns Formwork | 40 | PCS | 6 | 2027-01-10 | 2027-01-16
MS.CO.P2.B1.207 | B1 - Walls Formwork | 617 | m2 | 6 | 2027-01-10 | 2027-01-16
MS.CO.P2.B1.111 | B1 - Columns Concreting work | 40 | PCS | 6 | 2027-01-13 | 2027-01-19
MS.CO.P2.B1.211 | B1 - Walls Concreting work | 617 | m2 | 6 | 2027-01-13 | 2027-01-19
Slab |  | 4663 | m2 | 129 | 2026-10-10 | 2027-03-17
Part 1 (4,931.90 M2) |  |  |  | 36 | 2026-10-10 | 2026-11-19
MS.CO.P2.B1.124 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-10-10 | 2026-10-18
MS.CO.P2.B1.128 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-10-19 | 2026-10-25
MS.CO.P2.B1.129 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-10-26 | 2026-10-26
MS.CO.P2.B1.134 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-11-18 | 2026-11-19
Part 2 (4,931.90 M2) |  |  |  | 36 | 2026-10-12 | 2026-11-22
MS.CO.P2.B1.115 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-10-12 | 2026-10-20
MS.CO.P2.B1.117 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-10-21 | 2026-10-27
MS.CO.P2.B1.119 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-10-28 | 2026-10-28
MS.CO.P2.B1.130 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-11-21 | 2026-11-22
Part 3 (4,931.90 M2) |  |  |  | 36 | 2026-10-22 | 2026-12-02
MS.CO.P2.B1.116 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-10-22 | 2026-10-31
MS.CO.P2.B1.120 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-11-01 | 2026-11-07
MS.CO.P2.B1.122 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-11-08 | 2026-11-08
MS.CO.P2.B1.131 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-12-01 | 2026-12-02
Part 4 (4,931.90 M2) |  |  |  | 36 | 2026-11-04 | 2026-12-15
MS.CO.P2.B1.121 | Beams and Slab Formwork | 4663 | m2 | 8 | 2026-11-04 | 2026-11-12
MS.CO.P2.B1.125 | Beams and Slab Steel Fix | 4663 | m2 | 6 | 2026-11-14 | 2026-11-19
MS.CO.P2.B1.127 | Beams and Slab Concreting work | 4663 | m2 | 1 | 2026-11-21 | 2026-11-21
MS.CO.P2.B1.133 | DE shuttering for Slab | 4663 | m2 | 2 | 2026-12-14 | 2026-12-15
Part 5 (4,931.90 M2) |  |  |  | 32 | 2027-01-31 | 2027-03-17
MS.CO.P2.B1.118 | Beams and Slab Formwork | 4663 | m2 | 8 | 2027-01-31 | 2027-02-08
MS.CO.P2.B1.123 | Beams and Slab Steel Fix | 4663 | m2 | 7 | 2027-02-09 | 2027-02-17
MS.CO.P2.B1.126 | Beams and Slab Concreting work | 4663 | m2 | 3 | 2027-02-18 | 2027-02-23
MS.CO.P2.B1.132 | DE shuttering for Slab | 4663 | m2 | 2 | 2027-03-15 | 2027-03-17
Masonry Works |  |  |  | 10 | 2027-03-17 | 2027-03-29
MS.CO.P2.B1.135 | B1 - Block Works |  |  | 10 | 2027-03-17 | 2027-03-29
Super Structure Works |  |  |  | 126 | 2026-10-27 | 2027-03-31
Hotel |  |  |  | 124 | 2026-10-29 | 2027-03-31
Ground Floor |  |  |  | 68 | 2026-10-29 | 2027-01-16
Vertical Element |  |  |  | 10 | 2026-10-29 | 2026-11-09
MS.CO.P2.HO.100 | Columns & Walls Steel Fix | 92 | PCs | 6 | 2026-10-29 | 2026-11-04
MS.CO.P2.HO.101 | Columns & Walls Formwork | 92 | PCs | 6 | 2026-11-01 | 2026-11-07
MS.CO.P2.HO.102 | Columns & Walls Concreting work | 92 | PCs | 6 | 2026-11-03 | 2026-11-09
Slab |  | 2114.58 | M2 | 34 | 2026-11-04 | 2026-12-13
MS.CO.P2.HO.103 | Beams and Slab Formwork | 2114.58 | M2 | 7 | 2026-11-04 | 2026-11-11
MS.CO.P2.HO.104 | Beams and Slab Steel Fix | 2114.58 | M2 | 5 | 2026-11-12 | 2026-11-17
MS.CO.P2.HO.105 | Beams and Slab Concreting work | 2114.58 | M2 | 1 | 2026-11-18 | 2026-11-18
MS.CO.P2.HO.109 | DE shuttering for Slab | 2114.58 | M2 | 2 | 2026-12-12 | 2026-12-13
Masonry Works |  |  |  | 29 | 2026-12-14 | 2027-01-16
MS.CO.P2.HO.113 | GF - External Block Work |  |  | 14 | 2026-12-14 | 2026-12-29
MS.CO.P2.HO.115 | GF - Internal Block Work |  |  | 20 | 2026-12-24 | 2027-01-16
Mezzanine Floor |  |  |  | 70 | 2026-11-19 | 2027-02-08
Vertical Element |  |  |  | 9 | 2026-11-19 | 2026-11-29
MS.CO.P2.HO.106 | Columns & Walls Steel Fix | 92 | PCs | 5 | 2026-11-19 | 2026-11-24
MS.CO.P2.HO.107 | Columns & Walls Formwork | 92 | PCs | 5 | 2026-11-22 | 2026-11-26
MS.CO.P2.HO.108 | Columns & Walls Concreting work | 92 | PCs | 5 | 2026-11-24 | 2026-11-29
Slab |  | 2042.96 | M2 | 31 | 2026-11-26 | 2026-12-31
MS.CO.P2.HO.110 | Beams and Slab Formwork | 2042.96 | M2 | 5 | 2026-11-26 | 2026-12-01
MS.CO.P2.HO.111 | Beams and Slab Steel Fix | 2042.96 | M2 | 4 | 2026-12-02 | 2026-12-06
MS.CO.P2.HO.112 | Beams and Slab Concreting work | 2042.96 | M2 | 1 | 2026-12-07 | 2026-12-07
MS.CO.P2.HO.118 | DE shuttering for Slab | 2042.96 | M2 | 2 | 2026-12-30 | 2026-12-31
Masonry Works |  |  |  | 33 | 2027-01-02 | 2027-02-08
MS.CO.P2.HO.122 | GF - External Block Work |  |  | 14 | 2027-01-02 | 2027-01-17
MS.CO.P2.HO.124 | GF - Internal Block Work |  |  | 20 | 2027-01-17 | 2027-02-08
First Floor |  |  |  | 74 | 2026-12-08 | 2027-03-09
Vertical Element |  |  |  | 9 | 2026-12-08 | 2026-12-17
MS.CO.P2.HO.114 | Columns & Walls Steel Fix | 92 | PCs | 5 | 2026-12-08 | 2026-12-13
MS.CO.P2.HO.116 | Columns & Walls Formwork | 92 | PCs | 5 | 2026-12-10 | 2026-12-15
MS.CO.P2.HO.117 | Columns & Walls Concreting work | 92 | PCs | 5 | 2026-12-13 | 2026-12-17
Slab |  | 1915.48 | M2 | 31 | 2026-12-15 | 2027-01-19
MS.CO.P2.HO.119 | Beams and Slab Formwork | 1915.48 | M2 | 5 | 2026-12-15 | 2026-12-20
MS.CO.P2.HO.120 | Beams and Slab Steel Fix | 1915.48 | M2 | 4 | 2026-12-21 | 2026-12-24
MS.CO.P2.HO.121 | Beams and Slab Concreting work | 1915.48 | M2 | 1 | 2026-12-26 | 2026-12-26
MS.CO.P2.HO.127 | DE shuttering for Slab | 1915.48 | M2 | 2 | 2027-01-18 | 2027-01-19
Masonry Works |  |  |  | 37 | 2027-01-20 | 2027-03-09
MS.CO.P2.HO.131 | GF - External Block Work |  |  | 14 | 2027-01-20 | 2027-02-04
MS.CO.P2.HO.134 | GF - Internal Block Work |  |  | 20 | 2027-02-09 | 2027-03-09
Second Floor |  |  |  | 72 | 2026-12-27 | 2027-03-29
Vertical Element |  |  |  | 6 | 2026-12-27 | 2027-01-02
MS.CO.P2.HO.123 | Columns & Walls Steel Fix | 92 | PCs | 4 | 2026-12-27 | 2026-12-30
MS.CO.P2.HO.125 | Columns & Walls Formwork | 92 | PCs | 4 | 2026-12-28 | 2026-12-31
MS.CO.P2.HO.126 | Columns & Walls Concreting work | 92 | PCs | 4 | 2026-12-29 | 2027-01-02
Slab |  | 1915.48 | M2 | 30 | 2026-12-30 | 2027-02-02
MS.CO.P2.HO.128 | Beams and Slab Formwork | 1915.48 | M2 | 4 | 2026-12-30 | 2027-01-03
MS.CO.P2.HO.129 | Beams and Slab Steel Fix | 1915.48 | M2 | 4 | 2027-01-04 | 2027-01-07
MS.CO.P2.HO.130 | Beams and Slab Concreting work | 1915.48 | M2 | 1 | 2027-01-09 | 2027-01-09
MS.CO.P2.HO.136 | DE shuttering for Slab | 1915.48 | M2 | 2 | 2027-02-01 | 2027-02-02
Masonry Works |  |  |  | 39 | 2027-02-03 | 2027-03-29
MS.CO.P2.HO.140 | GF - External Block Work |  |  | 14 | 2027-02-03 | 2027-02-21
MS.CO.P2.HO.143 | GF - Internal Block Work |  |  | 14 | 2027-03-14 | 2027-03-29
Third Floor |  |  |  | 54 | 2027-01-10 | 2027-03-22
Vertical Element |  |  |  | 6 | 2027-01-10 | 2027-01-16
MS.CO.P2.HO.132 | Columns & Walls Steel Fix | 92 | PCs | 4 | 2027-01-10 | 2027-01-13
MS.CO.P2.HO.133 | Columns & Walls Formwork | 92 | PCs | 4 | 2027-01-11 | 2027-01-14
MS.CO.P2.HO.135 | Columns & Walls Concreting work | 92 | PCs | 4 | 2027-01-12 | 2027-01-16
Slab |  | 1915.48 | M2 | 31 | 2027-01-13 | 2027-02-18
MS.CO.P2.HO.137 | Beams and Slab Formwork | 1915.48 | M2 | 5 | 2027-01-13 | 2027-01-18
MS.CO.P2.HO.138 | Beams and Slab Steel Fix | 1915.48 | M2 | 4 | 2027-01-19 | 2027-01-23
MS.CO.P2.HO.139 | Beams and Slab Concreting work | 1915.48 | M2 | 1 | 2027-01-24 | 2027-01-24
MS.CO.P2.HO.145 | DE shuttering for Slab | 1915.48 | M2 | 2 | 2027-02-17 | 2027-02-18
Masonry Works |  |  |  | 20 | 2027-02-21 | 2027-03-22
MS.CO.P2.HO.149 | GF - External Block Work |  |  | 10 | 2027-02-21 | 2027-03-07
MS.CO.P2.HO.152 | GF - Internal Block Work |  |  | 14 | 2027-03-02 | 2027-03-22
Fourth Floor |  |  |  | 43 | 2027-01-25 | 2027-03-24
Vertical Element |  |  |  | 6 | 2027-01-25 | 2027-01-31
MS.CO.P2.HO.141 | Columns & Walls Steel Fix | 92 | PCs | 4 | 2027-01-25 | 2027-01-28
MS.CO.P2.HO.142 | Columns & Walls Formwork | 92 | PCs | 4 | 2027-01-26 | 2027-01-30
MS.CO.P2.HO.144 | Columns & Walls Concreting work | 92 | PCs | 4 | 2027-01-27 | 2027-01-31
Slab |  | 1915.48 | M2 | 28 | 2027-01-28 | 2027-03-07
MS.CO.P2.HO.146 | Beams and Slab Formwork | 1915.48 | M2 | 4 | 2027-01-28 | 2027-02-01
MS.CO.P2.HO.147 | Beams and Slab Steel Fix | 1915.48 | M2 | 3 | 2027-02-02 | 2027-02-04
MS.CO.P2.HO.148 | Beams and Slab Concreting work | 1915.48 | M2 | 1 | 2027-02-06 | 2027-02-06
MS.CO.P2.HO.154 | DE shuttering for Slab | 1915.48 | M2 | 2 | 2027-03-06 | 2027-03-07
Masonry Works |  |  |  | 12 | 2027-03-08 | 2027-03-24
MS.CO.P2.HO.158 | GF - External Block Work |  |  | 9 | 2027-03-08 | 2027-03-21
MS.CO.P2.HO.159 | GF - Internal Block Work |  |  | 9 | 2027-03-15 | 2027-03-24
Fifth Floor |  |  |  | 38 | 2027-02-07 | 2027-03-31
Vertical Element |  |  |  | 6 | 2027-02-07 | 2027-02-14
MS.CO.P2.HO.150 | Columns & Walls Steel Fix | 92 | PCs | 4 | 2027-02-07 | 2027-02-10
MS.CO.P2.HO.151 | Columns & Walls Formwork | 1915.48 | M2 | 4 | 2027-02-08 | 2027-02-11
MS.CO.P2.HO.153 | Columns & Walls Concreting work | 1915.48 | M2 | 4 | 2027-02-09 | 2027-02-14
Slab |  | 1915.48 | M2 | 26 | 2027-02-11 | 2027-03-22
MS.CO.P2.HO.155 | Beams and Slab Formwork | 1915.48 | M2 | 4 | 2027-02-11 | 2027-02-16
MS.CO.P2.HO.156 | Beams and Slab Steel Fix | 1915.48 | M2 | 3 | 2027-02-17 | 2027-02-21
MS.CO.P2.HO.157 | Beams and Slab Concreting work | 1915.48 | M2 | 1 | 2027-02-23 | 2027-02-23
MS.CO.P2.HO.160 | DE shuttering for Slab | 1915.48 | M2 | 2 | 2027-03-21 | 2027-03-22
Masonry Works |  |  |  | 8 | 2027-03-23 | 2027-03-31
MS.CO.P2.HO.161 | GF - External Block Work |  |  | 8 | 2027-03-23 | 2027-03-31
MS.CO.P2.HO.162 | GF - Internal Block Work |  |  | 8 | 2027-03-23 | 2027-03-31
RB-B |  |  |  | 123 | 2026-10-27 | 2027-03-28
Ground Floor |  |  |  | 66 | 2026-10-27 | 2027-01-11
Vertical Element |  |  |  | 9 | 2026-10-27 | 2026-11-05
MS.CO.P2.RB.100 | Columns & Walls Steel Fix | 98 | PCs | 5 | 2026-10-27 | 2026-11-01
MS.CO.P2.RB.101 | Columns & Walls Formwork | 98 | PCs | 5 | 2026-10-29 | 2026-11-03
MS.CO.P2.RB.102 | Columns & Walls Concreting work | 98 | PCs | 5 | 2026-11-01 | 2026-11-05
Slab |  | 2452.32 | M2 | 31 | 2026-11-03 | 2026-12-08
MS.CO.P2.RB.103 | Beams and Slab Formwork | 2452.32 | M2 | 5 | 2026-11-03 | 2026-11-08
MS.CO.P2.RB.104 | Beams and Slab Steel Fix | 2452.32 | M2 | 4 | 2026-11-09 | 2026-11-12
MS.CO.P2.RB.105 | Beams and Slab Concreting work | 2452.32 | M2 | 1 | 2026-11-14 | 2026-11-14
MS.CO.P2.RB.109 | DE shuttering for Slab | 2452.32 | M2 | 2 | 2026-12-07 | 2026-12-08
Masonry Works |  |  |  | 29 | 2026-12-09 | 2027-01-11
MS.CO.P2.RB.114 | GF - External Block Work |  |  | 20 | 2026-12-09 | 2026-12-31
MS.CO.P2.RB.117 | GF - Internal Block Work |  |  | 20 | 2026-12-20 | 2027-01-11
First Floor |  |  |  | 64 | 2026-11-15 | 2027-01-27
Vertical Element |  |  |  | 11 | 2026-11-15 | 2026-11-26
MS.CO.P2.RB.106 | Columns & Walls Steel Fix | 98 | PCs | 5 | 2026-11-15 | 2026-11-19
MS.CO.P2.RB.107 | Columns & Walls Formwork | 98 | PCs | 5 | 2026-11-18 | 2026-11-23
MS.CO.P2.RB.108 | Columns & Walls Concreting work | 98 | PCs | 5 | 2026-11-22 | 2026-11-26
Slab |  | 1264 | M2 | 31 | 2026-11-24 | 2026-12-29
MS.CO.P2.RB.110 | Beams and Slab Formwork | 1264 | M2 | 5 | 2026-11-24 | 2026-11-29
MS.CO.P2.RB.111 | Beams and Slab Steel Fix | 1264 | M2 | 4 | 2026-11-30 | 2026-12-03
MS.CO.P2.RB.112 | Beams and Slab Concreting work | 1264 | M2 | 1 | 2026-12-05 | 2026-12-05
MS.CO.P2.RB.118 | DE shuttering for Slab | 1264 | M2 | 2 | 2026-12-28 | 2026-12-29
Masonry Works |  |  |  | 25 | 2026-12-30 | 2027-01-27
MS.CO.P2.RB.122 | GF - External Block Work |  |  | 14 | 2026-12-30 | 2027-01-14
MS.CO.P2.RB.125 | GF - Internal Block Work |  |  | 14 | 2027-01-12 | 2027-01-27
Second Floor |  |  |  | 60 | 2026-12-06 | 2027-02-14
Vertical Element |  |  |  | 8 | 2026-12-06 | 2026-12-14
MS.CO.P2.RB.113 | Columns & Walls Steel Fix | 98 | PCs | 4 | 2026-12-06 | 2026-12-09
MS.CO.P2.RB.115 | Columns & Walls Formwork | 98 | PCs | 4 | 2026-12-08 | 2026-12-12
MS.CO.P2.RB.116 | Columns & Walls Concreting work | 98 | PCs | 4 | 2026-12-10 | 2026-12-14
Slab |  | 2079.1 | M2 | 31 | 2026-12-12 | 2027-01-16
MS.CO.P2.RB.119 | Beams and Slab Formwork | 2079.1 | M2 | 5 | 2026-12-12 | 2026-12-16
MS.CO.P2.RB.120 | Beams and Slab Steel Fix | 2079.1 | M2 | 4 | 2026-12-17 | 2026-12-21
MS.CO.P2.RB.121 | Beams and Slab Concreting work | 2079.1 | M2 | 1 | 2026-12-22 | 2026-12-22
MS.CO.P2.RB.127 | DE shuttering for Slab | 2079.1 | M2 | 2 | 2027-01-14 | 2027-01-16
Masonry Works |  |  |  | 24 | 2027-01-17 | 2027-02-14
MS.CO.P2.RB.131 | GF - External Block Work |  |  | 14 | 2027-01-17 | 2027-02-01
MS.CO.P2.RB.134 | GF - Internal Block Work |  |  | 14 | 2027-01-28 | 2027-02-14
Third Floor |  |  |  | 60 | 2026-12-23 | 2027-03-08
Vertical Element |  |  |  | 8 | 2026-12-23 | 2026-12-31
MS.CO.P2.RB.123 | Columns & Walls Steel Fix | 98 | PCs | 4 | 2026-12-23 | 2026-12-27
MS.CO.P2.RB.124 | Columns & Walls Formwork | 98 | PCs | 4 | 2026-12-26 | 2026-12-29
MS.CO.P2.RB.126 | Columns & Walls Concreting work | 98 | PCs | 4 | 2026-12-28 | 2026-12-31
Slab |  | 2079.1 | M2 | 31 | 2026-12-30 | 2027-02-03
MS.CO.P2.RB.128 | Beams and Slab Formwork | 2079.1 | M2 | 5 | 2026-12-30 | 2027-01-04
MS.CO.P2.RB.129 | Beams and Slab Steel Fix | 2079.1 | M2 | 4 | 2027-01-05 | 2027-01-09
MS.CO.P2.RB.130 | Beams and Slab Concreting work | 2079.1 | M2 | 1 | 2027-01-10 | 2027-01-10
MS.CO.P2.RB.136 | DE shuttering for Slab | 2079.1 | M2 | 2 | 2027-02-02 | 2027-02-03
Masonry Works |  |  |  | 23 | 2027-02-04 | 2027-03-08
MS.CO.P2.RB.140 | GF - External Block Work |  |  | 14 | 2027-02-04 | 2027-02-23
MS.CO.P2.RB.143 | GF - Internal Block Work |  |  | 14 | 2027-02-16 | 2027-03-08
Fourth Floor |  |  |  | 58 | 2027-01-11 | 2027-03-28
Vertical Element |  |  |  | 8 | 2027-01-11 | 2027-01-19
MS.CO.P2.RB.132 | Columns & Walls Steel Fix | 98 | PCs | 4 | 2027-01-11 | 2027-01-14
MS.CO.P2.RB.133 | Columns & Walls Formwork | 98 | PCs | 4 | 2027-01-13 | 2027-01-17
MS.CO.P2.RB.135 | Columns & Walls Concreting work | 98 | PCs | 4 | 2027-01-16 | 2027-01-19
Slab |  | 2079.1 | M2 | 30 | 2027-01-17 | 2027-02-23
MS.CO.P2.RB.137 | Beams and Slab Formwork | 2079.1 | M2 | 5 | 2027-01-17 | 2027-01-21
MS.CO.P2.RB.138 | Beams and Slab Steel Fix | 2079.1 | M2 | 4 | 2027-01-23 | 2027-01-26
MS.CO.P2.RB.139 | Beams and Slab Concreting work | 2079.1 | M2 | 1 | 2027-01-27 | 2027-01-27
MS.CO.P2.RB.145 | DE shuttering for Slab | 2079.1 | M2 | 2 | 2027-02-22 | 2027-02-23
Masonry Works |  |  |  | 23 | 2027-02-24 | 2027-03-28
MS.CO.P2.RB.149 | GF - External Block Work |  |  | 14 | 2027-02-24 | 2027-03-17
MS.CO.P2.RB.150 | GF - Internal Block Work |  |  | 14 | 2027-03-09 | 2027-03-28
Fifth Floor |  |  |  | 41 | 2027-01-28 | 2027-03-25
Vertical Element |  |  |  | 6 | 2027-01-28 | 2027-02-03
MS.CO.P2.RB.141 | Columns & Walls Steel Fix | 98 | PCs | 4 | 2027-01-28 | 2027-02-01
MS.CO.P2.RB.142 | Columns & Walls Formwork | 98 | PCs | 4 | 2027-01-30 | 2027-02-02
MS.CO.P2.RB.144 | Columns & Walls Concreting work | 98 | PCs | 4 | 2027-01-31 | 2027-02-03
Slab |  | 2079.1 | M2 | 24 | 2027-02-04 | 2027-03-09
MS.CO.P2.RB.146 | Beams and Slab Formwork | 2079.1 | M2 | 5 | 2027-02-04 | 2027-02-09
MS.CO.P2.RB.147 | Beams and Slab Steel Fix | 2079.1 | M2 | 4 | 2027-02-10 | 2027-02-15
MS.CO.P2.RB.148 | Beams and Slab Concreting work | 2079.1 | M2 | 1 | 2027-02-16 | 2027-02-16
MS.CO.P2.RB.151 | DE shuttering for Slab | 2079.1 | M2 | 2 | 2027-03-08 | 2027-03-09
Masonry Works |  |  |  | 11 | 2027-03-14 | 2027-03-25
MS.CO.P2.RB.152 | GF - External Block Work |  |  | 8 | 2027-03-14 | 2027-03-22
MS.CO.P2.RB.153 | GF - Internal Block Work |  |  | 8 | 2027-03-17 | 2027-03-25
FB-C |  |  |  | 114 | 2026-11-09 | 2027-03-30
Ground Floor |  |  |  | 66 | 2026-11-09 | 2027-01-24
Vertical Element |  |  |  | 9 | 2026-11-09 | 2026-11-18
MS.CO.P2.FBC.100 | Columns & Walls Steel Fix | 57 | PCS | 5 | 2026-11-09 | 2026-11-14
MS.CO.P2.FBC.101 | Columns & Walls Formwork | 57 | PCS | 5 | 2026-11-11 | 2026-11-16
MS.CO.P2.FBC.102 | Columns & Walls Concreting work | 57 | PCS | 5 | 2026-11-14 | 2026-11-18
Slab |  | 2516.7 | M2 | 31 | 2026-11-16 | 2026-12-21
MS.CO.P2.FBC.103 | Beams and Slab Formwork | 2516.7 | M2 | 5 | 2026-11-16 | 2026-11-21
MS.CO.P2.FBC.104 | Beams and Slab Steel Fix | 2516.7 | M2 | 4 | 2026-11-22 | 2026-11-25
MS.CO.P2.FBC.105 | Beams and Slab Concreting work | 2516.7 | M2 | 1 | 2026-11-26 | 2026-11-26
MS.CO.P2.FBC.109 | DE shuttering for Slab | 2516.7 | M2 | 2 | 2026-12-20 | 2026-12-21
Masonry Works |  |  |  | 29 | 2026-12-22 | 2027-01-24
MS.CO.P2.FBC.113 | External Block Work |  |  | 14 | 2026-12-22 | 2027-01-06
MS.CO.P2.FBC.116 | Internal Block Work |  |  | 20 | 2027-01-02 | 2027-01-24
First Floor |  |  |  | 70 | 2026-11-28 | 2027-02-17
Vertical Element |  |  |  | 8 | 2026-11-28 | 2026-12-06
MS.CO.P2.FBC.106 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-11-28 | 2026-12-01
MS.CO.P2.FBC.107 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-11-30 | 2026-12-03
MS.CO.P2.FBC.108 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-12-02 | 2026-12-06
Slab |  | 2242.27 | M2 | 29 | 2026-12-05 | 2027-01-06
MS.CO.P2.FBC.110 | Beams and Slab Formwork | 2242.27 | M2 | 4 | 2026-12-05 | 2026-12-08
MS.CO.P2.FBC.111 | Beams and Slab Steel Fix | 2242.27 | M2 | 3 | 2026-12-09 | 2026-12-12
MS.CO.P2.FBC.112 | Beams and Slab Concreting work | 2242.27 | M2 | 1 | 2026-12-13 | 2026-12-13
MS.CO.P2.FBC.118 | DE shuttering for Slab | 2242.27 | M2 | 2 | 2027-01-05 | 2027-01-06
Masonry Works |  |  |  | 35 | 2027-01-07 | 2027-02-17
MS.CO.P2.FBC.122 | External Block Work |  |  | 14 | 2027-01-07 | 2027-01-23
MS.CO.P2.FBC.125 | Internal Block Work |  |  | 20 | 2027-01-25 | 2027-02-17
Second Floor |  |  |  | 70 | 2026-12-14 | 2027-03-14
Vertical Element |  |  |  | 8 | 2026-12-14 | 2026-12-22
MS.CO.P2.FBC.114 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-12-14 | 2026-12-17
MS.CO.P2.FBC.115 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-12-16 | 2026-12-20
MS.CO.P2.FBC.117 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-12-19 | 2026-12-22
Slab |  | 2205.2 | M2 | 29 | 2026-12-21 | 2027-01-23
MS.CO.P2.FBC.119 | Beams and Slab Formwork | 2205.2 | M2 | 4 | 2026-12-21 | 2026-12-24
MS.CO.P2.FBC.120 | Beams and Slab Steel Fix | 2205.2 | M2 | 3 | 2026-12-26 | 2026-12-28
MS.CO.P2.FBC.121 | Beams and Slab Concreting work | 2205.2 | M2 | 1 | 2026-12-29 | 2026-12-29
MS.CO.P2.FBC.127 | DE shuttering for Slab | 2205.2 | M2 | 2 | 2027-01-21 | 2027-01-23
Masonry Works |  |  |  | 35 | 2027-01-24 | 2027-03-14
MS.CO.P2.FBC.131 | External Block Work |  |  | 12 | 2027-01-24 | 2027-02-06
MS.CO.P2.FBC.134 | Internal Block Work |  |  | 14 | 2027-02-18 | 2027-03-14
Third Floor |  |  |  | 68 | 2026-12-30 | 2027-03-28
Vertical Element |  |  |  | 6 | 2026-12-30 | 2027-01-05
MS.CO.P2.FBC.123 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-12-30 | 2027-01-03
MS.CO.P2.FBC.124 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-12-31 | 2027-01-04
MS.CO.P2.FBC.126 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-01-02 | 2027-01-05
Slab |  | 2205.2 | M2 | 31 | 2027-01-03 | 2027-02-07
MS.CO.P2.FBC.128 | Beams and Slab Formwork | 2205.2 | M2 | 4 | 2027-01-03 | 2027-01-06
MS.CO.P2.FBC.129 | Beams and Slab Steel Fix | 2205.2 | M2 | 3 | 2027-01-10 | 2027-01-12
MS.CO.P2.FBC.130 | Beams and Slab Concreting work | 2205.2 | M2 | 1 | 2027-01-13 | 2027-01-13
MS.CO.P2.FBC.136 | DE shuttering for Slab | 2205.2 | M2 | 2 | 2027-02-06 | 2027-02-07
Masonry Works |  |  |  | 34 | 2027-02-08 | 2027-03-28
MS.CO.P2.FBC.140 | External Block Work |  |  | 12 | 2027-02-08 | 2027-02-24
MS.CO.P2.FBC.143 | Internal Block Work |  |  | 12 | 2027-03-15 | 2027-03-28
Fourth Floor |  |  |  | 56 | 2027-01-14 | 2027-03-29
Vertical Element |  |  |  | 6 | 2027-01-14 | 2027-01-20
MS.CO.P2.FBC.132 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2027-01-14 | 2027-01-18
MS.CO.P2.FBC.133 | Columns & Walls Formwork | 57 | PCS | 4 | 2027-01-16 | 2027-01-19
MS.CO.P2.FBC.135 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-01-17 | 2027-01-20
Slab |  | 2205.2 | M2 | 28 | 2027-01-18 | 2027-02-21
MS.CO.P2.FBC.137 | Beams and Slab Formwork | 2205.2 | M2 | 4 | 2027-01-18 | 2027-01-21
MS.CO.P2.FBC.138 | Beams and Slab Steel Fix | 2205.2 | M2 | 3 | 2027-01-23 | 2027-01-25
MS.CO.P2.FBC.139 | Beams and Slab Concreting work | 2205.2 | M2 | 1 | 2027-01-26 | 2027-01-26
MS.CO.P2.FBC.145 | DE shuttering for Slab | 2205.2 | M2 | 2 | 2027-02-20 | 2027-02-21
Masonry Works |  |  |  | 23 | 2027-02-25 | 2027-03-29
MS.CO.P2.FBC.149 | External Block Work |  |  | 14 | 2027-02-25 | 2027-03-18
MS.CO.P2.FBC.152 | Internal Block Work |  |  | 14 | 2027-03-14 | 2027-03-29
Fifth Floor |  |  |  | 46 | 2027-01-27 | 2027-03-30
Vertical Element |  |  |  | 8 | 2027-01-27 | 2027-02-04
MS.CO.P2.FBC.141 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2027-01-27 | 2027-01-31
MS.CO.P2.FBC.142 | Columns & Walls Formwork | 57 | PCS | 4 | 2027-01-30 | 2027-02-02
MS.CO.P2.FBC.144 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-02-01 | 2027-02-04
Slab |  | 2238 | M2 | 29 | 2027-02-03 | 2027-03-17
MS.CO.P2.FBC.146 | Beams and Slab Formwork | 2238 | M2 | 4 | 2027-02-03 | 2027-02-07
MS.CO.P2.FBC.147 | Beams and Slab Steel Fix | 2238 | M2 | 3 | 2027-02-08 | 2027-02-10
MS.CO.P2.FBC.148 | Beams and Slab Concreting work | 2238 | M2 | 1 | 2027-02-11 | 2027-02-11
MS.CO.P2.FBC.155 | DE shuttering for Slab | 2238 | M2 | 2 | 2027-03-16 | 2027-03-17
Masonry Works |  |  |  | 10 | 2027-03-20 | 2027-03-30
MS.CO.P2.FBC.158 | External Block Work |  |  | 8 | 2027-03-20 | 2027-03-28
MS.CO.P2.FBC.160 | Internal Block Work |  |  | 8 | 2027-03-22 | 2027-03-30
Penthouse Floor |  |  |  | 32 | 2027-02-14 | 2027-03-30
Vertical Element |  |  |  | 4 | 2027-02-14 | 2027-02-17
MS.CO.P2.FBC.150 | Columns & Walls Steel Fix | 57 | PCS | 2 | 2027-02-14 | 2027-02-15
MS.CO.P2.FBC.151 | Columns & Walls Formwork | 57 | PCS | 2 | 2027-02-15 | 2027-02-16
MS.CO.P2.FBC.153 | Columns & Walls Concreting work | 57 | PCS | 1 | 2027-02-17 | 2027-02-17
Slab |  | 558.1 | M2 | 22 | 2027-02-18 | 2027-03-23
MS.CO.P2.FBC.154 | Beams and Slab Formwork | 558.1 | M2 | 4 | 2027-02-18 | 2027-02-24
MS.CO.P2.FBC.156 | Beams and Slab Steel Fix | 558.1 | M2 | 3 | 2027-02-25 | 2027-03-01
MS.CO.P2.FBC.157 | Beams and Slab Concreting work | 558.1 | M2 | 1 | 2027-03-02 | 2027-03-02
MS.CO.P2.FBC.159 | DE shuttering for Slab | 558.1 | M2 | 2 | 2027-03-22 | 2027-03-23
Masonry Works |  |  |  | 6 | 2027-03-24 | 2027-03-30
MS.CO.P2.FBC.161 | External Block Work |  |  | 6 | 2027-03-24 | 2027-03-30
MS.CO.P2.FBC.162 | Internal Block Work |  |  | 6 | 2027-03-24 | 2027-03-30
FB-R |  |  |  | 103 | 2026-11-22 | 2027-03-30
Ground Floor |  |  |  | 71 | 2026-11-22 | 2027-02-11
Vertical Element |  |  |  | 8 | 2026-11-22 | 2026-11-30
MS.CO.P2.FBR.100 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-11-22 | 2026-11-25
MS.CO.P2.FBR.101 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-11-24 | 2026-11-28
MS.CO.P2.FBR.102 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-11-26 | 2026-11-30
Slab |  | 1784.54 | M2 | 37 | 2026-11-28 | 2027-01-09
MS.CO.P2.FBR.103 | Beams and Slab Formwork | 1784.54 | M2 | 5 | 2026-11-28 | 2026-12-02
MS.CO.P2.FBR.104 | Beams and Slab Steel Fix | 1784.54 | M2 | 4 | 2026-12-03 | 2026-12-07
MS.CO.P2.FBR.105 | Beams and Slab Concreting work | 1784.54 | M2 | 7 | 2026-12-08 | 2026-12-15
MS.CO.P2.FBR.109 | DE shuttering for Slab | 1784.54 | M2 | 2 | 2027-01-07 | 2027-01-09
Masonry Works |  |  |  | 29 | 2027-01-10 | 2027-02-11
MS.CO.P2.FBR.114 | External Block Work |  |  | 14 | 2027-01-10 | 2027-01-25
MS.CO.P2.FBR.118 | Internal Block Work |  |  | 20 | 2027-01-20 | 2027-02-11
First Floor |  |  |  | 62 | 2026-12-16 | 2027-03-02
Vertical Element |  |  |  | 8 | 2026-12-16 | 2026-12-24
MS.CO.P2.FBR.106 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2026-12-16 | 2026-12-20
MS.CO.P2.FBR.107 | Columns & Walls Formwork | 57 | PCS | 4 | 2026-12-19 | 2026-12-22
MS.CO.P2.FBR.108 | Columns & Walls Concreting work | 57 | PCS | 4 | 2026-12-21 | 2026-12-24
Slab |  | 1514.91 | M2 | 29 | 2026-12-23 | 2027-01-25
MS.CO.P2.FBR.110 | Beams and Slab Formwork | 1514.91 | M2 | 4 | 2026-12-23 | 2026-12-27
MS.CO.P2.FBR.111 | Beams and Slab Steel Fix | 1514.91 | M2 | 3 | 2026-12-28 | 2026-12-30
MS.CO.P2.FBR.112 | Beams and Slab Concreting work | 1514.91 | M2 | 1 | 2026-12-31 | 2026-12-31
MS.CO.P2.FBR.117 | DE shuttering for Slab | 1514.91 | M2 | 2 | 2027-01-24 | 2027-01-25
Masonry Works |  |  |  | 27 | 2027-01-26 | 2027-03-02
MS.CO.P2.FBR.123 | External Block Work |  |  | 12 | 2027-01-26 | 2027-02-08
MS.CO.P2.FBR.126 | Internal Block Work |  |  | 12 | 2027-02-14 | 2027-03-02
Second Floor |  |  |  | 62 | 2027-01-02 | 2027-03-23
Vertical Element |  |  |  | 8 | 2027-01-02 | 2027-01-10
MS.CO.P2.FBR.113 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2027-01-02 | 2027-01-05
MS.CO.P2.FBR.115 | Columns & Walls Formwork | 57 | PCS | 4 | 2027-01-04 | 2027-01-07
MS.CO.P2.FBR.116 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-01-06 | 2027-01-10
Slab |  | 1478.54 | M2 | 31 | 2027-01-07 | 2027-02-11
MS.CO.P2.FBR.119 | Beams and Slab Formwork | 1478.54 | M2 | 5 | 2027-01-07 | 2027-01-12
MS.CO.P2.FBR.120 | Beams and Slab Steel Fix | 1478.54 | M2 | 4 | 2027-01-13 | 2027-01-17
MS.CO.P2.FBR.121 | Beams and Slab Concreting work | 1478.54 | M2 | 1 | 2027-01-18 | 2027-01-18
MS.CO.P2.FBR.127 | DE shuttering for Slab | 1478.54 | M2 | 2 | 2027-02-10 | 2027-02-11
Masonry Works |  |  |  | 26 | 2027-02-14 | 2027-03-23
MS.CO.P2.FBR.132 | External Block Work |  |  | 14 | 2027-02-14 | 2027-03-04
MS.CO.P2.FBR.136 | Internal Block Work |  |  | 14 | 2027-03-03 | 2027-03-23
Third Floor |  |  |  | 47 | 2027-01-19 | 2027-03-23
Vertical Element |  |  |  | 8 | 2027-01-19 | 2027-01-27
MS.CO.P2.FBR.122 | Columns & Walls Steel Fix | 57 | PCS | 4 | 2027-01-19 | 2027-01-23
MS.CO.P2.FBR.124 | Columns & Walls Formwork | 57 | PCS | 4 | 2027-01-21 | 2027-01-25
MS.CO.P2.FBR.125 | Columns & Walls Concreting work | 57 | PCS | 4 | 2027-01-24 | 2027-01-27
Slab |  | 1510.29 | M2 | 24 | 2027-01-26 | 2027-02-27
MS.CO.P2.FBR.128 | Beams and Slab Formwork | 1510.29 | M2 | 4 | 2027-01-26 | 2027-01-30
MS.CO.P2.FBR.129 | Beams and Slab Steel Fix | 1510.29 | M2 | 3 | 2027-01-31 | 2027-02-02
MS.CO.P2.FBR.130 | Beams and Slab Concreting work | 1510.29 | M2 | 1 | 2027-02-03 | 2027-02-03
MS.CO.P2.FBR.137 | DE shuttering for Slab | 1510.29 | M2 | 2 | 2027-02-25 | 2027-02-27
Masonry Works |  |  |  | 12 | 2027-03-07 | 2027-03-23
MS.CO.P2.FBR.140 | External Block Work |  |  | 10 | 2027-03-07 | 2027-03-21
MS.CO.P2.FBR.142 | Internal Block Work |  |  | 10 | 2027-03-09 | 2027-03-23
Penthouse Floor |  |  |  | 39 | 2027-02-04 | 2027-03-30
Vertical Element |  |  |  | 5 | 2027-02-04 | 2027-02-09
MS.CO.P2.FBR.131 | Columns & Walls Steel Fix | 57 | PCS | 3 | 2027-02-04 | 2027-02-07
MS.CO.P2.FBR.133 | Columns & Walls Formwork | 57 | PCS | 3 | 2027-02-06 | 2027-02-08
MS.CO.P2.FBR.134 | Columns & Walls Concreting work | 57 | PCS | 3 | 2027-02-07 | 2027-02-09
Slab |  | 398.11 | M2 | 21 | 2027-02-08 | 2027-03-10
MS.CO.P2.FBR.135 | Beams and Slab Formwork | 398.11 | M2 | 4 | 2027-02-08 | 2027-02-11
MS.CO.P2.FBR.138 | Beams and Slab Steel Fix | 398.11 | M2 | 3 | 2027-02-14 | 2027-02-16
MS.CO.P2.FBR.139 | Beams and Slab Concreting work | 398.11 | M2 | 1 | 2027-02-17 | 2027-02-17
MS.CO.P2.FBR.141 | DE shuttering for Slab | 398.11 | M2 | 2 | 2027-03-09 | 2027-03-10
Masonry Works |  |  |  | 8 | 2027-03-22 | 2027-03-30
MS.CO.P2.FBR.143 | External Block Work |  |  | 8 | 2027-03-22 | 2027-03-30
MS.CO.P2.FBR.144 | Internal Block Work |  |  | 8 | 2027-03-22 | 2027-03-30
External Work |  |  |  | 19 | 2027-02-04 | 2027-03-02
MS.CO.P2.ALL.144 | Special construction works planter, cross over ,water features ,canal |  |  | 19 | 2027-02-04 | 2027-03-02
Con.Phase (3) |  |  |  | 298 | 05-Apr-26 A | 2027-03-31
Sub-structure Works |  |  |  | 290 | 05-Apr-26 A | 2027-03-22
Foundation |  |  |  | 212 | 05-Apr-26 A | 2026-12-12
Part 1 |  |  |  | 43 | 19-Apr-26 A | 2026-06-16
Raft Foundation Works |  | 2696 | M2 | 43 | 19-Apr-26 A | 2026-06-16
MS.CO.P3(1).FO.110 | Formwork for Foundations | 2696 | M2 | 6 | 19-Apr-26 A | 2026-06-13
MS.CO.P3(1).FO.117 | Foundations Concrete Pouring | 2696 | M2 | 1 | 19-May-26 A | 2026-06-16
Part 2 |  |  |  | 30 | 20-Apr-26 A | 2026-06-17
Raft Foundation Works |  | 2696 | M2 | 30 | 20-Apr-26 A | 2026-06-17
MS.CO.P3(1).FO.108 | Formwork for Foundations | 2696 | M2 | 6 | 20-Apr-26 A | 2026-06-17
MS.CO.P3(1).FO.115 | Foundations Concrete Pouring | 2696 | M2 | 1 | 20-Jun-26 A | 2026-06-11
Part 3 |  |  |  | 44 | 05-Apr-26 A | 2026-06-15
Raft Foundation Works |  | 2696 | M2 | 44 | 05-Apr-26 A | 2026-06-15
MS.CO.P3(1).FO.116 | Formwork for Foundations | 2696 | M2 | 7 | 05-Apr-26 A | 2026-06-14
MS.CO.P3(1).FO.118 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 2696 | M2 | 7 | 12-Apr-26 A | 2026-06-15
MS.CO.P3(1).FO.120 | Foundations Concrete Pouring | 2696 | M2 | 3 | 20-May-26 A | 2026-06-14
Part 4 |  |  |  | 56 | 20-Apr-26 A | 2026-06-27
Raft Foundation Works |  | 2696 | M2 | 56 | 20-Apr-26 A | 2026-06-27
MS.CO.P3(2).FO.118 | Rebars for 1st layer for Foundation | 2696 | M2 | 10 | 20-Apr-26 A | 2026-06-18
MS.CO.P3(2).FO.124 | Installation for Mechanical and Electrical Embeds | 2696 | M2 | 6 | 2026-06-16 | 2026-06-22
MS.CO.P3(2).FO.126 | Formwork for Foundations | 2696 | M2 | 6 | 2026-06-17 | 2026-06-23
MS.CO.P3(2).FO.128 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 2696 | M2 | 6 | 2026-06-20 | 2026-06-25
MS.CO.P3(2).FO.129 | Foundations Concrete Pouring | 2696 | M2 | 1 | 2026-06-27 | 2026-06-27
Part 5 |  |  |  | 41 | 2026-09-01 | 2026-10-19
Excavation, Blinding & Waterproofing Works |  | 1055 | M2 | 27 | 2026-09-01 | 2026-10-03
MS.CO.P3(2).FO.139 | Excavation for drop Panels and Trenches | 1055 | M2 | 10 | 2026-09-01 | 2026-09-12
MS.CO.P1.FO.520 | Earthing and Lightning Protection System | 1055 | M2 | 2 | 2026-09-13 | 2026-09-14
MS.CO.P3(2).FO.149 | Blinding concrete for lower Part of Foundation | 1055 | M2 | 4 | 2026-09-15 | 2026-09-19
MS.CO.P3(2).FO.159 | Block work for Drop Panels | 1055 | M2 | 1 | 2026-09-20 | 2026-09-20
MS.CO.P3(2).FO.169 | Blinding concrete for Upper Part | 1055 | M2 | 2 | 2026-09-21 | 2026-09-22
MS.CO.P3(2).FO.179 | Water Proofing Membrane under Raft Foundation | 1055 | M2 | 8 | 2026-09-24 | 2026-10-03
Raft Foundation Works |  | 2696 | M2 | 14 | 2026-10-04 | 2026-10-19
MS.CO.P3(2).FO.104 | Rebars for 1st layer for Foundation | 2696 | M2 | 8 | 2026-10-04 | 2026-10-12
MS.CO.P3(2).FO.107 | Installation for Mechanical and Electrical Embeds | 2696 | M2 | 4 | 2026-10-11 | 2026-10-14
MS.CO.P3(2).FO.109 | Formwork for Foundations | 2696 | M2 | 5 | 2026-10-12 | 2026-10-17
MS.CO.P3(2).FO.112 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 2696 | M2 | 5 | 2026-10-13 | 2026-10-18
MS.CO.P3(2).FO.119 | Foundations Concrete Pouring | 2696 | M2 | 1 | 2026-10-19 | 2026-10-19
Part 6 |  |  |  | 39 | 2026-10-25 | 2026-12-08
Excavation, Blinding & Waterproofing Works |  | 1055 | M2 | 25 | 2026-10-25 | 2026-11-22
MS.CO.P3(2).FO.189 | Excavation for drop Panels and Trenches | 1055 | M2 | 10 | 2026-10-25 | 2026-11-04
MS.CO.P1.FO.560 | Earthing and Lightning Protection System | 1055 | M2 | 2 | 2026-11-05 | 2026-11-07
MS.CO.P3(2).FO.199 | Blinding concrete for lower Part of Foundation | 1055 | M2 | 3 | 2026-11-08 | 2026-11-10
MS.CO.P3(2).FO.209 | Block work for Drop Panels | 1055 | M2 | 2 | 2026-11-11 | 2026-11-12
MS.CO.P3(2).FO.219 | Blinding concrete for Upper Part | 1055 | M2 | 2 | 2026-11-14 | 2026-11-15
MS.CO.P3(2).FO.229 | Water Proofing Membrane under Raft Foundation | 1055 | M2 | 6 | 2026-11-16 | 2026-11-22
Raft Foundation Works |  | 2696 | M2 | 14 | 2026-11-23 | 2026-12-08
MS.CO.P3(2).FO.105 | Rebars for 1st layer for Foundation | 2696 | M2 | 8 | 2026-11-23 | 2026-12-01
MS.CO.P3(2).FO.110 | Installation for Mechanical and Electrical Embeds | 2696 | M2 | 5 | 2026-11-29 | 2026-12-03
MS.CO.P3(2).FO.113 | Formwork for Foundations | 2696 | M2 | 5 | 2026-11-30 | 2026-12-05
MS.CO.P3(2).FO.115 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 2696 | M2 | 5 | 2026-12-02 | 2026-12-07
MS.CO.P3(2).FO.122 | Foundations Concrete Pouring | 2696 | M2 | 1 | 2026-12-08 | 2026-12-08
Part 7 |  |  |  | 32 | 2026-11-05 | 2026-12-12
Excavation, Blinding & Waterproofing Works |  | 1055 | M2 | 18 | 2026-11-05 | 2026-11-25
MS.CO.P3(2).FO.239 | Excavation for drop Panels and Trenches | 1055 | M2 | 10 | 2026-11-05 | 2026-11-16
MS.CO.P1.FO.570 | Earthing and Lightning Protection System | 1055 | M2 | 2 | 2026-11-05 | 2026-11-07
MS.CO.P3(2).FO.249 | Blinding concrete for lower Part of Foundation | 1055 | M2 | 3 | 2026-11-16 | 2026-11-18
MS.CO.P3(2).FO.259 | Block work for Drop Panels | 1055 | M2 | 3 | 2026-11-17 | 2026-11-19
MS.CO.P3(2).FO.269 | Blinding concrete for Upper Part | 1055 | M2 | 3 | 2026-11-18 | 2026-11-21
MS.CO.P3(2).FO.279 | Water Proofing Membrane under Raft Foundation | 1055 | M2 | 6 | 2026-11-19 | 2026-11-25
Raft Foundation Works |  | 2696 | M2 | 14 | 2026-11-26 | 2026-12-12
MS.CO.P3(2).FO.108 | Rebars for 1st layer for Foundation | 2696 | M2 | 6 | 2026-11-26 | 2026-12-02
MS.CO.P3(2).FO.114 | Installation for Mechanical and Electrical Embeds | 2696 | M2 | 4 | 2026-12-02 | 2026-12-06
MS.CO.P3(2).FO.116 | Formwork for Foundations | 2696 | M2 | 5 | 2026-12-03 | 2026-12-08
MS.CO.P3(2).FO.120 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 2696 | M2 | 5 | 2026-12-06 | 2026-12-10
MS.CO.P3(2).FO.125 | Foundations Concrete Pouring | 2696 | M2 | 1 | 2026-12-12 | 2026-12-12
Basement 2 |  |  |  | 225 | 2026-06-17 | 2027-03-16
Vertical Element |  |  |  | 167 | 2026-06-17 | 2026-12-29
Part 1 |  |  |  | 30 | 2026-06-17 | 2026-07-21
MS.CO.P3(1).B2.200 | B2 - Walls Steel Fix | 432 | m2 | 7 | 2026-06-17 | 2026-06-24
MS.CO.P3(1).B2.203 | B2 - Walls Formwork | 432 | m2 | 7 | 2026-06-22 | 2026-06-29
MS.CO.P3(1).B2.207 | B2 - Walls Concreting work | 432 | m2 | 7 | 2026-06-27 | 2026-07-04
MS.CO.P3(1).B2.100 | B2 - Columns Steel Fix | 53 |  | 12 | 2026-06-29 | 2026-07-12
MS.CO.P3(1).B2.103 | B2 - Columns Formwork |  |  | 12 | 2026-07-04 | 2026-07-16
MS.CO.P3(1).B2.107 | B2 - Columns Concreting work |  |  | 12 | 2026-07-08 | 2026-07-21
Part 2 |  |  |  | 16 | 2026-06-29 | 2026-07-16
MS.CO.P3(1).B2.101 | B2 - Columns Steel Fix | 432 | PCS | 7 | 2026-06-29 | 2026-07-06
MS.CO.P3(1).B2.201 | B2 - Walls Steel Fix | 53 | m2 | 7 | 2026-06-29 | 2026-07-06
MS.CO.P3(1).B2.104 | B2 - Columns Formwork | 432 | PCS | 7 | 2026-07-04 | 2026-07-11
MS.CO.P3(1).B2.204 | B2 - Walls Formwork | 53 | m2 | 7 | 2026-07-05 | 2026-07-12
MS.CO.P3(1).B2.108 | B2 - Columns Concreting work | 432 | PCS | 7 | 2026-07-08 | 2026-07-15
MS.CO.P3(1).B2.208 | B2 - Walls Concreting work | 53 | m2 | 7 | 2026-07-09 | 2026-07-16
Part 3 |  |  |  | 27 | 2026-06-29 | 2026-07-29
MS.CO.P3(1).B2.102 | B2 - Columns Steel Fix | 432 | PCS | 12 | 2026-06-29 | 2026-07-12
MS.CO.P3(1).B2.202 | B2 - Walls Steel Fix | 53 | m2 | 12 | 2026-06-29 | 2026-07-12
MS.CO.P3(1).B2.105 | B2 - Columns Formwork | 432 | PCS | 12 | 2026-07-04 | 2026-07-16
MS.CO.P3(1).B2.109 | B2 - Columns Concreting work | 53 | m2 | 12 | 2026-07-08 | 2026-07-21
MS.CO.P3(1).B2.205 | B2 - Walls Formwork | 432 | PCS | 7 | 2026-07-18 | 2026-07-25
MS.CO.P3(1).B2.209 | B2 - Walls Concreting work | 53 | m2 | 7 | 2026-07-22 | 2026-07-29
Part 4 |  |  |  | 11 | 2026-07-13 | 2026-07-25
MS.CO.P3(2).B2.100 | B2 - Columns Steel Fix | 432 | PCS | 7 | 2026-07-13 | 2026-07-20
MS.CO.P3(2).B2.200 | B2 - Walls Steel Fix | 53 | m2 | 7 | 2026-07-13 | 2026-07-20
MS.CO.P3(2).B2.103 | B2 - Columns Formwork | 432 | PCS | 7 | 2026-07-15 | 2026-07-22
MS.CO.P3(2).B2.203 | B2 - Walls Formwork | 53 | m2 | 7 | 2026-07-15 | 2026-07-22
MS.CO.P3(2).B2.108 | B2 - Columns Concreting work | 432 | PCS | 7 | 2026-07-18 | 2026-07-25
MS.CO.P3(2).B2.208 | B2 - Walls Concreting work | 53 | m2 | 7 | 2026-07-18 | 2026-07-25
Part 5 |  |  |  | 8 | 2026-10-20 | 2026-10-28
MS.CO.P3(2).B2.101 | B2 - Columns Steel Fix | 432 | PCS | 6 | 2026-10-20 | 2026-10-26
MS.CO.P3(2).B2.201 | B2 - Walls Steel Fix | 53 | m2 | 6 | 2026-10-20 | 2026-10-26
MS.CO.P3(2).B2.105 | B2 - Columns Formwork | 432 | PCS | 6 | 2026-10-21 | 2026-10-27
MS.CO.P3(2).B2.205 | B2 - Walls Formwork | 53 | m2 | 6 | 2026-10-21 | 2026-10-27
MS.CO.P3(2).B2.110 | B2 - Columns Concreting work | 432 | PCS | 1 | 2026-10-28 | 2026-10-28
MS.CO.P3(2).B2.210 | B2 - Walls Concreting work | 53 | m2 | 1 | 2026-10-28 | 2026-10-28
Part 6 |  |  |  | 14 | 2026-12-09 | 2026-12-24
MS.CO.P3(2).B2.102 | B2 - Columns Steel Fix | 432 | PCS | 6 | 2026-12-09 | 2026-12-15
MS.CO.P3(2).B2.202 | B2 - Walls Steel Fix | 53 | m2 | 6 | 2026-12-09 | 2026-12-15
MS.CO.P3(2).B2.106 | B2 - Columns Formwork | 432 | PCS | 6 | 2026-12-14 | 2026-12-20
MS.CO.P3(2).B2.206 | B2 - Walls Formwork | 53 | m2 | 6 | 2026-12-14 | 2026-12-20
MS.CO.P3(2).B2.111 | B2 - Columns Concreting work | 432 | PCS | 6 | 2026-12-19 | 2026-12-24
MS.CO.P3(2).B2.211 | B2 - Walls Concreting work | 53 | m2 | 6 | 2026-12-19 | 2026-12-24
Part 7 |  |  |  | 15 | 2026-12-13 | 2026-12-29
MS.CO.P3(2).B2.104 | B2 - Columns Steel Fix | 432 | PCS | 7 | 2026-12-13 | 2026-12-20
MS.CO.P3(2).B2.204 | B2 - Walls Steel Fix | 53 | m2 | 7 | 2026-12-13 | 2026-12-20
MS.CO.P3(2).B2.109 | B2 - Columns Formwork | 432 | PCS | 7 | 2026-12-17 | 2026-12-24
MS.CO.P3(2).B2.209 | B2 - Walls Formwork | 53 | m2 | 7 | 2026-12-17 | 2026-12-24
MS.CO.P3(2).B2.113 | B2 - Columns Concreting work | 432 | PCS | 7 | 2026-12-22 | 2026-12-29
MS.CO.P3(2).B2.213 | B2 - Walls Concreting work | 53 | m2 | 7 | 2026-12-22 | 2026-12-29
Slab |  |  |  | 178 | 2026-07-13 | 2027-02-06
Part 1 |  |  |  | 51 | 2026-07-14 | 2026-09-10
MS.CO.P3(1).B2.115 | Beams and Slab Formwork | 4093 | m2 | 10 | 2026-07-14 | 2026-07-25
MS.CO.P3(1).B2.118 | Beams and Slab Steel Fix | 4093 | m2 | 8 | 2026-08-03 | 2026-08-11
MS.CO.P3(1).B2.122 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-08-12 | 2026-08-12
MS.CO.P3(1).B2.130 | DE shuttering for Slab | 4093 | m2 | 6 | 2026-09-05 | 2026-09-10
Part 2 |  |  |  | 49 | 2026-07-13 | 2026-09-07
MS.CO.P3(1).B2.116 | Beams and Slab Formwork | 4093 | m2 | 10 | 2026-07-13 | 2026-07-23
MS.CO.P3(1).B2.119 | Beams and Slab Steel Fix | 4093 | m2 | 8 | 2026-08-03 | 2026-08-11
MS.CO.P3(1).B2.123 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-08-12 | 2026-08-12
MS.CO.P3(1).B2.131 | DE shuttering for Slab | 4093 | m2 | 3 | 2026-09-05 | 2026-09-07
Part 3 |  |  |  | 40 | 2026-07-26 | 2026-09-09
MS.CO.P3(1).B2.117 | Beams and Slab Formwork | 4093 | m2 | 10 | 2026-07-26 | 2026-08-05
MS.CO.P3(1).B2.120 | Beams and Slab Steel Fix | 4093 | m2 | 8 | 2026-08-06 | 2026-08-15
MS.CO.P3(1).B2.124 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-08-16 | 2026-08-16
MS.CO.P3(1).B2.132 | DE shuttering for Slab | 4093 | m2 | 2 | 2026-09-08 | 2026-09-09
Part 4 |  |  |  | 40 | 2026-08-17 | 2026-10-03
MS.CO.P3(2).B2.115 | Beams and Slab Formwork | 4093 | m2 | 10 | 2026-08-17 | 2026-08-27
MS.CO.P3(2).B2.118 | Beams and Slab Steel Fix | 4093 | m2 | 8 | 2026-08-29 | 2026-09-06
MS.CO.P3(2).B2.120 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-09-07 | 2026-09-07
MS.CO.P3(2).B2.130 | DE shuttering for Slab | 4093 | m2 | 2 | 2026-10-01 | 2026-10-03
Part 5 |  |  |  | 37 | 2026-10-29 | 2026-12-10
MS.CO.P3(2).B2.116 | Beams and Slab Formwork | 4093 | m2 | 8 | 2026-10-29 | 2026-11-07
MS.CO.P3(2).B2.121 | Beams and Slab Steel Fix | 4093 | m2 | 7 | 2026-11-08 | 2026-11-15
MS.CO.P3(2).B2.122 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-11-16 | 2026-11-16
MS.CO.P3(2).B2.131 | DE shuttering for Slab | 4093 | m2 | 2 | 2026-12-09 | 2026-12-10
Part 6 |  |  |  | 37 | 2026-12-22 | 2027-02-02
MS.CO.P3(2).B2.117 | Beams and Slab Formwork | 4093 | m2 | 7 | 2026-12-22 | 2026-12-29
MS.CO.P3(2).B2.123 | Beams and Slab Steel Fix | 4093 | m2 | 7 | 2026-12-30 | 2027-01-06
MS.CO.P3(2).B2.125 | Beams and Slab Concreting work | 4093 | m2 | 2 | 2027-01-07 | 2027-01-09
MS.CO.P3(2).B2.132 | DE shuttering for Slab | 4093 | m2 | 2 | 2027-02-01 | 2027-02-02
Part 7 |  |  |  | 37 | 2026-12-26 | 2027-02-06
MS.CO.P3(2).B2.119 | Beams and Slab Formwork | 4093 | m2 | 7 | 2026-12-26 | 2027-01-02
MS.CO.P3(2).B2.126 | Beams and Slab Steel Fix | 4093 | m2 | 7 | 2027-01-03 | 2027-01-10
MS.CO.P3(2).B2.127 | Beams and Slab Concreting work | 4093 | m2 | 2 | 2027-01-11 | 2027-01-12
MS.CO.P3(2).B2.133 | DE shuttering for Slab | 4093 | m2 | 2 | 2027-02-04 | 2027-02-06
Masonry Works |  |  |  | 25 | 2027-02-07 | 2027-03-16
MS.CO.P3(1).B2.135 | B2 - Block Works |  |  | 25 | 2027-02-07 | 2027-03-16
Basement 1 |  |  |  | 181 | 2026-08-13 | 2027-03-22
Vertical Element |  |  |  | 148 | 2026-08-13 | 2027-02-02
Part 1 |  |  |  | 16 | 2026-08-13 | 2026-08-31
MS.CO.P3(1).B1.100 | B1 - Columns Steel Fix | 432 | PCS | 8 | 2026-08-13 | 2026-08-22
MS.CO.P3(1).B1.200 | B1 - Walls Steel Fix | 53 | m2 | 8 | 2026-08-13 | 2026-08-22
MS.CO.P3(1).B1.103 | B1 - Columns Formwork | 432 | PCS | 8 | 2026-08-18 | 2026-08-26
MS.CO.P3(1).B1.203 | B1 - Walls Formwork | 53 | m2 | 8 | 2026-08-18 | 2026-08-26
MS.CO.P3(1).B1.107 | B1 - Columns Concreting work | 432 | PCS | 8 | 2026-08-23 | 2026-08-31
MS.CO.P3(1).B1.207 | B1 - Walls Concreting work | 53 | m2 | 8 | 2026-08-23 | 2026-08-31
Part 2 |  |  |  | 16 | 2026-08-13 | 2026-08-31
MS.CO.P3(1).B1.101 | B1 - Columns Steel Fix | 432 | PCS | 8 | 2026-08-13 | 2026-08-22
MS.CO.P3(1).B1.201 | B1 - Walls Steel Fix | 53 | m2 | 8 | 2026-08-13 | 2026-08-22
MS.CO.P3(1).B1.104 | B1 - Columns Formwork | 432 | PCS | 8 | 2026-08-18 | 2026-08-26
MS.CO.P3(1).B1.204 | B1 - Walls Formwork | 53 | m2 | 8 | 2026-08-18 | 2026-08-26
MS.CO.P3(1).B1.108 | B1 - Columns Concreting work | 432 | PCS | 8 | 2026-08-23 | 2026-08-31
MS.CO.P3(1).B1.208 | B1 - Walls Concreting work | 53 | m2 | 8 | 2026-08-23 | 2026-08-31
Part 3 |  |  |  | 16 | 2026-08-17 | 2026-09-03
MS.CO.P3(1).B1.102 | B1 - Columns Steel Fix | 432 | PCS | 8 | 2026-08-17 | 2026-08-25
MS.CO.P3(1).B1.202 | B1 - Walls Steel Fix | 53 | m2 | 8 | 2026-08-17 | 2026-08-25
MS.CO.P3(1).B1.105 | B1 - Columns Formwork | 432 | PCS | 8 | 2026-08-22 | 2026-08-30
MS.CO.P3(1).B1.205 | B1 - Walls Formwork | 53 | m2 | 8 | 2026-08-22 | 2026-08-30
MS.CO.P3(1).B1.109 | B1 - Columns Concreting work | 432 | PCS | 8 | 2026-08-26 | 2026-09-03
MS.CO.P3(1).B1.209 | B1 - Walls Concreting work | 53 | m2 | 8 | 2026-08-26 | 2026-09-03
Part 4 |  |  |  | 13 | 2026-09-08 | 2026-09-22
MS.CO.P3(2).B1.100 | B1 - Columns Steel Fix | 432 | PCS | 10 | 2026-09-08 | 2026-09-19
MS.CO.P3(2).B1.200 | B1 - Walls Steel Fix | 53 | m2 | 10 | 2026-09-08 | 2026-09-19
MS.CO.P3(2).B1.203 | B1 - Walls Formwork | 432 | PCS | 10 | 2026-09-09 | 2026-09-20
MS.CO.P3(2).B1.103 | B1 - Columns Formwork | 53 | m2 | 10 | 2026-09-10 | 2026-09-21
MS.CO.P3(2).B1.208 | B1 - Walls Concreting work | 432 | PCS | 10 | 2026-09-10 | 2026-09-21
MS.CO.P3(2).B1.108 | B1 - Columns Concreting work | 53 | m2 | 10 | 2026-09-12 | 2026-09-22
Part 5 |  |  |  | 12 | 2026-11-17 | 2026-11-30
MS.CO.P3(2).B1.101 | B1 - Columns Steel Fix | 432 | PCS | 6 | 2026-11-17 | 2026-11-23
MS.CO.P3(2).B1.201 | B1 - Walls Steel Fix | 53 | m2 | 6 | 2026-11-17 | 2026-11-23
MS.CO.P3(2).B1.105 | B1 - Columns Formwork | 432 | PCS | 6 | 2026-11-22 | 2026-11-28
MS.CO.P3(2).B1.205 | B1 - Walls Formwork | 53 | m2 | 6 | 2026-11-24 | 2026-11-30
MS.CO.P3(2).B1.210 | B1 - Walls Concreting work | 432 | PCS | 6 | 2026-11-24 | 2026-11-30
MS.CO.P3(2).B1.110 | B1 - Columns Concreting work | 53 | m2 | 1 | 2026-11-29 | 2026-11-29
Part 6 |  |  |  | 14 | 2027-01-10 | 2027-01-25
MS.CO.P3(2).B1.102 | B1 - Columns Steel Fix | 432 | PCS | 6 | 2027-01-10 | 2027-01-16
MS.CO.P3(2).B1.202 | B1 - Walls Steel Fix | 53 | m2 | 6 | 2027-01-10 | 2027-01-16
MS.CO.P3(2).B1.106 | B1 - Columns Formwork | 432 | PCS | 6 | 2027-01-14 | 2027-01-20
MS.CO.P3(2).B1.206 | B1 - Walls Formwork | 53 | m2 | 6 | 2027-01-17 | 2027-01-23
MS.CO.P3(2).B1.211 | B1 - Walls Concreting work | 432 | PCS | 6 | 2027-01-17 | 2027-01-23
MS.CO.P3(2).B1.111 | B1 - Columns Concreting work | 53 | m2 | 6 | 2027-01-19 | 2027-01-25
Part 7 |  |  |  | 18 | 2027-01-13 | 2027-02-02
MS.CO.P3(2).B1.104 | B1 - Columns Steel Fix | 432 | PCS | 6 | 2027-01-13 | 2027-01-19
MS.CO.P3(2).B1.204 | B1 - Walls Steel Fix | 53 | m2 | 6 | 2027-01-13 | 2027-01-19
MS.CO.P3(2).B1.109 | B1 - Columns Formwork | 432 | PCS | 6 | 2027-01-16 | 2027-01-21
MS.CO.P3(2).B1.113 | B1 - Columns Concreting work | 53 | m2 | 6 | 2027-01-18 | 2027-01-24
MS.CO.P3(2).B1.209 | B1 - Walls Formwork | 432 | PCS | 6 | 2027-01-20 | 2027-01-26
MS.CO.P3(2).B1.213 | B1 - Walls Concreting work | 53 | m2 | 6 | 2027-01-27 | 2027-02-02
Slab |  |  |  | 159 | 2026-09-08 | 2027-03-22
Part 1 |  |  |  | 37 | 2026-09-12 | 2026-10-25
MS.CO.P3(1).B1.115 | Beams and Slab Formwork | 4093 | m2 | 8 | 2026-09-12 | 2026-09-20
MS.CO.P3(1).B1.118 | Beams and Slab Steel Fix | 4093 | m2 | 7 | 2026-09-21 | 2026-09-29
MS.CO.P3(1).B1.122 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-09-30 | 2026-09-30
MS.CO.P3(1).B1.130 | DE shuttering for Slab | 4093 | m2 | 2 | 2026-10-24 | 2026-10-25
Part 2 |  |  |  | 37 | 2026-09-08 | 2026-10-21
MS.CO.P3(1).B1.116 | Beams and Slab Formwork | 4093 | m2 | 8 | 2026-09-08 | 2026-09-16
MS.CO.P3(1).B1.119 | Beams and Slab Steel Fix | 4093 | m2 | 7 | 2026-09-17 | 2026-09-26
MS.CO.P3(1).B1.123 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-09-27 | 2026-09-27
MS.CO.P3(1).B1.131 | DE shuttering for Slab | 4093 | m2 | 2 | 2026-10-20 | 2026-10-21
Part 3 |  |  |  | 39 | 2026-09-10 | 2026-10-26
MS.CO.P3(1).B1.117 | Beams and Slab Formwork | 4093 | m2 | 8 | 2026-09-10 | 2026-09-19
MS.CO.P3(1).B1.120 | Beams and Slab Steel Fix | 4093 | m2 | 7 | 2026-09-20 | 2026-09-28
MS.CO.P3(1).B1.124 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-09-29 | 2026-09-29
MS.CO.P3(1).B1.132 | DE shuttering for Slab | 4093 | m2 | 4 | 2026-10-22 | 2026-10-26
Part 4 |  |  |  | 35 | 2026-09-21 | 2026-11-01
MS.CO.P3(2).B1.115 | Beams and Slab Formwork | 4093 | m2 | 8 | 2026-09-21 | 2026-09-30
MS.CO.P3(2).B1.118 | Beams and Slab Steel Fix | 4093 | m2 | 5 | 2026-10-01 | 2026-10-06
MS.CO.P3(2).B1.120 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-10-07 | 2026-10-07
MS.CO.P3(2).B1.130 | DE shuttering for Slab | 4093 | m2 | 2 | 2026-10-31 | 2026-11-01
Part 5 |  |  |  | 35 | 2026-12-01 | 2027-01-10
MS.CO.P3(2).B1.116 | Beams and Slab Formwork | 4093 | m2 | 8 | 2026-12-01 | 2026-12-09
MS.CO.P3(2).B1.121 | Beams and Slab Steel Fix | 4093 | m2 | 5 | 2026-12-10 | 2026-12-15
MS.CO.P3(2).B1.122 | Beams and Slab Concreting work | 4093 | m2 | 1 | 2026-12-16 | 2026-12-16
MS.CO.P3(2).B1.131 | DE shuttering for Slab | 4093 | m2 | 2 | 2027-01-09 | 2027-01-10
Part 6 |  |  |  | 35 | 2027-01-23 | 2027-03-11
MS.CO.P3(2).B1.117 | Beams and Slab Formwork | 4093 | m2 | 7 | 2027-01-23 | 2027-01-30
MS.CO.P3(2).B1.123 | Beams and Slab Steel Fix | 4093 | m2 | 7 | 2027-01-31 | 2027-02-07
MS.CO.P3(2).B1.125 | Beams and Slab Concreting work | 4093 | m2 | 2 | 2027-02-08 | 2027-02-09
MS.CO.P3(2).B1.132 | DE shuttering for Slab | 4093 | m2 | 2 | 2027-03-10 | 2027-03-11
Part 7 |  |  |  | 36 | 2027-01-31 | 2027-03-22
MS.CO.P3(2).B1.119 | Beams and Slab Formwork | 4093 | m2 | 7 | 2027-01-31 | 2027-02-07
MS.CO.P3(2).B1.126 | Beams and Slab Steel Fix | 4093 | m2 | 7 | 2027-02-08 | 2027-02-16
MS.CO.P3(2).B1.127 | Beams and Slab Concreting work | 4093 | m2 | 2 | 2027-02-17 | 2027-02-18
MS.CO.P3(2).B1.133 | DE shuttering for Slab | 4093 | m2 | 2 | 2027-03-21 | 2027-03-22
Masonry Works |  |  |  | 8 | 2027-02-28 | 2027-03-14
MS.CO.P3(1).B1.135 | B2 - Block Works |  |  | 8 | 2027-02-28 | 2027-03-14
Super Structure Works |  |  |  | 151 | 2026-09-28 | 2027-03-31
4FA-K |  |  |  | 144 | 2026-10-01 | 2027-03-27
Lower Ground Floor |  |  |  | 83 | 2026-10-01 | 2027-01-05
Vertical Element |  |  |  | 15 | 2026-10-01 | 2026-10-18
MS.CO.P3(1).FAM.100 | Columns & Walls Steel Fix | 57 | pcs | 8 | 2026-10-01 | 2026-10-10
MS.CO.P3(1).FAM.101 | Columns & Walls Formwork | 57 | pcs | 8 | 2026-10-05 | 2026-10-13
MS.CO.P3(1).FAM.102 | Columns & Walls Concreting work | 57 | pcs | 8 | 2026-10-10 | 2026-10-18
Slab |  | 1814.8 | M2 | 33 | 2026-10-26 | 2026-12-02
MS.CO.P3(1).FAM.103 | Beams and Slab Formwork | 1814.8 | M2 | 6 | 2026-10-26 | 2026-11-01
MS.CO.P3(1).FAM.104 | Beams and Slab Steel Fix | 1814.8 | M2 | 5 | 2026-11-02 | 2026-11-07
MS.CO.P3(1).FAM.105 | Beams and Slab Concreting work | 1814.8 | M2 | 1 | 2026-11-08 | 2026-11-08
MS.CO.P3(1).FAM.109 | DE shuttering for Slab | 1814.8 | M2 | 2 | 2026-12-01 | 2026-12-02
Masonry Works |  |  |  | 29 | 2026-12-03 | 2027-01-05
MS.CO.P3(1).FAM.116 | External Block Work |  |  | 14 | 2026-12-03 | 2026-12-19
MS.CO.P3(1).FAM.118 | Internal Block Work |  |  | 20 | 2026-12-14 | 2027-01-05
Ground Floor |  |  |  | 70 | 2026-11-09 | 2027-01-28
Vertical Element |  |  |  | 8 | 2026-11-09 | 2026-11-17
MS.CO.P3(1).FAM.106 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2026-11-09 | 2026-11-12
MS.CO.P3(1).FAM.107 | Columns & Walls Formwork | 57 | pcs | 4 | 2026-11-11 | 2026-11-15
MS.CO.P3(1).FAM.108 | Columns & Walls Concreting work | 57 | pcs | 4 | 2026-11-14 | 2026-11-17
Slab |  | 1544 | M2 | 31 | 2026-11-15 | 2026-12-20
MS.CO.P3(1).FAM.110 | Beams and Slab Formwork | 1544 | M2 | 5 | 2026-11-15 | 2026-11-19
MS.CO.P3(1).FAM.111 | Beams and Slab Steel Fix | 1544 | M2 | 4 | 2026-11-21 | 2026-11-24
MS.CO.P3(1).FAM.112 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2026-11-25 | 2026-11-25
MS.CO.P3(1).FAM.117 | DE shuttering for Slab | 1544 | M2 | 2 | 2026-12-19 | 2026-12-20
Masonry Works |  |  |  | 34 | 2026-12-21 | 2027-01-28
MS.CO.P3(1).FAM.125 | External Block Work |  |  | 14 | 2026-12-21 | 2027-01-05
MS.CO.P3(1).FAM.126 | Internal Block Work |  |  | 20 | 2027-01-06 | 2027-01-28
First Floor |  |  |  | 69 | 2026-11-26 | 2027-02-15
Vertical Element |  | 57 | pcs | 8 | 2026-11-26 | 2026-12-05
MS.CO.P3(1).FAM.113 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2026-11-26 | 2026-11-30
MS.CO.P3(1).FAM.114 | Columns & Walls Formwork | 57 | pcs | 4 | 2026-11-29 | 2026-12-02
MS.CO.P3(1).FAM.115 | Columns & Walls Concreting work | 57 | pcs | 4 | 2026-12-01 | 2026-12-05
Slab |  | 1507.3 | M2 | 31 | 2026-12-03 | 2027-01-07
MS.CO.P3(1).FAM.119 | Beams and Slab Formwork | 1507.3 | M2 | 5 | 2026-12-03 | 2026-12-08
MS.CO.P3(1).FAM.120 | Beams and Slab Steel Fix | 1507.3 | M2 | 4 | 2026-12-09 | 2026-12-13
MS.CO.P3(1).FAM.121 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2026-12-14 | 2026-12-14
MS.CO.P3(1).FAM.127 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-01-06 | 2027-01-07
Masonry Works |  |  |  | 32 | 2027-01-09 | 2027-02-15
MS.CO.P3(1).FAM.134 | External Block Work |  |  | 14 | 2027-01-09 | 2027-01-24
MS.CO.P3(1).FAM.135 | Internal Block Work |  |  | 14 | 2027-01-30 | 2027-02-15
Second Floor |  |  |  | 65 | 2026-12-15 | 2027-03-04
Vertical Element |  |  |  | 8 | 2026-12-15 | 2026-12-23
MS.CO.P3(1).FAM.122 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2026-12-15 | 2026-12-19
MS.CO.P3(1).FAM.123 | Columns & Walls Formwork | 57 | pcs | 4 | 2026-12-17 | 2026-12-21
MS.CO.P3(1).FAM.124 | Columns & Walls Concreting work | 57 | pcs | 4 | 2026-12-20 | 2026-12-23
Slab |  | 1507.3 | M2 | 31 | 2026-12-22 | 2027-01-26
MS.CO.P3(1).FAM.128 | Beams and Slab Formwork | 1507.3 | M2 | 5 | 2026-12-22 | 2026-12-27
MS.CO.P3(1).FAM.129 | Beams and Slab Steel Fix | 1507.3 | M2 | 4 | 2026-12-28 | 2026-12-31
MS.CO.P3(1).FAM.130 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2027-01-02 | 2027-01-02
MS.CO.P3(1).FAM.136 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-01-25 | 2027-01-26
Masonry Works |  |  |  | 28 | 2027-01-27 | 2027-03-04
MS.CO.P3(1).FAM.144 | External Block Work |  |  | 12 | 2027-01-27 | 2027-02-09
MS.CO.P3(1).FAM.148 | Internal Block Work |  |  | 12 | 2027-02-16 | 2027-03-04
Third Floor |  |  |  | 61 | 2027-01-03 | 2027-03-23
Vertical Element |  |  |  | 7 | 2027-01-03 | 2027-01-10
MS.CO.P3(1).FAM.131 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2027-01-03 | 2027-01-06
MS.CO.P3(1).FAM.132 | Columns & Walls Formwork | 57 | pcs | 4 | 2027-01-04 | 2027-01-07
MS.CO.P3(1).FAM.133 | Columns & Walls Concreting work | 57 | pcs | 4 | 2027-01-06 | 2027-01-10
Slab |  | 1544 | M2 | 30 | 2027-01-09 | 2027-02-13
MS.CO.P3(1).FAM.137 | Beams and Slab Formwork | 1544 | M2 | 5 | 2027-01-09 | 2027-01-13
MS.CO.P3(1).FAM.138 | Beams and Slab Steel Fix | 1544 | M2 | 4 | 2027-01-14 | 2027-01-18
MS.CO.P3(1).FAM.139 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2027-01-19 | 2027-01-19
MS.CO.P3(1).FAM.147 | DE shuttering for Slab | 1544 | M2 | 2 | 2027-02-11 | 2027-02-13
Masonry Works |  |  |  | 26 | 2027-02-14 | 2027-03-23
MS.CO.P3(1).FAM.150 | External Block Work |  |  | 12 | 2027-02-14 | 2027-03-02
MS.CO.P3(1).FAM.151 | Internal Block Work |  |  | 12 | 2027-03-07 | 2027-03-23
Penthouse Floor |  |  |  | 49 | 2027-01-20 | 2027-03-27
Vertical Element |  |  |  | 4 | 2027-01-20 | 2027-01-24
MS.CO.P3(1).FAM.140 | Columns & Walls Steel Fix | 42 | pcs | 2 | 2027-01-20 | 2027-01-21
MS.CO.P3(1).FAM.141 | Columns & Walls Formwork | 42 | pcs | 2 | 2027-01-21 | 2027-01-23
MS.CO.P3(1).FAM.142 | Columns & Walls Concreting work | 42 | pcs | 2 | 2027-01-23 | 2027-01-24
Slab |  | 398.23 | M2 | 19 | 2027-01-27 | 2027-02-20
MS.CO.P3(1).FAM.143 | Beams and Slab Formwork | 398.23 | M2 | 3 | 2027-01-27 | 2027-01-30
MS.CO.P3(1).FAM.145 | Beams and Slab Steel Fix | 398.23 | M2 | 2 | 2027-01-31 | 2027-02-01
MS.CO.P3(1).FAM.146 | Beams and Slab Concreting work | 398.23 | M2 | 1 | 2027-02-02 | 2027-02-02
MS.CO.P3(1).FAM.149 | DE shuttering for Slab | 398.23 | M2 | 2 | 2027-02-18 | 2027-02-20
Masonry Works |  |  |  | 17 | 2027-03-03 | 2027-03-27
MS.CO.P3(1).FAM.152 | External Block Work |  |  | 8 | 2027-03-03 | 2027-03-16
MS.CO.P3(1).FAM.153 | Internal Block Work |  |  | 8 | 2027-03-18 | 2027-03-27
4FA-L |  |  |  | 149 | 2026-09-28 | 2027-03-29
Lower Ground Floor |  |  |  | 90 | 2026-09-28 | 2027-01-10
Vertical Element |  |  |  | 12 | 2026-09-28 | 2026-10-11
MS.CO.P3(1).FAN.100 | Columns & Walls Steel Fix | 57 | pcs | 6 | 2026-09-28 | 2026-10-04
MS.CO.P3(1).FAN.101 | Columns & Walls Formwork | 57 | pcs | 6 | 2026-10-01 | 2026-10-07
MS.CO.P3(1).FAN.102 | Columns & Walls Concreting work | 57 | pcs | 6 | 2026-10-05 | 2026-10-11
Slab |  | 1868 | M2 | 40 | 2026-10-22 | 2026-12-07
MS.CO.P3(1).FAN.103 | Beams and Slab Formwork | 1868 | M2 | 10 | 2026-10-22 | 2026-11-02
MS.CO.P3(1).FAN.104 | Beams and Slab Steel Fix | 1868 | M2 | 8 | 2026-11-03 | 2026-11-11
MS.CO.P3(1).FAN.105 | Beams and Slab Concreting work | 1868 | M2 | 1 | 2026-11-12 | 2026-11-12
MS.CO.P3(1).FAN.109 | DE shuttering for Slab | 1868 | M2 | 2 | 2026-12-06 | 2026-12-07
Masonry Works |  |  |  | 29 | 2026-12-08 | 2027-01-10
MS.CO.P3(1).FAN.116 | External Block Work |  |  | 14 | 2026-12-08 | 2026-12-23
MS.CO.P3(1).FAN.118 | Internal Block Work |  |  | 20 | 2026-12-19 | 2027-01-10
Ground Floor |  |  |  | 64 | 2026-11-14 | 2027-01-26
Vertical Element |  |  |  | 8 | 2026-11-14 | 2026-11-22
MS.CO.P3(1).FAN.106 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2026-11-14 | 2026-11-17
MS.CO.P3(1).FAN.107 | Columns & Walls Formwork | 57 | pcs | 4 | 2026-11-16 | 2026-11-19
MS.CO.P3(1).FAN.108 | Columns & Walls Concreting work | 57 | pcs | 4 | 2026-11-18 | 2026-11-22
Slab |  | 1544 | M2 | 31 | 2026-11-19 | 2026-12-24
MS.CO.P3(1).FAN.110 | Beams and Slab Formwork | 1544 | M2 | 5 | 2026-11-19 | 2026-11-24
MS.CO.P3(1).FAN.111 | Beams and Slab Steel Fix | 1544 | M2 | 4 | 2026-11-25 | 2026-11-29
MS.CO.P3(1).FAN.112 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2026-11-30 | 2026-11-30
MS.CO.P3(1).FAN.117 | DE shuttering for Slab | 1544 | M2 | 2 | 2026-12-23 | 2026-12-24
Masonry Works |  |  |  | 28 | 2026-12-26 | 2027-01-26
MS.CO.P3(1).FAN.125 | External Block Work |  |  | 14 | 2026-12-26 | 2027-01-10
MS.CO.P3(1).FAN.126 | Internal Block Work |  |  | 14 | 2027-01-11 | 2027-01-26
First Floor |  |  |  | 69 | 2026-12-01 | 2027-02-21
Vertical Element |  |  |  | 7 | 2026-12-01 | 2026-12-08
MS.CO.P3(1).FAN.113 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2026-12-01 | 2026-12-05
MS.CO.P3(1).FAN.114 | Columns & Walls Formwork | 57 | pcs | 4 | 2026-12-03 | 2026-12-07
MS.CO.P3(1).FAN.115 | Columns & Walls Concreting work | 57 | pcs | 1 | 2026-12-08 | 2026-12-08
Slab |  | 1507.3 | M2 | 33 | 2026-12-09 | 2027-01-16
MS.CO.P3(1).FAN.119 | Beams and Slab Formwork | 1507.3 | M2 | 6 | 2026-12-09 | 2026-12-15
MS.CO.P3(1).FAN.120 | Beams and Slab Steel Fix | 1507.3 | M2 | 5 | 2026-12-16 | 2026-12-21
MS.CO.P3(1).FAN.121 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2026-12-22 | 2026-12-22
MS.CO.P3(1).FAN.127 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-01-14 | 2027-01-16
Masonry Works |  |  |  | 29 | 2027-01-17 | 2027-02-21
MS.CO.P3(1).FAN.134 | External Block Work |  |  | 14 | 2027-01-17 | 2027-02-01
MS.CO.P3(1).FAN.135 | Internal Block Work |  |  | 20 | 2027-01-27 | 2027-02-21
Second Floor |  |  |  | 62 | 2026-12-23 | 2027-03-14
Vertical Element |  |  |  | 7 | 2026-12-23 | 2026-12-30
MS.CO.P3(1).FAN.122 | Columns & Walls Steel Fix | 57 | pcs | 5 | 2026-12-23 | 2026-12-28
MS.CO.P3(1).FAN.123 | Columns & Walls Formwork | 57 | pcs | 5 | 2026-12-24 | 2026-12-29
MS.CO.P3(1).FAN.124 | Columns & Walls Concreting work | 57 | pcs | 5 | 2026-12-26 | 2026-12-30
Slab |  | 1507.3 | M2 | 33 | 2026-12-27 | 2027-02-02
MS.CO.P3(1).FAN.128 | Beams and Slab Formwork | 1507.3 | M2 | 6 | 2026-12-27 | 2027-01-02
MS.CO.P3(1).FAN.129 | Beams and Slab Steel Fix | 1507.3 | M2 | 5 | 2027-01-03 | 2027-01-07
MS.CO.P3(1).FAN.130 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2027-01-09 | 2027-01-09
MS.CO.P3(1).FAN.136 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-02-01 | 2027-02-02
Masonry Works |  |  |  | 26 | 2027-02-03 | 2027-03-14
MS.CO.P3(1).FAN.144 | External Block Work |  |  | 12 | 2027-02-03 | 2027-02-17
MS.CO.P3(1).FAN.148 | Internal Block Work |  |  | 12 | 2027-02-23 | 2027-03-14
Third Floor |  |  |  | 59 | 2027-01-10 | 2027-03-28
Vertical Element |  |  |  | 6 | 2027-01-10 | 2027-01-16
MS.CO.P3(1).FAN.131 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2027-01-10 | 2027-01-13
MS.CO.P3(1).FAN.132 | Columns & Walls Formwork | 57 | pcs | 4 | 2027-01-11 | 2027-01-14
MS.CO.P3(1).FAN.133 | Columns & Walls Concreting work | 57 | pcs | 4 | 2027-01-12 | 2027-01-16
Slab |  | 1544 | M2 | 32 | 2027-01-17 | 2027-02-27
MS.CO.P3(1).FAN.137 | Beams and Slab Formwork | 1544 | M2 | 6 | 2027-01-17 | 2027-01-23
MS.CO.P3(1).FAN.138 | Beams and Slab Steel Fix | 1544 | M2 | 5 | 2027-01-24 | 2027-01-28
MS.CO.P3(1).FAN.139 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2027-01-30 | 2027-01-30
MS.CO.P3(1).FAN.147 | DE shuttering for Slab | 1544 | M2 | 2 | 2027-02-25 | 2027-02-27
Masonry Works |  |  |  | 21 | 2027-02-28 | 2027-03-28
MS.CO.P3(1).FAN.150 | External Block Work |  |  | 12 | 2027-02-28 | 2027-03-17
MS.CO.P3(1).FAN.151 | Internal Block Work |  |  | 12 | 2027-03-15 | 2027-03-28
Penthouse Floor |  |  |  | 42 | 2027-01-31 | 2027-03-29
Vertical Element |  |  |  | 4 | 2027-01-31 | 2027-02-03
MS.CO.P3(1).FAN.140 | Columns & Walls Steel Fix | 42 | pcs | 2 | 2027-01-31 | 2027-02-01
MS.CO.P3(1).FAN.141 | Columns & Walls Formwork | 42 | pcs | 2 | 2027-02-01 | 2027-02-02
MS.CO.P3(1).FAN.142 | Columns & Walls Concreting work | 42 | pcs | 2 | 2027-02-02 | 2027-02-03
Slab |  | 398.23 | M2 | 23 | 2027-02-06 | 2027-03-11
MS.CO.P3(1).FAN.143 | Beams and Slab Formwork | 398.23 | M2 | 4 | 2027-02-06 | 2027-02-09
MS.CO.P3(1).FAN.145 | Beams and Slab Steel Fix | 398.23 | M2 | 3 | 2027-02-10 | 2027-02-14
MS.CO.P3(1).FAN.146 | Beams and Slab Concreting work | 398.23 | M2 | 1 | 2027-02-15 | 2027-02-15
MS.CO.P3(1).FAN.149 | DE shuttering for Slab | 398.23 | M2 | 2 | 2027-03-10 | 2027-03-11
Masonry Works |  |  |  | 14 | 2027-03-14 | 2027-03-29
MS.CO.P3(1).FAN.152 | External Block Work |  |  | 8 | 2027-03-14 | 2027-03-22
MS.CO.P3(1).FAN.153 | Internal Block Work |  |  | 8 | 2027-03-21 | 2027-03-29
4FA-M |  |  |  | 149 | 2026-09-30 | 2027-03-31
Lower Ground Floor |  |  |  | 92 | 2026-09-30 | 2027-01-14
Vertical Element |  |  |  | 18 | 2026-09-30 | 2026-10-20
MS.CO.P3(1).FAO.100 | Columns & Walls Steel Fix | 57 | pcs | 6 | 2026-09-30 | 2026-10-06
MS.CO.P3(1).FAO.101 | Columns & Walls Formwork | 57 | pcs | 6 | 2026-10-12 | 2026-10-18
MS.CO.P3(1).FAO.102 | Columns & Walls Concreting work | 57 | pcs | 2 | 2026-10-19 | 2026-10-20
Slab |  | 1868 | M2 | 40 | 2026-10-27 | 2026-12-12
MS.CO.P3(1).FAO.103 | Beams and Slab Formwork | 1868 | M2 | 10 | 2026-10-27 | 2026-11-07
MS.CO.P3(1).FAO.104 | Beams and Slab Steel Fix | 1868 | M2 | 8 | 2026-11-08 | 2026-11-16
MS.CO.P3(1).FAO.105 | Beams and Slab Concreting work | 1868 | M2 | 1 | 2026-11-17 | 2026-11-17
MS.CO.P3(1).FAO.109 | DE shuttering for Slab | 1868 | M2 | 2 | 2026-12-10 | 2026-12-12
Masonry Works |  |  |  | 29 | 2026-12-13 | 2027-01-14
MS.CO.P3(1).FAO.116 | External Block Work |  |  | 14 | 2026-12-13 | 2026-12-28
MS.CO.P3(1).FAO.117 | Internal Block Work |  |  | 20 | 2026-12-23 | 2027-01-14
Ground Floor |  |  |  | 60 | 2026-11-18 | 2027-01-26
Vertical Element |  |  |  | 9 | 2026-11-18 | 2026-11-28
MS.CO.P3(1).FAO.106 | Columns & Walls Steel Fix | 57 | pcs | 5 | 2026-11-18 | 2026-11-23
MS.CO.P3(1).FAO.107 | Columns & Walls Formwork | 57 | pcs | 5 | 2026-11-22 | 2026-11-26
MS.CO.P3(1).FAO.108 | Columns & Walls Concreting work | 57 | pcs | 5 | 2026-11-23 | 2026-11-28
Slab |  | 1544 | M2 | 33 | 2026-11-24 | 2026-12-31
MS.CO.P3(1).FAO.110 | Beams and Slab Formwork | 1544 | M2 | 6 | 2026-11-24 | 2026-11-30
MS.CO.P3(1).FAO.111 | Beams and Slab Steel Fix | 1544 | M2 | 5 | 2026-12-01 | 2026-12-06
MS.CO.P3(1).FAO.112 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2026-12-07 | 2026-12-07
MS.CO.P3(1).FAO.118 | DE shuttering for Slab | 1544 | M2 | 2 | 2026-12-30 | 2026-12-31
Masonry Works |  |  |  | 22 | 2027-01-02 | 2027-01-26
MS.CO.P3(1).FAO.125 | External Block Work |  |  | 12 | 2027-01-02 | 2027-01-14
MS.CO.P3(1).FAO.126 | Internal Block Work |  |  | 10 | 2027-01-16 | 2027-01-26
First Floor |  |  |  | 53 | 2026-12-08 | 2027-02-07
Vertical Element |  |  |  | 6 | 2026-12-08 | 2026-12-14
MS.CO.P3(1).FAO.113 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2026-12-08 | 2026-12-12
MS.CO.P3(1).FAO.114 | Columns & Walls Formwork | 57 | pcs | 4 | 2026-12-09 | 2026-12-13
MS.CO.P3(1).FAO.115 | Columns & Walls Concreting work | 57 | pcs | 4 | 2026-12-10 | 2026-12-14
Slab |  | 1507.3 | M2 | 33 | 2026-12-12 | 2027-01-18
MS.CO.P3(1).FAO.119 | Beams and Slab Formwork | 1507.3 | M2 | 6 | 2026-12-12 | 2026-12-17
MS.CO.P3(1).FAO.120 | Beams and Slab Steel Fix | 1507.3 | M2 | 5 | 2026-12-19 | 2026-12-23
MS.CO.P3(1).FAO.121 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2026-12-24 | 2026-12-24
MS.CO.P3(1).FAO.127 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-01-17 | 2027-01-18
Masonry Works |  |  |  | 17 | 2027-01-19 | 2027-02-07
MS.CO.P3(1).FAO.134 | External Block Work |  |  | 14 | 2027-01-19 | 2027-02-03
MS.CO.P3(1).FAO.136 | Internal Block Work |  |  | 10 | 2027-01-27 | 2027-02-07
Second Floor |  |  |  | 53 | 2026-12-26 | 2027-03-01
Vertical Element |  |  |  | 8 | 2026-12-26 | 2027-01-03
MS.CO.P3(1).FAO.122 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2026-12-26 | 2026-12-29
MS.CO.P3(1).FAO.123 | Columns & Walls Formwork | 57 | pcs | 4 | 2026-12-28 | 2026-12-31
MS.CO.P3(1).FAO.124 | Columns & Walls Concreting work | 57 | pcs | 4 | 2026-12-30 | 2027-01-03
Slab |  | 1507.3 | M2 | 33 | 2026-12-31 | 2027-02-07
MS.CO.P3(1).FAO.128 | Beams and Slab Formwork | 1507.3 | M2 | 6 | 2026-12-31 | 2027-01-06
MS.CO.P3(1).FAO.129 | Beams and Slab Steel Fix | 1507.3 | M2 | 5 | 2027-01-07 | 2027-01-12
MS.CO.P3(1).FAO.130 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2027-01-13 | 2027-01-13
MS.CO.P3(1).FAO.135 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-02-06 | 2027-02-07
Masonry Works |  |  |  | 15 | 2027-02-08 | 2027-03-01
MS.CO.P3(1).FAO.144 | External Block Work |  |  | 12 | 2027-02-08 | 2027-02-24
MS.CO.P3(1).FAO.147 | Internal Block Work |  |  | 12 | 2027-02-11 | 2027-03-01
Third Floor |  |  |  | 46 | 2027-01-14 | 2027-03-17
Vertical Element |  |  |  | 6 | 2027-01-14 | 2027-01-20
MS.CO.P3(1).FAO.131 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2027-01-14 | 2027-01-18
MS.CO.P3(1).FAO.132 | Columns & Walls Formwork | 57 | pcs | 4 | 2027-01-16 | 2027-01-19
MS.CO.P3(1).FAO.133 | Columns & Walls Concreting work | 57 | pcs | 4 | 2027-01-17 | 2027-01-20
Slab |  | 1544 | M2 | 31 | 2027-01-18 | 2027-02-25
MS.CO.P3(1).FAO.137 | Beams and Slab Formwork | 1544 | M2 | 5 | 2027-01-18 | 2027-01-23
MS.CO.P3(1).FAO.138 | Beams and Slab Steel Fix | 1544 | M2 | 4 | 2027-01-24 | 2027-01-27
MS.CO.P3(1).FAO.139 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2027-01-28 | 2027-01-28
MS.CO.P3(1).FAO.148 | DE shuttering for Slab | 1544 | M2 | 2 | 2027-02-24 | 2027-02-25
Masonry Works |  |  |  | 12 | 2027-02-28 | 2027-03-17
MS.CO.P3(1).FAO.150 | External Block Work |  |  | 10 | 2027-02-28 | 2027-03-15
MS.CO.P3(1).FAO.151 | Internal Block Work |  |  | 10 | 2027-03-02 | 2027-03-17
Penthouse Floor |  |  |  | 45 | 2027-01-30 | 2027-03-31
Vertical Element |  |  |  | 5 | 2027-01-30 | 2027-02-03
MS.CO.P3(1).FAO.140 | Columns & Walls Steel Fix | 42 | pcs | 3 | 2027-01-30 | 2027-02-01
MS.CO.P3(1).FAO.141 | Columns & Walls Formwork | 42 | pcs | 3 | 2027-01-31 | 2027-02-02
MS.CO.P3(1).FAO.142 | Columns & Walls Concreting work | 42 | pcs | 3 | 2027-02-01 | 2027-02-03
Slab |  | 398.23 | M2 | 22 | 2027-02-02 | 2027-03-03
MS.CO.P3(1).FAO.143 | Beams and Slab Formwork | 398.23 | M2 | 4 | 2027-02-02 | 2027-02-06
MS.CO.P3(1).FAO.145 | Beams and Slab Steel Fix | 398.23 | M2 | 3 | 2027-02-07 | 2027-02-09
MS.CO.P3(1).FAO.146 | Beams and Slab Concreting work | 398.23 | M2 | 1 | 2027-02-10 | 2027-02-10
MS.CO.P3(1).FAO.149 | DE shuttering for Slab | 398.23 | M2 | 2 | 2027-03-02 | 2027-03-03
Masonry Works |  |  |  | 14 | 2027-03-16 | 2027-03-31
MS.CO.P3(1).FAO.152 | External Block Work |  |  | 8 | 2027-03-16 | 2027-03-24
MS.CO.P3(1).FAO.153 | Internal Block Work |  |  | 8 | 2027-03-23 | 2027-03-31
4FA-N |  |  |  | 133 | 2026-10-08 | 2027-03-21
Lower Ground Floor |  |  |  | 71 | 2026-10-08 | 2026-12-29
Vertical Element |  |  |  | 7 | 2026-10-08 | 2026-10-15
MS.CO.P3(2).FAL.100 | Columns & Walls Steel Fix | 57 | pcs | 5 | 2026-10-08 | 2026-10-13
MS.CO.P3(2).FAL.101 | Columns & Walls Formwork | 57 | pcs | 5 | 2026-10-10 | 2026-10-14
MS.CO.P3(2).FAL.102 | Columns & Walls Concreting work | 57 | pcs | 1 | 2026-10-15 | 2026-10-15
Slab |  | 1868 | M2 | 35 | 2026-10-17 | 2026-11-25
MS.CO.P3(2).FAL.103 | Beams and Slab Formwork | 1868 | M2 | 8 | 2026-10-17 | 2026-10-25
MS.CO.P3(2).FAL.104 | Beams and Slab Steel Fix | 1868 | M2 | 5 | 2026-10-26 | 2026-10-31
MS.CO.P3(2).FAL.105 | Beams and Slab Concreting work | 1868 | M2 | 1 | 2026-11-01 | 2026-11-01
MS.CO.P3(2).FAL.111 | DE shuttering for Slab | 1868 | M2 | 2 | 2026-11-24 | 2026-11-25
Masonry Works |  |  |  | 29 | 2026-11-26 | 2026-12-29
MS.CO.P3(2).FAL.117 | External Block Work |  |  | 14 | 2026-11-26 | 2026-12-12
MS.CO.P3(2).FAL.121 | Internal Block Work |  |  | 20 | 2026-12-07 | 2026-12-29
Ground Floor |  |  |  | 71 | 2026-11-02 | 2027-01-23
Vertical Element |  |  |  | 7 | 2026-11-02 | 2026-11-09
MS.CO.P3(2).FAL.106 | Columns & Walls Steel Fix | 57 | pcs | 5 | 2026-11-02 | 2026-11-07
MS.CO.P3(2).FAL.107 | Columns & Walls Formwork | 57 | pcs | 5 | 2026-11-03 | 2026-11-08
MS.CO.P3(2).FAL.108 | Columns & Walls Concreting work | 57 | pcs | 1 | 2026-11-09 | 2026-11-09
Slab |  | 1544 | M2 | 35 | 2026-11-10 | 2026-12-20
MS.CO.P3(2).FAL.109 | Beams and Slab Formwork | 1544 | M2 | 8 | 2026-11-10 | 2026-11-18
MS.CO.P3(2).FAL.110 | Beams and Slab Steel Fix | 1544 | M2 | 5 | 2026-11-19 | 2026-11-24
MS.CO.P3(2).FAL.112 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2026-11-25 | 2026-11-25
MS.CO.P3(2).FAL.119 | DE shuttering for Slab | 1544 | M2 | 2 | 2026-12-19 | 2026-12-20
Masonry Works |  |  |  | 29 | 2026-12-21 | 2027-01-23
MS.CO.P3(2).FAL.126 | External Block Work |  |  | 14 | 2026-12-21 | 2027-01-05
MS.CO.P3(2).FAL.130 | Internal Block Work |  |  | 20 | 2026-12-31 | 2027-01-23
First Floor |  |  |  | 65 | 2026-11-26 | 2027-02-09
Vertical Element |  |  |  | 7 | 2026-11-26 | 2026-12-03
MS.CO.P3(2).FAL.113 | Columns & Walls Steel Fix | 57 | pcs | 5 | 2026-11-26 | 2026-12-01
MS.CO.P3(2).FAL.114 | Columns & Walls Formwork | 57 | pcs | 5 | 2026-11-28 | 2026-12-02
MS.CO.P3(2).FAL.115 | Columns & Walls Concreting work | 57 | pcs | 1 | 2026-12-03 | 2026-12-03
Slab |  | 1507.3 | M2 | 35 | 2026-12-05 | 2027-01-13
MS.CO.P3(2).FAL.116 | Beams and Slab Formwork | 1507.3 | M2 | 8 | 2026-12-05 | 2026-12-13
MS.CO.P3(2).FAL.118 | Beams and Slab Steel Fix | 1507.3 | M2 | 5 | 2026-12-14 | 2026-12-19
MS.CO.P3(2).FAL.120 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2026-12-20 | 2026-12-20
MS.CO.P3(2).FAL.128 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-01-12 | 2027-01-13
Masonry Works |  |  |  | 23 | 2027-01-14 | 2027-02-09
MS.CO.P3(2).FAL.135 | External Block Work |  |  | 14 | 2027-01-14 | 2027-01-30
MS.CO.P3(2).FAL.141 | Internal Block Work |  |  | 14 | 2027-01-25 | 2027-02-09
Second Floor |  |  |  | 61 | 2026-12-21 | 2027-03-07
Vertical Element |  |  |  | 7 | 2026-12-21 | 2026-12-28
MS.CO.P3(2).FAL.122 | Columns & Walls Steel Fix | 57 | pcs | 5 | 2026-12-21 | 2026-12-26
MS.CO.P3(2).FAL.123 | Columns & Walls Formwork | 57 | pcs | 5 | 2026-12-22 | 2026-12-27
MS.CO.P3(2).FAL.124 | Columns & Walls Concreting work | 57 | pcs | 1 | 2026-12-28 | 2026-12-28
Slab |  | 1507.3 | M2 | 35 | 2026-12-29 | 2027-02-07
MS.CO.P3(2).FAL.125 | Beams and Slab Formwork | 1507.3 | M2 | 8 | 2026-12-29 | 2027-01-06
MS.CO.P3(2).FAL.127 | Beams and Slab Steel Fix | 1507.3 | M2 | 5 | 2027-01-07 | 2027-01-12
MS.CO.P3(2).FAL.129 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2027-01-13 | 2027-01-13
MS.CO.P3(2).FAL.137 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-02-06 | 2027-02-07
Masonry Works |  |  |  | 19 | 2027-02-08 | 2027-03-07
MS.CO.P3(2).FAL.146 | External Block Work |  |  | 10 | 2027-02-08 | 2027-02-21
MS.CO.P3(2).FAL.148 | Internal Block Work |  |  | 10 | 2027-02-21 | 2027-03-07
Third Floor |  |  |  | 49 | 2027-01-14 | 2027-03-21
Vertical Element |  |  |  | 7 | 2027-01-14 | 2027-01-21
MS.CO.P3(2).FAL.131 | Columns & Walls Steel Fix | 57 | pcs | 5 | 2027-01-14 | 2027-01-19
MS.CO.P3(2).FAL.132 | Columns & Walls Formwork | 57 | pcs | 5 | 2027-01-16 | 2027-01-20
MS.CO.P3(2).FAL.133 | Columns & Walls Concreting work | 57 | pcs | 1 | 2027-01-21 | 2027-01-21
Slab |  | 1544 | M2 | 30 | 2027-01-23 | 2027-03-02
MS.CO.P3(2).FAL.134 | Beams and Slab Formwork | 1544 | M2 | 8 | 2027-01-23 | 2027-01-31
MS.CO.P3(2).FAL.136 | Beams and Slab Steel Fix | 1544 | M2 | 5 | 2027-02-01 | 2027-02-06
MS.CO.P3(2).FAL.138 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2027-02-07 | 2027-02-07
MS.CO.P3(2).FAL.147 | DE shuttering for Slab | 1544 | M2 | 2 | 2027-03-01 | 2027-03-02
Masonry Works |  |  |  | 12 | 2027-03-03 | 2027-03-21
MS.CO.P3(2).FAL.150 | External Block Work |  |  | 6 | 2027-03-03 | 2027-03-14
MS.CO.P3(2).FAL.151 | Internal Block Work |  |  | 6 | 2027-03-15 | 2027-03-21
Penthouse Floor |  |  |  | 28 | 2027-02-08 | 2027-03-21
Vertical Element |  |  |  | 3 | 2027-02-08 | 2027-02-10
MS.CO.P3(2).FAL.139 | Columns & Walls Formwork | 42 | pcs | 2 | 2027-02-08 | 2027-02-09
MS.CO.P3(2).FAL.140 | Columns & Walls Steel Fix | 42 | pcs | 1 | 2027-02-08 | 2027-02-08
MS.CO.P3(2).FAL.142 | Columns & Walls Concreting work | 42 | pcs | 1 | 2027-02-10 | 2027-02-10
Slab |  | 398.23 | M2 | 18 | 2027-02-11 | 2027-03-09
MS.CO.P3(2).FAL.143 | Beams and Slab Formwork | 398.23 | M2 | 3 | 2027-02-11 | 2027-02-15
MS.CO.P3(2).FAL.144 | Beams and Slab Steel Fix | 398.23 | M2 | 2 | 2027-02-16 | 2027-02-17
MS.CO.P3(2).FAL.145 | Beams and Slab Concreting work | 398.23 | M2 | 1 | 2027-02-18 | 2027-02-18
MS.CO.P3(2).FAL.149 | DE shuttering for Slab | 398.23 | M2 | 2 | 2027-03-08 | 2027-03-09
Masonry Works |  |  |  | 7 | 2027-03-14 | 2027-03-21
MS.CO.P3(2).FAL.152 | External Block Work |  |  | 7 | 2027-03-14 | 2027-03-21
MS.CO.P3(2).FAL.153 | Internal Block Work |  |  | 7 | 2027-03-14 | 2027-03-21
4FA-O |  |  |  | 80 | 2026-12-17 | 2027-03-29
Lower Ground Floor |  |  |  | 49 | 2026-12-17 | 2027-02-11
Vertical Element |  |  |  | 4 | 2026-12-17 | 2026-12-21
MS.CO.P3(2).FAK.100 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2026-12-17 | 2026-12-19
MS.CO.P3(2).FAK.101 | Columns & Walls Formwork | 57 | pcs | 2 | 2026-12-19 | 2026-12-20
MS.CO.P3(2).FAK.102 | Columns & Walls Concreting work | 57 | pcs | 1 | 2026-12-21 | 2026-12-21
Slab |  | 1617.47 | M2 | 27 | 2026-12-22 | 2027-01-21
MS.CO.P3(2).FAK.103 | Beams and Slab Formwork | 1617.47 | M2 | 3 | 2026-12-22 | 2026-12-24
MS.CO.P3(2).FAK.104 | Beams and Slab Steel Fix | 1617.47 | M2 | 3 | 2026-12-24 | 2026-12-27
MS.CO.P3(2).FAK.105 | Beams and Slab Concreting work | 1617.47 | M2 | 1 | 2026-12-28 | 2026-12-28
MS.CO.P3(2).FAK.111 | DE shuttering for Slab | 1617.47 | M2 | 2 | 2027-01-20 | 2027-01-21
Masonry Works |  |  |  | 18 | 2027-01-23 | 2027-02-11
MS.CO.P3(2).FAK.117 | External Block Work |  |  | 12 | 2027-01-23 | 2027-02-04
MS.CO.P3(2).FAK.122 | Internal Block Work |  |  | 10 | 2027-02-01 | 2027-02-11
Mezzanine Floor |  |  |  | 50 | 2026-12-29 | 2027-03-01
Vertical Element |  |  |  | 4 | 2026-12-29 | 2027-01-02
MS.CO.P3(2).FAK.194 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2026-12-29 | 2026-12-30
MS.CO.P3(2).FAK.184 | Columns & Walls Formwork | 57 | pcs | 2 | 2026-12-30 | 2026-12-31
MS.CO.P3(2).FAK.204 | Columns & Walls Concreting work | 57 | pcs | 1 | 2027-01-02 | 2027-01-02
Slab |  | 548.65 | M2 | 27 | 2027-01-03 | 2027-02-02
MS.CO.P3(2).FAK.214 | Beams and Slab Formwork | 548.65 | M2 | 3 | 2027-01-03 | 2027-01-05
MS.CO.P3(2).FAK.224 | Beams and Slab Steel Fix | 548.65 | M2 | 3 | 2027-01-05 | 2027-01-07
MS.CO.P3(2).FAK.234 | Beams and Slab Concreting work | 548.65 | M2 | 1 | 2027-01-09 | 2027-01-09
MS.CO.P3(2).FAK.244 | DE shuttering for Slab | 548.65 | M2 | 2 | 2027-02-01 | 2027-02-02
Masonry Works |  |  |  | 19 | 2027-02-03 | 2027-03-01
MS.CO.P3(2).FAK.164 | External Block Work |  |  | 10 | 2027-02-03 | 2027-02-15
MS.CO.P3(2).FAK.174 | Internal Block Work |  |  | 8 | 2027-02-17 | 2027-03-01
Ground Floor |  |  |  | 43 | 2027-01-10 | 2027-03-04
Vertical Element |  |  |  | 4 | 2027-01-10 | 2027-01-13
MS.CO.P3(2).FAK.106 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2027-01-10 | 2027-01-11
MS.CO.P3(2).FAK.107 | Columns & Walls Formwork | 57 | pcs | 2 | 2027-01-11 | 2027-01-12
MS.CO.P3(2).FAK.108 | Columns & Walls Concreting work | 57 | pcs | 1 | 2027-01-13 | 2027-01-13
Slab |  | 548.65 | M2 | 26 | 2027-01-14 | 2027-02-14
MS.CO.P3(2).FAK.109 | Beams and Slab Formwork | 548.65 | M2 | 3 | 2027-01-14 | 2027-01-17
MS.CO.P3(2).FAK.110 | Beams and Slab Steel Fix | 548.65 | M2 | 3 | 2027-01-17 | 2027-01-19
MS.CO.P3(2).FAK.112 | Beams and Slab Concreting work | 548.65 | M2 | 1 | 2027-01-20 | 2027-01-20
MS.CO.P3(2).FAK.119 | DE shuttering for Slab | 548.65 | M2 | 2 | 2027-02-13 | 2027-02-14
Masonry Works |  |  |  | 13 | 2027-02-15 | 2027-03-04
MS.CO.P3(2).FAK.126 | External Block Work |  |  | 10 | 2027-02-15 | 2027-03-01
MS.CO.P3(2).FAK.131 | Internal Block Work |  |  | 8 | 2027-02-23 | 2027-03-04
First Floor |  |  |  | 50 | 2027-01-21 | 2027-03-29
Vertical Element |  |  |  | 4 | 2027-01-21 | 2027-01-25
MS.CO.P3(2).FAK.113 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2027-01-21 | 2027-01-23
MS.CO.P3(2).FAK.114 | Columns & Walls Formwork | 57 | pcs | 2 | 2027-01-23 | 2027-01-24
MS.CO.P3(2).FAK.115 | Columns & Walls Concreting work | 57 | pcs | 1 | 2027-01-25 | 2027-01-25
Slab |  | 1507.3 | M2 | 27 | 2027-01-26 | 2027-03-02
MS.CO.P3(2).FAK.116 | Beams and Slab Formwork | 1507.3 | M2 | 3 | 2027-01-26 | 2027-01-28
MS.CO.P3(2).FAK.118 | Beams and Slab Steel Fix | 1507.3 | M2 | 3 | 2027-01-28 | 2027-01-31
MS.CO.P3(2).FAK.120 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2027-02-01 | 2027-02-01
MS.CO.P3(2).FAK.128 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-03-01 | 2027-03-02
Masonry Works |  |  |  | 19 | 2027-03-03 | 2027-03-29
MS.CO.P3(2).FAK.135 | External Block Work |  |  | 10 | 2027-03-03 | 2027-03-18
MS.CO.P3(2).FAK.142 | Internal Block Work |  |  | 10 | 2027-03-18 | 2027-03-29
Second Floor |  |  |  | 34 | 2027-02-02 | 2027-03-22
Vertical Element |  |  |  | 4 | 2027-02-02 | 2027-02-06
MS.CO.P3(2).FAK.121 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2027-02-02 | 2027-02-03
MS.CO.P3(2).FAK.123 | Columns & Walls Formwork | 57 | pcs | 2 | 2027-02-03 | 2027-02-04
MS.CO.P3(2).FAK.124 | Columns & Walls Concreting work | 57 | pcs | 1 | 2027-02-06 | 2027-02-06
Slab |  | 1507.3 | M2 | 22 | 2027-02-07 | 2027-03-09
MS.CO.P3(2).FAK.125 | Beams and Slab Formwork | 1507.3 | M2 | 3 | 2027-02-07 | 2027-02-09
MS.CO.P3(2).FAK.127 | Beams and Slab Steel Fix | 1507.3 | M2 | 3 | 2027-02-09 | 2027-02-11
MS.CO.P3(2).FAK.129 | Beams and Slab Concreting work | 1507.3 | M2 | 1 | 2027-02-14 | 2027-02-14
MS.CO.P3(2).FAK.136 | DE shuttering for Slab | 1507.3 | M2 | 2 | 2027-03-08 | 2027-03-09
Masonry Works |  |  |  | 6 | 2027-03-16 | 2027-03-22
MS.CO.P3(2).FAK.146 | External Block Work |  |  | 6 | 2027-03-16 | 2027-03-22
MS.CO.P3(2).FAK.148 | Internal Block Work |  |  | 6 | 2027-03-16 | 2027-03-22
Third Floor |  |  |  | 29 | 2027-02-15 | 2027-03-28
Vertical Element |  |  |  | 5 | 2027-02-15 | 2027-02-21
MS.CO.P3(2).FAK.130 | Columns & Walls Steel Fix | 57 | pcs | 3 | 2027-02-15 | 2027-02-17
MS.CO.P3(2).FAK.132 | Columns & Walls Formwork | 57 | pcs | 3 | 2027-02-16 | 2027-02-18
MS.CO.P3(2).FAK.133 | Columns & Walls Concreting work | 57 | pcs | 1 | 2027-02-21 | 2027-02-21
Slab |  | 1544 | M2 | 18 | 2027-02-23 | 2027-03-21
MS.CO.P3(2).FAK.134 | Beams and Slab Formwork | 1544 | M2 | 3 | 2027-02-23 | 2027-02-25
MS.CO.P3(2).FAK.137 | Beams and Slab Steel Fix | 1544 | M2 | 3 | 2027-02-25 | 2027-03-01
MS.CO.P3(2).FAK.138 | Beams and Slab Concreting work | 1544 | M2 | 1 | 2027-03-02 | 2027-03-02
MS.CO.P3(2).FAK.147 | DE shuttering for Slab | 1544 | M2 | 2 | 2027-03-20 | 2027-03-21
Masonry Works |  |  |  | 6 | 2027-03-22 | 2027-03-28
MS.CO.P3(2).FAK.151 | External Block Work |  |  | 4 | 2027-03-22 | 2027-03-25
MS.CO.P3(2).FAK.154 | Internal Block Work |  |  | 4 | 2027-03-24 | 2027-03-28
Penthouse Floor |  |  |  | 18 | 2027-03-03 | 2027-03-28
Vertical Element |  |  |  | 1 | 2027-03-03 | 2027-03-03
MS.CO.P3(2).FAK.139 | Columns & Walls Formwork | 42 | pcs | 1 | 2027-03-03 | 2027-03-03
MS.CO.P3(2).FAK.140 | Columns & Walls Steel Fix | 42 | pcs | 1 | 2027-03-03 | 2027-03-03
MS.CO.P3(2).FAK.141 | Columns & Walls Concreting work | 42 | pcs | 1 | 2027-03-03 | 2027-03-03
Slab |  | 398.23 | M2 | 13 | 2027-03-04 | 2027-03-23
MS.CO.P3(2).FAK.143 | Beams and Slab Formwork | 398.23 | M2 | 2 | 2027-03-04 | 2027-03-07
MS.CO.P3(2).FAK.144 | Beams and Slab Steel Fix | 398.23 | M2 | 2 | 2027-03-07 | 2027-03-08
MS.CO.P3(2).FAK.145 | Beams and Slab Concreting work | 398.23 | M2 | 1 | 2027-03-09 | 2027-03-09
MS.CO.P3(2).FAK.149 | DE shuttering for Slab | 398.23 | M2 | 2 | 2027-03-22 | 2027-03-23
Masonry Works |  |  |  | 4 | 2027-03-24 | 2027-03-28
MS.CO.P3(2).FAK.152 | External Block Work |  |  | 4 | 2027-03-24 | 2027-03-28
MS.CO.P3(2).FAK.153 | Internal Block Work |  |  | 4 | 2027-03-24 | 2027-03-28
Mosque |  |  |  | 78 | 2026-12-17 | 2027-03-27
Ground Floor |  |  |  | 54 | 2026-12-17 | 2027-02-18
Skeleton Works |  |  |  | 54 | 2026-12-17 | 2027-02-18
MS.CO.P3(1)MQ.100 | GF- Columns & Walls Formwork, Steel & Concreting work | 40 | Pcs | 7 | 2026-12-17 | 2026-12-24
MS.CO.P3(1)MQ.101 | GF- Slabs & Beams Formwork, Steel Fix & Concreting Work | 644.54 | M2 | 12 | 2026-12-26 | 2027-01-07
MS.CO.P3(1)MQ.102 | GF- Slabs & Beams DE shuttering Work | 644.54 | M2 | 18 | 2027-01-09 | 2027-01-28
MS.CO.P3(1)MQ.106 | GF - Block Work | 644.54 | M2 | 17 | 2027-01-30 | 2027-02-18
First Floor |  |  |  | 54 | 2027-01-09 | 2027-03-21
Skeleton Works |  |  |  | 54 | 2027-01-09 | 2027-03-21
MS.CO.P3(1)MQ.103 | FF- Columns & Walls Formwork, steel Fix & Concreting work | 40 | Pcs | 7 | 2027-01-09 | 2027-01-16
MS.CO.P3(1)MQ.104 | FF- Slabs & Beams Formwork, steel Fix & Concreting work | 483.59 | M2 | 12 | 2027-01-17 | 2027-01-30
MS.CO.P3(1)MQ.107 | FF- Slabs & Beams DE shuttering work | 483.59 | M2 | 18 | 2027-01-31 | 2027-02-23
MS.CO.P3(1)MQ.111 | FF - Block Work | 483.59 | M2 | 17 | 2027-02-24 | 2027-03-21
Top Of Roof |  |  |  | 40 | 2027-01-31 | 2027-03-27
Skeleton Works |  |  |  | 40 | 2027-01-31 | 2027-03-27
MS.CO.P3(1)MQ.105 | Top Of Roof- Columns & Walls Formwork, Steel & Concreting work |  |  | 5 | 2027-01-31 | 2027-02-04
MS.CO.P3(1)MQ.108 | Top Of Roof- Slabs & Beams Formwork & Steel & Concreting work |  |  | 8 | 2027-02-06 | 2027-02-15
MS.CO.P3(1)MQ.109 | Top Of Roof- Slabs & Beams DE shuttering work |  |  | 12 | 2027-02-16 | 2027-03-04
MS.CO.P3(1)MQ.110 | Top Of Roof - External Block Work |  |  | 9 | 2027-03-07 | 2027-03-20
MS.CO.P3(1)MQ.113 | Top Of Roof - Internal Block Work |  |  | 9 | 2027-03-17 | 2027-03-27
External Work |  |  |  | 10 | 2027-03-07 | 2027-03-21
MS.CO.P3(1)MQ.112 | Special construction works planter, cross over ,water features ,canal |  |  | 10 | 2027-03-07 | 2027-03-21
Con.Phase (4) |  |  |  | 264 | 10-May-26 A | 2027-03-31
Soil Improvement |  |  |  | 35 | 10-May-26 A | 2026-06-27
MS.EN.P4.ALL.157 | trimming for CMC (up to bottom level of drop panel) |  |  | 32 | 10-May-26 A | 2026-06-15
MS.EN.P4.ALL.177 | Perform Geophysical Activity |  |  | 2 | 2026-06-11 | 2026-06-13
MS.EN.P4.ALL.187 | Soil Improvement |  |  | 12 | 2026-06-14 | 2026-06-27
MS.EN.P4.ALL.167 | Remaining CMC |  |  | 6 | 2026-06-21 | 2026-06-27
Sub-structure Works |  |  |  | 232 | 2026-06-21 | 2027-03-28
Foundation |  |  |  | 87 | 2026-06-21 | 2026-09-30
Part 1 |  |  |  | 61 | 2026-06-21 | 2026-08-30
Excavation, Blinding & Waterproofing Works |  | 3306 | M2 | 40 | 2026-06-21 | 2026-08-05
MS.CO.F4.FO.100 | Backfilling Including Drop Panels and Trenches | 3306 | M2 | 12 | 2026-06-21 | 2026-07-04
MS.CO.P1.FO.240 | Earthing and Lightning Protection System | 3306 | M2 | 4 | 2026-07-05 | 2026-07-08
MS.CO.F4.FO.112 | Blinding concrete for lower Part of Foundation | 3306 | M2 | 4 | 2026-07-09 | 2026-07-13
MS.CO.F4.FO.115 | Block work for Drop Panels | 3306 | M2 | 3 | 2026-07-14 | 2026-07-16
MS.CO.F4.FO.117 | Blinding concrete for Upper Part | 3306 | M2 | 4 | 2026-07-18 | 2026-07-21
MS.CO.F4.FO.120 | Water Proofing Membrane under Raft Foundation | 3306 | M2 | 13 | 2026-07-22 | 2026-08-05
Raft Foundation Works |  | 6557 | M2 | 21 | 2026-08-06 | 2026-08-30
MS.CO.F4.FO.111 | Rebars for 1st layer for Foundation | 6557 | M2 | 10 | 2026-08-06 | 2026-08-17
- | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 6557 | M2 | 9 | 2026-08-18 | 2026-08-27
MS.CO.F4.FO.113 | Installation for Mechanical and Electrical Embeds | 6557 | M2 | 6 | 2026-08-18 | 2026-08-24
MS.CO.F4.FO.114 | Formwork for Foundations | 6557 | M2 | 5 | 2026-08-23 | 2026-08-27
MS.CO.F4.FO.118 | Foundations Concrete Pouring | 6557 | M2 | 2 | 2026-08-29 | 2026-08-30
Part 2 |  |  |  | 60 | 2026-07-05 | 2026-09-12
Excavation, Blinding & Waterproofing Works |  | 3306 | M2 | 40 | 2026-07-05 | 2026-08-19
MS.CO.F4.FO.130 | Backfilling Including Drop Panels and Trenches | 3306 | M2 | 12 | 2026-07-05 | 2026-07-18
MS.CO.P1.FO.580 | Earthing and Lightning Protection System | 3306 | M2 | 4 | 2026-07-19 | 2026-07-22
MS.CO.F4.FO.140 | Blinding concrete for lower Part of Foundation | 3306 | M2 | 4 | 2026-07-23 | 2026-07-27
MS.CO.F4.FO.150 | Block work for Drop Panels | 3306 | M2 | 4 | 2026-07-28 | 2026-08-01
MS.CO.F4.FO.160 | Blinding concrete for Upper Part | 3306 | M2 | 4 | 2026-08-02 | 2026-08-05
MS.CO.F4.FO.170 | Water Proofing Membrane under Raft Foundation | 3306 | M2 | 12 | 2026-08-06 | 2026-08-19
Raft Foundation Works |  | 6557 | M2 | 20 | 2026-08-20 | 2026-09-12
MS.CO.F4.FO.106 | Rebars for 1st layer for Foundation | 6557 | M2 | 10 | 2026-08-20 | 2026-08-31
MS.CO.F4.FO.107 | Installation for Mechanical and Electrical Embeds | 6557 | M2 | 7 | 2026-08-27 | 2026-09-03
MS.CO.F4.FO.109 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 6557 | M2 | 8 | 2026-09-01 | 2026-09-09
MS.CO.F4.FO.108 | Formwork for Foundations | 6557 | M2 | 7 | 2026-09-02 | 2026-09-09
MS.CO.F4.FO.110 | Foundations Concrete Pouring | 6557 | M2 | 2 | 2026-09-10 | 2026-09-12
Part 3 |  |  |  | 63 | 2026-07-19 | 2026-09-30
Excavation, Blinding & Waterproofing Works |  | 3306 | M2 | 43 | 2026-07-19 | 2026-09-06
MS.CO.F4.FO.180 | Backfilling Including Drop Panels and Trenches | 3306 | M2 | 10 | 2026-07-19 | 2026-07-29
MS.CO.P1.FO.590 | Earthing and Lightning Protection System | 3306 | M2 | 3 | 2026-07-30 | 2026-08-02
MS.CO.F4.FO.190 | Blinding concrete for lower Part of Foundation | 3306 | M2 | 6 | 2026-08-03 | 2026-08-09
MS.CO.F4.FO.200 | Block work for Drop Panels | 3306 | M2 | 6 | 2026-08-10 | 2026-08-16
MS.CO.F4.FO.210 | Blinding concrete for Upper Part | 3306 | M2 | 6 | 2026-08-17 | 2026-08-23
MS.CO.F4.FO.220 | Water Proofing Membrane under Raft Foundation | 3306 | M2 | 12 | 2026-08-24 | 2026-09-06
Raft Foundation Works |  | 6557 | M2 | 20 | 2026-09-07 | 2026-09-30
MS.CO.F4.FO.101 | Rebars for 1st layer for Foundation | 6557 | M2 | 9 | 2026-09-07 | 2026-09-16
MS.CO.F4.FO.102 | Installation for Mechanical and Electrical Embeds | 6557 | M2 | 7 | 2026-09-14 | 2026-09-21
MS.CO.F4.FO.103 | Formwork for Foundations | 6557 | M2 | 7 | 2026-09-15 | 2026-09-22
MS.CO.F4.FO.104 | Rebars for 2nd layer for Foundation and Tower Crane Anchors | 6557 | M2 | 7 | 2026-09-19 | 2026-09-27
MS.CO.F4.FO.105 | Foundations Concrete Pouring | 6557 | M2 | 3 | 2026-09-28 | 2026-09-30
Basement 3 |  |  |  | 104 | 2026-08-31 | 2026-12-30
Skeleton Works |  |  |  | 81 | 2026-08-31 | 2026-12-03
Vertical Element |  |  |  | 44 | 2026-08-31 | 2026-10-21
Part 1 |  |  |  | 13 | 2026-08-31 | 2026-09-14
MS.CO.F4.B3.106 | B3 - Columns Steel Fix | 152 | Pcs | 6 | 2026-08-31 | 2026-09-06
MS.CO.F4.B3.206 | B3 - Walls Steel Fix | 171 | m2 | 6 | 2026-08-31 | 2026-09-06
MS.CO.F4.B3.207 | B3 - Walls Formwork | 171 | m2 | 6 | 2026-09-03 | 2026-09-09
MS.CO.F4.B3.107 | B3 - Columns Formwork | 152 | Pcs | 6 | 2026-09-05 | 2026-09-10
MS.CO.F4.B3.209 | B3 - Walls Concreting work | 171 | m2 | 6 | 2026-09-07 | 2026-09-13
MS.CO.F4.B3.109 | B3 - Columns Concreting work | 152 | Pcs | 6 | 2026-09-08 | 2026-09-14
Part 2 |  |  |  | 16 | 2026-09-13 | 2026-10-01
MS.CO.F4.B3.103 | B3 - Columns Steel Fix | 152 | Pcs | 6 | 2026-09-13 | 2026-09-19
MS.CO.F4.B3.203 | B3 - Walls Steel Fix | 171 | m2 | 6 | 2026-09-13 | 2026-09-19
MS.CO.F4.B3.104 | B3 - Columns Formwork | 152 | Pcs | 6 | 2026-09-17 | 2026-09-24
MS.CO.F4.B3.204 | B3 - Walls Formwork | 171 | m2 | 6 | 2026-09-17 | 2026-09-24
MS.CO.F4.B3.105 | B3 - Columns Concreting work | 152 | Pcs | 6 | 2026-09-22 | 2026-09-29
MS.CO.F4.B3.205 | B3 - Walls Concreting work | 171 | m2 | 6 | 2026-09-26 | 2026-10-01
Part 3 |  |  |  | 18 | 2026-10-01 | 2026-10-21
MS.CO.F4.B3.100 | B3 - Columns Steel Fix | 152 | Pcs | 9 | 2026-10-01 | 2026-10-11
MS.CO.F4.B3.201 | B3 - Walls Formwork | 1416 | m2 | 9 | 2026-10-01 | 2026-10-11
MS.CO.F4.B3.200 | B3 - Walls Steel Fix | 1416 | m2 | 9 | 2026-10-01 | 2026-10-11
MS.CO.F4.B3.101 | B3 - Columns Formwork | 152 | Pcs | 9 | 2026-10-06 | 2026-10-15
MS.CO.F4.B3.102 | B3 - Columns Concreting work | 152 | Pcs | 9 | 2026-10-11 | 2026-10-20
MS.CO.F4.B3.202 | B3 - Walls Concreting work | 1416 | m2 | 9 | 2026-10-12 | 2026-10-21
Slab |  |  |  | 75 | 2026-09-07 | 2026-12-03
Part 1 |  |  |  | 39 | 2026-09-07 | 2026-10-22
MS.CO.F4.B3.120 | Beams and Slab Formwork | 6557 | m2 | 11 | 2026-09-07 | 2026-09-19
MS.CO.F4.B3.122 | Beams and Slab Steel Fix | 6557 | m2 | 6 | 2026-09-20 | 2026-09-27
MS.CO.F4.B3.123 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2026-09-28 | 2026-09-28
MS.CO.F4.B3.132 | DE shuttering for Slab | 6557 | m2 | 2 | 2026-10-21 | 2026-10-22
Part 2 |  |  |  | 41 | 2026-09-26 | 2026-11-11
MS.CO.F4.B3.114 | Beams and Slab Formwork | 6557 | m2 | 12 | 2026-09-26 | 2026-10-08
MS.CO.F4.B3.117 | Beams and Slab Steel Fix | 6557 | m2 | 7 | 2026-10-10 | 2026-10-17
MS.CO.F4.B3.118 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2026-10-18 | 2026-10-18
MS.CO.F4.B3.128 | DE shuttering for Slab | 6557 | m2 | 2 | 2026-11-10 | 2026-11-11
Part 3 |  |  |  | 44 | 2026-10-14 | 2026-12-03
MS.CO.F4.B3.108 | Beams and Slab Formwork | 6557 | m2 | 12 | 2026-10-14 | 2026-10-27
MS.CO.F4.B3.110 | Beams and Slab Steel Fix | 6557 | m2 | 10 | 2026-10-28 | 2026-11-08
MS.CO.F4.B3.112 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2026-11-09 | 2026-11-09
MS.CO.F4.B3.124 | DE shuttering for Slab | 6557 | m2 | 2 | 2026-12-02 | 2026-12-03
Masonry Works |  |  |  | 23 | 2026-12-05 | 2026-12-30
MS.CO.F4.B3.135 | B3 - Block Works |  |  | 23 | 2026-12-05 | 2026-12-30
Basement 2 |  |  |  | 114 | 2026-09-29 | 2027-02-08
Skeleton Works |  |  |  | 91 | 2026-09-29 | 2027-01-12
Vertical Element |  |  |  | 53 | 2026-09-29 | 2026-11-29
Part 1 |  |  |  | 12 | 2026-09-29 | 2026-10-12
MS.CO.F4.B2.106 | B2 - Columns Steel Fix | 152 | Pcs | 6 | 2026-09-29 | 2026-10-05
MS.CO.F4.B2.206 | B2 - Walls Steel Fix | 2047 | m2 | 6 | 2026-09-29 | 2026-10-05
MS.CO.F4.B2.108 | B2 - Columns Formwork | 152 | Pcs | 6 | 2026-10-03 | 2026-10-08
MS.CO.F4.B2.208 | B2 - Walls Formwork | 2047 | m2 | 6 | 2026-10-03 | 2026-10-08
MS.CO.F4.B2.110 | B2 - Columns Concreting work | 152 | Pcs | 6 | 2026-10-06 | 2026-10-12
MS.CO.F4.B2.210 | B2 - Walls Concreting work | 2047 | m2 | 6 | 2026-10-06 | 2026-10-12
Part 2 |  |  |  | 14 | 2026-10-19 | 2026-11-03
MS.CO.F4.B2.103 | B2 - Columns Steel Fix | 152 | Pcs | 6 | 2026-10-19 | 2026-10-25
MS.CO.F4.B2.203 | B2 - Walls Steel Fix | 2047 | m2 | 6 | 2026-10-19 | 2026-10-25
MS.CO.F4.B2.104 | B2 - Columns Formwork | 152 | Pcs | 6 | 2026-10-22 | 2026-10-28
MS.CO.F4.B2.204 | B2 - Walls Formwork | 2047 | m2 | 6 | 2026-10-24 | 2026-10-29
MS.CO.F4.B2.105 | B2 - Columns Concreting work | 152 | Pcs | 6 | 2026-10-27 | 2026-11-02
MS.CO.F4.B2.205 | B2 - Walls Concreting work | 2047 | m2 | 6 | 2026-10-28 | 2026-11-03
Part 3 |  |  |  | 17 | 2026-11-10 | 2026-11-29
MS.CO.F4.B2.100 | B2 - Columns Steel Fix | 152 | Pcs | 9 | 2026-11-10 | 2026-11-19
MS.CO.F4.B2.200 | B2 - Walls Steel Fix | 2047 | m2 | 9 | 2026-11-10 | 2026-11-19
MS.CO.F4.B2.101 | B2 - Columns Formwork | 152 | Pcs | 9 | 2026-11-15 | 2026-11-24
MS.CO.F4.B2.201 | B2 - Walls Formwork | 2047 | m2 | 9 | 2026-11-15 | 2026-11-24
MS.CO.F4.B2.102 | B2 - Columns Concreting work | 152 | Pcs | 9 | 2026-11-19 | 2026-11-29
MS.CO.F4.B2.202 | B2 - Walls Concreting work | 2047 | m2 | 9 | 2026-11-19 | 2026-11-29
Slab |  |  |  | 84 | 2026-10-07 | 2027-01-12
Part 1 |  |  |  | 43 | 2026-10-07 | 2026-11-25
MS.CO.F4.B2.120 | Beams and Slab Formwork | 6557 | m2 | 11 | 2026-10-07 | 2026-10-19
MS.CO.F4.B2.122 | Beams and Slab Steel Fix | 6557 | m2 | 10 | 2026-10-20 | 2026-10-31
MS.CO.F4.B2.123 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2026-11-01 | 2026-11-01
MS.CO.F4.B2.132 | DE shuttering for Slab | 6557 | m2 | 2 | 2026-11-24 | 2026-11-25
Part 2 |  |  |  | 39 | 2026-10-31 | 2026-12-14
MS.CO.F4.B2.114 | Beams and Slab Formwork | 6557 | m2 | 10 | 2026-10-31 | 2026-11-10
MS.CO.F4.B2.117 | Beams and Slab Steel Fix | 6557 | m2 | 7 | 2026-11-11 | 2026-11-18
MS.CO.F4.B2.118 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2026-11-19 | 2026-11-19
MS.CO.F4.B2.128 | DE shuttering for Slab | 6557 | m2 | 2 | 2026-12-13 | 2026-12-14
Part 3 |  |  |  | 44 | 2026-11-23 | 2027-01-12
MS.CO.F4.B2.107 | Beams and Slab Formwork | 6557 | m2 | 12 | 2026-11-23 | 2026-12-06
MS.CO.F4.B2.109 | Beams and Slab Steel Fix | 6557 | m2 | 10 | 2026-12-07 | 2026-12-17
MS.CO.F4.B2.111 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2026-12-19 | 2026-12-19
MS.CO.F4.B2.124 | DE shuttering for Slab |  |  | 2 | 2027-01-11 | 2027-01-12
Masonry Works |  |  |  | 23 | 2027-01-13 | 2027-02-08
MS.CO.F4.B2.135 | B2 - Block Works |  |  | 23 | 2027-01-13 | 2027-02-08
Basement 1 |  |  |  | 118 | 2026-11-02 | 2027-03-28
Skeleton Works |  |  |  | 95 | 2026-11-02 | 2027-02-23
Vertical Element |  |  |  | 58 | 2026-11-02 | 2027-01-07
Part 1 |  |  |  | 12 | 2026-11-02 | 2026-11-15
MS.CO.F4.B1.106 | B1 - Columns Steel Fix | 152 | Pcs | 6 | 2026-11-02 | 2026-11-08
MS.CO.F4.B1.206 | B1 - Walls Steel Fix | 2047 | m2 | 6 | 2026-11-02 | 2026-11-08
MS.CO.F4.B1.108 | B1 - Columns Formwork | 152 | Pcs | 6 | 2026-11-05 | 2026-11-11
MS.CO.F4.B1.208 | B1 - Walls Formwork | 2047 | m2 | 6 | 2026-11-05 | 2026-11-11
MS.CO.F4.B1.111 | B1 - Columns Concreting work | 152 | Pcs | 6 | 2026-11-09 | 2026-11-15
MS.CO.F4.B1.211 | B1 - Walls Concreting work | 2047 | m2 | 6 | 2026-11-09 | 2026-11-15
Part 2 |  |  |  | 12 | 2026-11-21 | 2026-12-03
MS.CO.F4.B1.103 | B1 - Columns Steel Fix | 152 | Pcs | 6 | 2026-11-21 | 2026-11-26
MS.CO.F4.B1.203 | B1 - Walls Steel Fix | 2047 | m2 | 6 | 2026-11-21 | 2026-11-26
MS.CO.F4.B1.104 | B1 - Columns Formwork | 152 | Pcs | 6 | 2026-11-24 | 2026-11-30
MS.CO.F4.B1.204 | B1 - Walls Formwork | 2047 | m2 | 6 | 2026-11-24 | 2026-11-30
MS.CO.F4.B1.105 | B1 - Columns Concreting work | 152 | Pcs | 6 | 2026-11-28 | 2026-12-03
MS.CO.F4.B1.205 | B1 - Walls Concreting work | 2047 | m2 | 6 | 2026-11-28 | 2026-12-03
Part 3 |  |  |  | 17 | 2026-12-20 | 2027-01-07
MS.CO.F4.B1.100 | B1 - Columns Steel Fix | 152 | Pcs | 9 | 2026-12-20 | 2026-12-29
MS.CO.F4.B1.200 | B1 - Walls Steel Fix | 2047 | m2 | 9 | 2026-12-20 | 2026-12-29
MS.CO.F4.B1.101 | B1 - Columns Formwork | 152 | Pcs | 9 | 2026-12-24 | 2027-01-03
MS.CO.F4.B1.201 | B1 - Walls Formwork | 2047 | m2 | 9 | 2026-12-24 | 2027-01-03
MS.CO.F4.B1.102 | B1 - Columns Concreting work | 152 | Pcs | 9 | 2026-12-29 | 2027-01-07
MS.CO.F4.B1.202 | B1 - Walls Concreting work | 2047 | m2 | 9 | 2026-12-29 | 2027-01-07
Slab |  |  |  | 88 | 2026-11-10 | 2027-02-23
Part 1 |  |  |  | 39 | 2026-11-10 | 2026-12-24
MS.CO.F4.B1.120 | Beams and Slab Formwork | 6557 | m2 | 10 | 2026-11-10 | 2026-11-21
MS.CO.F4.B1.123 | Beams and Slab Steel Fix | 6557 | m2 | 7 | 2026-11-22 | 2026-11-29
MS.CO.F4.B1.124 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2026-11-30 | 2026-11-30
MS.CO.F4.B1.132 | DE shuttering for Slab | 6557 | m2 | 2 | 2026-12-23 | 2026-12-24
Part 2 |  |  |  | 41 | 2026-11-30 | 2027-01-16
MS.CO.F4.B1.114 | Beams and Slab Formwork | 6557 | m2 | 12 | 2026-11-30 | 2026-12-13
MS.CO.F4.B1.117 | Beams and Slab Steel Fix | 6557 | m2 | 7 | 2026-12-14 | 2026-12-21
MS.CO.F4.B1.118 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2026-12-22 | 2026-12-22
MS.CO.F4.B1.128 | DE shuttering for Slab | 6557 | m2 | 2 | 2027-01-14 | 2027-01-16
Part 3 |  |  |  | 43 | 2027-01-02 | 2027-02-23
MS.CO.F4.B1.107 | Beams and Slab Formwork | 6557 | m2 | 12 | 2027-01-02 | 2027-01-14
MS.CO.F4.B1.109 | Beams and Slab Steel Fix | 6557 | m2 | 10 | 2027-01-16 | 2027-01-26
MS.CO.F4.B1.110 | Beams and Slab Concreting work | 6557 | m2 | 1 | 2027-01-27 | 2027-01-27
MS.CO.F4.B1.122 | DE shuttering for Slab | 6557 | m2 | 2 | 2027-02-22 | 2027-02-23
Masonry Works |  |  |  | 23 | 2027-02-24 | 2027-03-28
MS.CO.F4.B1.135 | B1 - Block Works |  |  | 23 | 2027-02-24 | 2027-03-28
Super Strcture Works |  |  |  | 96 | 2026-12-01 | 2027-03-31
FC-Q |  |  |  | 77 | 2026-12-23 | 2027-03-31
Ground Floor |  |  |  | 63 | 2026-12-23 | 2027-03-15
Vertical Element |  |  |  | 6 | 2026-12-23 | 2026-12-29
MS.CO.F4.FCQ.100 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2026-12-23 | 2026-12-27
MS.CO.F4.FCQ.101 | Columns & Walls Formwork | 57 | pcs | 4 | 2026-12-24 | 2026-12-28
MS.CO.F4.FCQ.102 | Columns & Walls Concreting work | 57 | pcs | 4 | 2026-12-26 | 2026-12-29
Slab |  | 2187.12 | M2 | 31 | 2026-12-27 | 2027-01-31
MS.CO.F4.FCQ.103 | Beams and Slab Formwork | 2187.12 | M2 | 5 | 2026-12-27 | 2026-12-31
MS.CO.F4.FCQ.104 | Beams and Slab Steel Fix | 2187.12 | M2 | 4 | 2027-01-02 | 2027-01-05
MS.CO.F4.FCQ.105 | Beams and Slab Concreting work | 2187.12 | M2 | 1 | 2027-01-06 | 2027-01-06
MS.CO.F4.FCQ.109 | DE shuttering for Slab | 2187.12 | M2 | 2 | 2027-01-30 | 2027-01-31
Masonry Works |  |  |  | 29 | 2027-02-01 | 2027-03-15
MS.CO.F4.FCQ.114 | External Block Work |  |  | 14 | 2027-02-01 | 2027-02-17
MS.CO.F4.FCQ.117 | Internal Block Work |  |  | 20 | 2027-02-11 | 2027-03-15
First Floor |  |  |  | 64 | 2027-01-07 | 2027-03-31
Vertical Element |  |  |  | 6 | 2027-01-07 | 2027-01-13
MS.CO.F4.FCQ.106 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2027-01-07 | 2027-01-11
MS.CO.F4.FCQ.107 | Columns & Walls Formwork | 57 | pcs | 4 | 2027-01-09 | 2027-01-12
MS.CO.F4.FCQ.108 | Columns & Walls Concreting work | 57 | pcs | 4 | 2027-01-10 | 2027-01-13
Slab |  | 1762.22 | M2 | 31 | 2027-01-11 | 2027-02-16
MS.CO.F4.FCQ.110 | Beams and Slab Formwork | 1762.22 | M2 | 5 | 2027-01-11 | 2027-01-16
MS.CO.F4.FCQ.111 | Beams and Slab Steel Fix | 1762.22 | M2 | 4 | 2027-01-17 | 2027-01-20
MS.CO.F4.FCQ.112 | Beams and Slab Concreting work | 1762.22 | M2 | 1 | 2027-01-21 | 2027-01-21
MS.CO.F4.FCQ.118 | DE shuttering for Slab | 1762.22 | M2 | 2 | 2027-02-15 | 2027-02-16
Masonry Works |  |  |  | 29 | 2027-02-18 | 2027-03-31
MS.CO.F4.FCQ.123 | External Block Work |  |  | 14 | 2027-02-18 | 2027-03-14
MS.CO.F4.FCQ.127 | Internal Block Work |  |  | 20 | 2027-03-04 | 2027-03-31
Second Floor |  |  |  | 49 | 2027-01-23 | 2027-03-29
Vertical Element |  |  |  | 6 | 2027-01-23 | 2027-01-28
MS.CO.F4.FCQ.113 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2027-01-23 | 2027-01-26
MS.CO.F4.FCQ.115 | Columns & Walls Formwork | 57 | pcs | 4 | 2027-01-24 | 2027-01-27
MS.CO.F4.FCQ.116 | Columns & Walls Concreting work | 57 | pcs | 4 | 2027-01-25 | 2027-01-28
Slab |  | 1699.95 | M2 | 30 | 2027-01-26 | 2027-03-07
MS.CO.F4.FCQ.119 | Beams and Slab Formwork | 1699.95 | M2 | 5 | 2027-01-26 | 2027-01-31
MS.CO.F4.FCQ.120 | Beams and Slab Steel Fix | 1699.95 | M2 | 4 | 2027-02-01 | 2027-02-04
MS.CO.F4.FCQ.121 | Beams and Slab Concreting work | 1699.95 | M2 | 1 | 2027-02-06 | 2027-02-06
MS.CO.F4.FCQ.126 | DE shuttering for Slab | 1699.95 | M2 | 2 | 2027-03-06 | 2027-03-07
Masonry Works |  |  |  | 13 | 2027-03-15 | 2027-03-29
MS.CO.F4.FCQ.132 | External Block Work |  |  | 10 | 2027-03-15 | 2027-03-25
MS.CO.F4.FCQ.136 | Internal Block Work |  |  | 10 | 2027-03-18 | 2027-03-29
Third Floor |  |  |  | 38 | 2027-02-07 | 2027-03-31
Vertical Element |  |  |  | 6 | 2027-02-07 | 2027-02-14
MS.CO.F4.FCQ.122 | Columns & Walls Steel Fix | 57 | pcs | 4 | 2027-02-07 | 2027-02-10
MS.CO.F4.FCQ.124 | Columns & Walls Formwork | 57 | pcs | 4 | 2027-02-08 | 2027-02-11
MS.CO.F4.FCQ.125 | Columns & Walls Concreting work | 57 | pcs | 4 | 2027-02-09 | 2027-02-14
Slab |  | 1762.1 | M2 | 25 | 2027-02-10 | 2027-03-20
MS.CO.F4.FCQ.128 | Beams and Slab Formwork | 1762.1 | M2 | 4 | 2027-02-10 | 2027-02-15
MS.CO.F4.FCQ.129 | Beams and Slab Steel Fix | 1762.1 | M2 | 3 | 2027-02-16 | 2027-02-18
MS.CO.F4.FCQ.130 | Beams and Slab Concreting work | 1762.1 | M2 | 1 | 2027-02-21 | 2027-02-21
MS.CO.F4.FCQ.137 | DE shuttering for Slab | 1762.1 | M2 | 2 | 2027-03-18 | 2027-03-20
Masonry Works |  |  |  | 10 | 2027-03-21 | 2027-03-31
MS.CO.F4.FCQ.140 | External Block Work |  |  | 8 | 2027-03-21 | 2027-03-29
MS.CO.F4.FCQ.142 | Internal Block Work |  |  | 8 | 2027-03-23 | 2027-03-31
Penthouse Floor |  |  |  | 26 | 2027-02-23 | 2027-03-30
Vertical Element |  |  |  | 4 | 2027-02-23 | 2027-02-28
MS.CO.F4.FCQ.131 | Columns & Walls Steel Fix | 42 | pcs | 2 | 2027-02-23 | 2027-02-24
MS.CO.F4.FCQ.133 | Columns & Walls Formwork | 42 | pcs | 2 | 2027-02-24 | 2027-02-25
MS.CO.F4.FCQ.134 | Columns & Walls Concreting work | 42 | pcs | 2 | 2027-02-25 | 2027-02-28
Slab |  | 433.09 | M2 | 17 | 2027-02-28 | 2027-03-23
MS.CO.F4.FCQ.135 | Beams and Slab Formwork | 433.09 | M2 | 3 | 2027-02-28 | 2027-03-02
MS.CO.F4.FCQ.138 | Beams and Slab Steel Fix | 433.09 | M2 | 2 | 2027-03-03 | 2027-03-04
MS.CO.F4.FCQ.139 | Beams and Slab Concreting work | 433.09 | M2 | 1 | 2027-03-07 | 2027-03-07
MS.CO.F4.FCQ.141 | DE shuttering for Slab | 433.09 | M2 | 1 | 2027-03-23 | 2027-03-23
Masonry Works |  |  |  | 6 | 2027-03-24 | 2027-03-30
MS.CO.F4.FCQ.143 | External Block Work |  |  | 6 | 2027-03-24 | 2027-03-30
MS.CO.F4.FCQ.144 | Internal Block Work |  |  | 6 | 2027-03-24 | 2027-03-30
FC-D |  |  |  | 96 | 2026-12-01 | 2027-03-31
Ground Floor |  |  |  | 62 | 2026-12-01 | 2027-02-10
Vertical Element |  |  |  | 5 | 2026-12-01 | 2026-12-06
MS.CO.F4.FCD.100 | Columns & Walls Steel Fix | 57 | pcs | 3 | 2026-12-01 | 2026-12-03
MS.CO.F4.FCD.101 | Columns & Walls Formwork | 57 | pcs | 3 | 2026-12-02 | 2026-12-05
MS.CO.F4.FCD.102 | Columns & Walls Concreting work | 57 | pcs | 3 | 2026-12-03 | 2026-12-06
Slab |  | 2796.65 | M2 | 29 | 2026-12-06 | 2027-01-07
MS.CO.F4.FCD.103 | Beams and Slab Formwork | 2796.65 | M2 | 4 | 2026-12-06 | 2026-12-09
MS.CO.F4.FCD.104 | Beams and Slab Steel Fix | 2796.65 | M2 | 3 | 2026-12-10 | 2026-12-13
MS.CO.F4.FCD.105 | Beams and Slab Concreting work | 2796.65 | M2 | 1 | 2026-12-14 | 2026-12-14
MS.CO.F4.FCD.109 | DE shuttering for Slab | 2796.65 | M2 | 2 | 2027-01-06 | 2027-01-07
Masonry Works |  |  |  | 29 | 2027-01-09 | 2027-02-10
MS.CO.F4.FCD.113 | External Block Work |  |  | 14 | 2027-01-09 | 2027-01-24
MS.CO.F4.FCD.116 | Internal Block Work |  |  | 20 | 2027-01-19 | 2027-02-10
First Floor |  |  |  | 70 | 2026-12-15 | 2027-03-15
Vertical Element |  |  |  | 5 | 2026-12-15 | 2026-12-20
MS.CO.F4.FCD.106 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2026-12-15 | 2026-12-16
MS.CO.F4.FCD.107 | Columns & Walls Formwork | 57 | pcs | 2 | 2026-12-16 | 2026-12-17
MS.CO.F4.FCD.108 | Columns & Walls Concreting work | 57 | pcs | 2 | 2026-12-19 | 2026-12-20
Slab |  | 2276.61 | M2 | 28 | 2026-12-21 | 2027-01-21
MS.CO.F4.FCD.110 | Beams and Slab Formwork | 2276.61 | M2 | 3 | 2026-12-21 | 2026-12-23
MS.CO.F4.FCD.111 | Beams and Slab Steel Fix | 2276.61 | M2 | 3 | 2026-12-24 | 2026-12-27
MS.CO.F4.FCD.112 | Beams and Slab Concreting work | 2276.61 | M2 | 1 | 2026-12-28 | 2026-12-28
MS.CO.F4.FCD.118 | DE shuttering for Slab | 2276.61 | M2 | 2 | 2027-01-20 | 2027-01-21
Masonry Works |  |  |  | 35 | 2027-01-25 | 2027-03-15
MS.CO.F4.FCD.122 | External Block Work |  |  | 14 | 2027-01-25 | 2027-02-09
MS.CO.F4.FCD.125 | Internal Block Work |  |  | 20 | 2027-02-11 | 2027-03-15
Second Floor |  |  |  | 70 | 2026-12-29 | 2027-03-29
Vertical Element |  |  |  | 5 | 2026-12-29 | 2027-01-03
MS.CO.F4.FCD.114 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2026-12-29 | 2026-12-30
MS.CO.F4.FCD.115 | Columns & Walls Formwork | 57 | pcs | 2 | 2026-12-30 | 2026-12-31
MS.CO.F4.FCD.117 | Columns & Walls Concreting work | 57 | pcs | 2 | 2027-01-02 | 2027-01-03
Slab |  | 2174.09 | M2 | 28 | 2027-01-03 | 2027-02-03
MS.CO.F4.FCD.119 | Beams and Slab Formwork | 2174.09 | M2 | 3 | 2027-01-03 | 2027-01-05
MS.CO.F4.FCD.120 | Beams and Slab Steel Fix | 2174.09 | M2 | 3 | 2027-01-06 | 2027-01-09
MS.CO.F4.FCD.121 | Beams and Slab Concreting work | 2174.09 | M2 | 1 | 2027-01-10 | 2027-01-10
MS.CO.F4.FCD.127 | DE shuttering for Slab | 2174.09 | M2 | 2 | 2027-02-02 | 2027-02-03
Masonry Works |  |  |  | 33 | 2027-02-10 | 2027-03-29
MS.CO.F4.FCD.131 | External Block Work |  |  | 12 | 2027-02-10 | 2027-02-28
MS.CO.F4.FCD.134 | Internal Block Work |  |  | 12 | 2027-03-16 | 2027-03-29
Third Floor |  |  |  | 61 | 2027-01-11 | 2027-03-31
Vertical Element |  |  |  | 5 | 2027-01-11 | 2027-01-16
MS.CO.F4.FCD.123 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2027-01-11 | 2027-01-12
MS.CO.F4.FCD.124 | Columns & Walls Formwork | 57 | pcs | 2 | 2027-01-12 | 2027-01-13
MS.CO.F4.FCD.126 | Columns & Walls Concreting work | 57 | pcs | 2 | 2027-01-14 | 2027-01-16
Slab |  | 2175.29 | M2 | 28 | 2027-01-16 | 2027-02-17
MS.CO.F4.FCD.128 | Beams and Slab Formwork | 2175.29 | M2 | 3 | 2027-01-16 | 2027-01-18
MS.CO.F4.FCD.129 | Beams and Slab Steel Fix | 2175.29 | M2 | 3 | 2027-01-19 | 2027-01-21
MS.CO.F4.FCD.130 | Beams and Slab Concreting work | 2175.29 | M2 | 1 | 2027-01-23 | 2027-01-23
MS.CO.F4.FCD.136 | DE shuttering for Slab | 2175.29 | M2 | 2 | 2027-02-16 | 2027-02-17
Masonry Works |  |  |  | 23 | 2027-03-01 | 2027-03-31
MS.CO.F4.FCD.140 | External Block Work |  |  | 12 | 2027-03-01 | 2027-03-18
MS.CO.F4.FCD.143 | Internal Block Work |  |  | 14 | 2027-03-16 | 2027-03-31
Fourth Floor |  |  |  | 46 | 2027-01-24 | 2027-03-27
Vertical Element |  |  |  | 5 | 2027-01-24 | 2027-01-28
MS.CO.F4.FCD.132 | Columns & Walls Steel Fix | 57 | pcs | 2 | 2027-01-24 | 2027-01-25
MS.CO.F4.FCD.133 | Columns & Walls Formwork | 57 | pcs | 2 | 2027-01-25 | 2027-01-26
MS.CO.F4.FCD.135 | Columns & Walls Concreting work | 57 | pcs | 2 | 2027-01-27 | 2027-01-28
Slab |  | 2172.29 | M2 | 25 | 2027-01-28 | 2027-03-02
MS.CO.F4.FCD.137 | Beams and Slab Formwork | 2172.29 | M2 | 3 | 2027-01-28 | 2027-01-31
MS.CO.F4.FCD.138 | Beams and Slab Steel Fix | 2172.29 | M2 | 3 | 2027-02-01 | 2027-02-03
MS.CO.F4.FCD.139 | Beams and Slab Concreting work | 2172.29 | M2 | 1 | 2027-02-04 | 2027-02-04
MS.CO.F4.FCD.145 | DE shuttering for Slab | 2172.29 | M2 | 2 | 2027-03-01 | 2027-03-02
Masonry Works |  |  |  | 17 | 2027-03-03 | 2027-03-27
MS.CO.F4.FCD.149 | External Block Work |  |  | 10 | 2027-03-03 | 2027-03-18
MS.CO.F4.FCD.153 | Internal Block Work |  |  | 10 | 2027-03-16 | 2027-03-27
Fifth Floor |  |  |  | 34 | 2027-02-06 | 2027-03-25
Vertical Element |  |  |  | 6 | 2027-02-06 | 2027-02-11
MS.CO.F4.FCD.141 | Columns & Walls Steel Fix | 57 | pcs | 3 | 2027-02-06 | 2027-02-08
MS.CO.F4.FCD.142 | Columns & Walls Formwork | 57 | pcs | 3 | 2027-02-07 | 2027-02-09
MS.CO.F4.FCD.144 | Columns & Walls Concreting work | 57 | pcs | 3 | 2027-02-09 | 2027-02-11
Slab |  | 2279.36 | M2 | 23 | 2027-02-11 | 2027-03-18
MS.CO.F4.FCD.146 | Beams and Slab Formwork | 2279.36 | M2 | 3 | 2027-02-11 | 2027-02-15
MS.CO.F4.FCD.147 | Beams and Slab Steel Fix | 2279.36 | M2 | 3 | 2027-02-16 | 2027-02-18
MS.CO.F4.FCD.148 | Beams and Slab Concreting work | 2279.36 | M2 | 1 | 2027-02-21 | 2027-02-21
MS.CO.F4.FCD.158 | DE shuttering for Slab | 2279.36 | M2 | 2 | 2027-03-17 | 2027-03-18
Masonry Works |  |  |  | 6 | 2027-03-20 | 2027-03-25
MS.CO.F4.FCD.160 | External Block Work |  |  | 6 | 2027-03-20 | 2027-03-25
MS.CO.F4.FCD.161 | Internal Block Work |  |  | 6 | 2027-03-20 | 2027-03-25
Penthouse Floor |  |  |  | 23 | 2027-02-23 | 2027-03-27
Vertical Element |  |  |  | 4 | 2027-02-23 | 2027-02-28
MS.CO.F4.FCD.150 | Columns & Walls Steel Fix | 42 | pcs | 2 | 2027-02-23 | 2027-02-24
MS.CO.F4.FCD.151 | Columns & Walls Formwork | 42 | pcs | 2 | 2027-02-24 | 2027-02-25
MS.CO.F4.FCD.152 | Columns & Walls Concreting work | 42 | pcs | 2 | 2027-02-25 | 2027-02-28
Slab |  | 542 | M2 | 17 | 2027-02-25 | 2027-03-22
MS.CO.F4.FCD.154 | Beams and Slab Formwork | 542 | M2 | 3 | 2027-02-25 | 2027-03-01
MS.CO.F4.FCD.155 | Beams and Slab Steel Fix | 542 | M2 | 2 | 2027-03-02 | 2027-03-03
MS.CO.F4.FCD.157 | Beams and Slab Concreting work | 542 | M2 | 1 | 2027-03-04 | 2027-03-04
MS.CO.F4.FCD.159 | DE shuttering for Slab | 542 | M2 | 2 | 2027-03-21 | 2027-03-22
Masonry Works |  |  |  | 4 | 2027-03-23 | 2027-03-27
MS.CO.F4.FCD.162 | External Block Work |  |  | 4 | 2027-03-23 | 2027-03-27
MS.CO.F4.FCD.163 | Internal Block Work |  |  | 4 | 2027-03-23 | 2027-03-27
External Work |  |  |  | 19 | 2027-02-07 | 2027-03-04
MS.CO.F4.FCD.156 | Special construction works planter, cross over ,water features ,canal |  |  | 19 | 2027-02-07 | 2027-03-04
Con.Phase (5) |  |  |  | 310 | 12-Feb-26 A | 2027-03-31
Soil Improvement |  |  |  | 92 | 12-Feb-26 A | 2026-07-09
Phase (5) Ramp Influence Area |  |  |  | 92 | 12-Feb-26 A | 2026-07-09
MS.EN.P5.ALL.104 | Ramp Removal |  |  | 20 | 12-Feb-26 A | 2026-06-28
MS.EN.P5.ALL.106 | Perform Geophysical Activity |  |  | 0 | 2026-06-29 | 2026-06-29
MS.EN.P5.ALL.107 | Report preparation and Soil Improvement Proposal |  |  | 1 | 2026-06-29 | 2026-06-29
MS.EN.P5.ALL.110 | Soil Improvement (By Other) |  |  | 6 | 2026-06-30 | 2026-07-06
A1060 | Post-Grouting Verification Test |  |  | 3 | 2026-07-07 | 2026-07-09
Sub-structure Works |  |  |  | 200 | 07-Apr-26 A | 2026-11-30
Foundation |  |  |  | 112 | 07-Apr-26 A | 2026-08-18
Part 1 |  |  |  | 76 | 07-Apr-26 A | 2026-07-07
Excavation, Blinding & Waterproofing Works |  |  |  | 30 | 07-Apr-26 A | 2026-06-15
MS.CO.P5.FO.101 | Blinding concrete for lower Part of Foundation |  |  | 4 | 07-Apr-26 A | 2026-06-11
MS.CO.P5.FO.103 | Blinding concrete for Upper Part |  |  | 6 | 21-Apr-26 A | 2026-06-14
MS.CO.P5.FO.104 | Water Proofing Membrane under Raft Foundation |  |  | 12 | 28-Apr-26 A | 2026-06-15
Raft Foundation Works |  |  |  | 35 | 18-May-26 A | 2026-07-07
MS.CO.P5.FO.105 | Rebars for 1st layer for Foundation | 5365 | M2 | 9 | 18-May-26 A | 2026-06-21
MS.CO.P5.FO.109 | Installation for Mechanical and Electrical Embeds |  |  | 6 | 2026-06-22 | 2026-06-28
MS.CO.P5.FO.114 | Formwork for Foundations |  |  | 6 | 2026-06-23 | 2026-06-29
MS.CO.P5.FO.118 | Rebars for 2nd layer for Foundation and Tower Crane Anchors |  |  | 9 | 2026-06-25 | 2026-07-05
MS.CO.P5.FO.124 | Foundations Concrete Pouring |  |  | 2 | 2026-07-06 | 2026-07-07
Part 2 |  |  |  | 38 | 2026-07-06 | 2026-08-18
Excavation, Blinding & Waterproofing Works |  |  |  | 22 | 2026-07-06 | 2026-07-30
MS.CO.P5.FO.165 | Excavation for drop Panels and Trenches | 3180 | M2 | 7 | 2026-07-06 | 2026-07-13
MS.CO.P1.FO.530 | Earthing and Lightning Protection System |  |  | 2 | 2026-07-14 | 2026-07-15
MS.CO.P5.FO.135 | Blinding concrete for lower Part of Foundation |  |  | 2 | 2026-07-16 | 2026-07-18
MS.CO.P5.FO.155 | Block work for Drop Panels |  |  | 1 | 2026-07-19 | 2026-07-19
MS.CO.P5.FO.145 | Blinding concrete for Upper Part |  |  | 2 | 2026-07-20 | 2026-07-21
MS.CO.P5.FO.175 | Water Proofing Membrane under Raft Foundation |  |  | 8 | 2026-07-22 | 2026-07-30
Raft Foundation Works |  |  |  | 16 | 2026-08-01 | 2026-08-18
MS.CO.P5.FO.106 | Rebars for 1st layer for Foundation | 5365 | M2 | 9 | 2026-08-01 | 2026-08-10
MS.CO.P5.FO.110 | Installation for Mechanical and Electrical Embeds |  |  | 9 | 2026-08-04 | 2026-08-13
MS.CO.P5.FO.115 | Formwork for Foundations |  |  | 9 | 2026-08-05 | 2026-08-15
MS.CO.P5.FO.119 | Rebars for 2nd layer for Foundation and Tower Crane Anchors |  |  | 9 | 2026-08-08 | 2026-08-17
MS.CO.P5.FO.125 | Foundations Concrete Pouring |  |  | 1 | 2026-08-18 | 2026-08-18
Basement 2 |  |  |  | 104 | 2026-07-08 | 2026-11-07
Skeleton Works |  |  |  | 76 | 2026-07-08 | 2026-10-05
Vertical Element |  |  |  | 44 | 2026-07-08 | 2026-08-27
Part 1 |  |  |  | 10 | 2026-07-08 | 2026-07-19
MS.CO.P5.B2.100 | B2 - Columns Steel Fix | 188 | pcs | 6 | 2026-07-08 | 2026-07-14
MS.CO.P5.B2.200 | Walls Steel Fix | 453 | m2 | 6 | 2026-07-08 | 2026-07-14
MS.CO.P5.B2.105 | B2 - Columns Formwork |  |  | 6 | 2026-07-11 | 2026-07-16
MS.CO.P5.B2.205 | Walls Formwork |  |  | 6 | 2026-07-11 | 2026-07-16
MS.CO.P5.B2.110 | B2 - Columns Concreting work |  |  | 3 | 2026-07-16 | 2026-07-19
MS.CO.P5.B2.210 | Walls Concreting work |  |  | 3 | 2026-07-16 | 2026-07-19
Part 2 |  |  |  | 8 | 2026-08-19 | 2026-08-27
MS.CO.P5.B2.101 | B2 - Columns Steel Fix | 188 | pcs | 4 | 2026-08-19 | 2026-08-23
MS.CO.P5.B2.201 | Walls Steel Fix | 453 | m2 | 4 | 2026-08-19 | 2026-08-23
MS.CO.P5.B2.106 | B2 - Columns Formwork |  |  | 4 | 2026-08-22 | 2026-08-25
MS.CO.P5.B2.206 | Walls Formwork |  |  | 4 | 2026-08-22 | 2026-08-25
MS.CO.P5.B2.111 | B2 - Columns Concreting work |  |  | 3 | 2026-08-25 | 2026-08-27
MS.CO.P5.B2.211 | Walls Concreting work |  |  | 3 | 2026-08-25 | 2026-08-27
Slab |  |  |  | 68 | 2026-07-18 | 2026-10-05
Part 1 |  |  |  | 34 | 2026-07-18 | 2026-08-25
MS.CO.P5.B2.115 | Beams and Slab Formwork | 6186 | m2 | 7 | 2026-07-18 | 2026-07-25
MS.CO.P5.B2.120 | Beams and Slab Steel Fix |  |  | 5 | 2026-07-26 | 2026-07-30
MS.CO.P5.B2.124 | Beams and Slab Concreting work |  |  | 1 | 2026-08-01 | 2026-08-01
MS.CO.P5.B2.130 | DE shuttering for Slab |  |  | 2 | 2026-08-24 | 2026-08-25
Part 2 |  |  |  | 34 | 2026-08-26 | 2026-10-05
MS.CO.P5.B2.116 | Beams and Slab Formwork | 6186 | m2 | 7 | 2026-08-26 | 2026-09-02
MS.CO.P5.B2.121 | Beams and Slab Steel Fix |  |  | 5 | 2026-09-03 | 2026-09-08
MS.CO.P5.B2.125 | Beams and Slab Concreting work |  |  | 1 | 2026-09-09 | 2026-09-09
MS.CO.P5.B2.131 | DE shuttering for Slab |  |  | 2 | 2026-10-04 | 2026-10-05
Masonry Works |  |  |  | 28 | 2026-10-06 | 2026-11-07
MS.CO.P5.B2.135 | B2 - Block Works |  |  | 28 | 2026-10-06 | 2026-11-07
Basement 1 |  |  |  | 103 | 2026-08-02 | 2026-11-30
Skeleton Works |  |  |  | 75 | 2026-08-02 | 2026-10-28
Vertical Element |  |  |  | 44 | 2026-08-02 | 2026-09-21
Part 1 |  |  |  | 12 | 2026-08-02 | 2026-08-15
MS.CO.P5.B1.100 | B1 - Columns Steel Fix | 188 | pcs | 4 | 2026-08-02 | 2026-08-05
MS.CO.P5.B1.200 | Walls Steel Fix | 453 | m2 | 4 | 2026-08-02 | 2026-08-05
MS.CO.P5.B1.105 | B1 - Columns Formwork |  |  | 4 | 2026-08-04 | 2026-08-08
MS.CO.P5.B1.205 | Walls Formwork |  |  | 4 | 2026-08-06 | 2026-08-10
MS.CO.P5.B1.110 | B1 - Columns Concreting work |  |  | 4 | 2026-08-09 | 2026-08-12
MS.CO.P5.B1.210 | Walls Concreting work |  |  | 4 | 2026-08-11 | 2026-08-15
Part 2 |  |  |  | 10 | 2026-09-10 | 2026-09-21
MS.CO.P5.B1.101 | B1 - Columns Steel Fix | 188 | pcs | 4 | 2026-09-10 | 2026-09-14
MS.CO.P5.B1.201 | Walls Steel Fix | 453 | m2 | 4 | 2026-09-10 | 2026-09-14
MS.CO.P5.B1.106 | B1 - Columns Formwork |  |  | 4 | 2026-09-13 | 2026-09-16
MS.CO.P5.B1.206 | Walls Formwork |  |  | 4 | 2026-09-13 | 2026-09-16
MS.CO.P5.B1.111 | B1 - Columns Concreting work |  |  | 4 | 2026-09-15 | 2026-09-19
MS.CO.P5.B1.211 | Walls Concreting work |  |  | 4 | 2026-09-17 | 2026-09-21
Slab |  |  |  | 64 | 2026-08-15 | 2026-10-28
Part 1 (2,326.70 M2) |  |  |  | 34 | 2026-08-15 | 2026-09-22
MS.CO.P5.B1.115 | Beams and Slab Formwork | 6186 | m2 | 7 | 2026-08-15 | 2026-08-22
MS.CO.P5.B1.120 | Beams and Slab Steel Fix |  |  | 5 | 2026-08-23 | 2026-08-27
MS.CO.P5.B1.124 | Beams and Slab Concreting work |  |  | 1 | 2026-08-29 | 2026-08-29
MS.CO.P5.B1.130 | DE shuttering for Slab |  |  | 2 | 2026-09-21 | 2026-09-22
Part 2 (2,326.70 M2) |  |  |  | 34 | 2026-09-19 | 2026-10-28
MS.CO.P5.B1.116 | Beams and Slab Formwork | 6186 | m2 | 7 | 2026-09-19 | 2026-09-27
MS.CO.P5.B1.121 | Beams and Slab Steel Fix |  |  | 5 | 2026-09-28 | 2026-10-03
MS.CO.P5.B1.125 | Beams and Slab Concreting work |  |  | 1 | 2026-10-04 | 2026-10-04
MS.CO.P5.B1.131 | DE shuttering for Slab |  |  | 2 | 2026-10-27 | 2026-10-28
Masonry Works |  |  |  | 28 | 2026-10-29 | 2026-11-30
MS.CO.P5.B1.135 | B2 - Block Works |  |  | 28 | 2026-10-29 | 2026-11-30
Super Strcture Works |  |  |  | 144 | 2026-10-06 | 2027-03-31
10FA-J |  |  |  | 144 | 2026-10-06 | 2027-03-31
Lower Ground Floor |  |  |  | 63 | 2026-10-06 | 2026-12-17
Vertical Element |  |  |  | 8 | 2026-10-06 | 2026-10-14
MS.CO.P5.FA.100 | Columns & Walls Steel Fix | 151 | Pcs | 4 | 2026-10-06 | 2026-10-10
MS.CO.P5.FA.101 | Columns & Walls Formwork |  |  | 4 | 2026-10-08 | 2026-10-12
MS.CO.P5.FA.102 | Columns & Walls Concreting work |  |  | 4 | 2026-10-11 | 2026-10-14
Slab |  | 5529.16 | M2 | 29 | 2026-10-13 | 2026-11-15
MS.CO.P5.FA.103 | Beams and Slab Formwork |  |  | 4 | 2026-10-13 | 2026-10-17
MS.CO.P5.FA.104 | Beams and Slab Steel Fix |  |  | 3 | 2026-10-18 | 2026-10-20
MS.CO.P5.FA.105 | Beams and Slab Concreting work |  |  | 1 | 2026-10-21 | 2026-10-21
MS.CO.P5.FA.109 | DE shuttering for Slab |  |  | 2 | 2026-11-14 | 2026-11-15
Masonry Works |  |  |  | 15 | 2026-12-01 | 2026-12-17
MS.CO.P5.FA.115 | External Block Work |  |  | 12 | 2026-12-01 | 2026-12-14
MS.CO.P5.FA.118 | Internal Block Work |  |  | 12 | 2026-12-05 | 2026-12-17
Ground Floor |  |  |  | 67 | 2026-10-22 | 2027-01-07
Vertical Element |  |  |  | 6 | 2026-10-22 | 2026-10-28
MS.CO.P5.FA.106 | Columns & Walls Steel Fix | 151 | Pcs | 3 | 2026-10-22 | 2026-10-25
MS.CO.P5.FA.107 | Columns & Walls Formwork |  |  | 3 | 2026-10-25 | 2026-10-27
MS.CO.P5.FA.108 | Columns & Walls Concreting work |  |  | 3 | 2026-10-26 | 2026-10-28
Slab |  | 3952.35 | M2 | 29 | 2026-10-27 | 2026-11-29
MS.CO.P5.FA.110 | Beams and Slab Formwork |  |  | 4 | 2026-10-27 | 2026-10-31
MS.CO.P5.FA.111 | Beams and Slab Steel Fix |  |  | 3 | 2026-11-01 | 2026-11-03
MS.CO.P5.FA.112 | Beams and Slab Concreting work |  |  | 1 | 2026-11-04 | 2026-11-04
MS.CO.P5.FA.117 | DE shuttering for Slab |  |  | 2 | 2026-11-28 | 2026-11-29
Masonry Works |  |  |  | 21 | 2026-12-15 | 2027-01-07
MS.CO.P5.FA.124 | External Block Work |  |  | 10 | 2026-12-15 | 2026-12-26
MS.CO.P5.FA.127 | Internal Block Work |  |  | 12 | 2026-12-26 | 2027-01-07
First Floor |  |  |  | 69 | 2026-11-05 | 2027-01-24
Vertical Element |  |  |  | 6 | 2026-11-05 | 2026-11-11
MS.CO.P5.FA.113 | Columns & Walls Steel Fix | 151 | Pcs | 3 | 2026-11-05 | 2026-11-08
MS.CO.P5.FA.114 | Columns & Walls Formwork |  |  | 3 | 2026-11-08 | 2026-11-10
MS.CO.P5.FA.116 | Columns & Walls Concreting work |  |  | 3 | 2026-11-09 | 2026-11-11
Slab |  | 4969.6 | M2 | 29 | 2026-11-10 | 2026-12-13
MS.CO.P5.FA.119 | Beams and Slab Formwork |  |  | 4 | 2026-11-10 | 2026-11-14
MS.CO.P5.FA.120 | Beams and Slab Steel Fix |  |  | 3 | 2026-11-15 | 2026-11-17
MS.CO.P5.FA.121 | Beams and Slab Concreting work |  |  | 1 | 2026-11-18 | 2026-11-18
MS.CO.P5.FA.126 | DE shuttering for Slab |  |  | 2 | 2026-12-12 | 2026-12-13
Masonry Works |  |  |  | 25 | 2026-12-27 | 2027-01-24
MS.CO.P5.FA.133 | External Block Work |  |  | 12 | 2026-12-27 | 2027-01-09
MS.CO.P5.FA.136 | Internal Block Work |  |  | 14 | 2027-01-09 | 2027-01-24
Second Floor |  |  |  | 69 | 2026-11-19 | 2027-02-07
Vertical Element |  |  |  | 6 | 2026-11-19 | 2026-11-25
MS.CO.P5.FA.122 | Columns & Walls Steel Fix | 151 | Pcs | 3 | 2026-11-19 | 2026-11-22
MS.CO.P5.FA.123 | Columns & Walls Formwork |  |  | 3 | 2026-11-22 | 2026-11-24
MS.CO.P5.FA.125 | Columns & Walls Concreting work |  |  | 3 | 2026-11-23 | 2026-11-25
Slab |  | 4716.46 | M2 | 27 | 2026-11-25 | 2026-12-26
MS.CO.P5.FA.128 | Beams and Slab Formwork |  |  | 3 | 2026-11-25 | 2026-11-28
MS.CO.P5.FA.129 | Beams and Slab Steel Fix |  |  | 2 | 2026-11-29 | 2026-11-30
MS.CO.P5.FA.130 | Beams and Slab Concreting work |  |  | 1 | 2026-12-01 | 2026-12-01
MS.CO.P5.FA.135 | DE shuttering for Slab |  |  | 2 | 2026-12-24 | 2026-12-26
Masonry Works |  |  |  | 25 | 2027-01-10 | 2027-02-07
MS.CO.P5.FA.142 | External Block Work |  |  | 12 | 2027-01-10 | 2027-01-23
MS.CO.P5.FA.145 | Internal Block Work |  |  | 12 | 2027-01-25 | 2027-02-07
Third Floor |  |  |  | 70 | 2026-12-02 | 2027-02-24
Vertical Element |  |  |  | 5 | 2026-12-02 | 2026-12-07
MS.CO.P5.FA.131 | Columns & Walls Steel Fix | 151 | Pcs | 3 | 2026-12-02 | 2026-12-05
MS.CO.P5.FA.132 | Columns & Walls Formwork |  |  | 3 | 2026-12-03 | 2026-12-06
MS.CO.P5.FA.134 | Columns & Walls Concreting work |  |  | 3 | 2026-12-05 | 2026-12-07
Slab |  | 4629.31 | M2 | 27 | 2026-12-07 | 2027-01-06
MS.CO.P5.FA.137 | Beams and Slab Formwork |  |  | 3 | 2026-12-07 | 2026-12-09
MS.CO.P5.FA.138 | Beams and Slab Steel Fix |  |  | 2 | 2026-12-10 | 2026-12-12
MS.CO.P5.FA.139 | Beams and Slab Concreting work |  |  | 1 | 2026-12-13 | 2026-12-13
MS.CO.P5.FA.144 | DE shuttering for Slab |  |  | 2 | 2027-01-05 | 2027-01-06
Masonry Works |  |  |  | 25 | 2027-01-24 | 2027-02-24
MS.CO.P5.FA.151 | External Block Work |  |  | 12 | 2027-01-24 | 2027-02-06
MS.CO.P5.FA.154 | Internal Block Work |  |  | 12 | 2027-02-08 | 2027-02-24
Fourth Floor |  |  |  | 72 | 2026-12-14 | 2027-03-16
Vertical Element |  |  |  | 5 | 2026-12-14 | 2026-12-19
MS.CO.P5.FA.140 | Columns & Walls Steel Fix | 151 | Pcs | 3 | 2026-12-14 | 2026-12-16
MS.CO.P5.FA.141 | Columns & Walls Formwork |  |  | 3 | 2026-12-15 | 2026-12-17
MS.CO.P5.FA.143 | Columns & Walls Concreting work |  |  | 3 | 2026-12-16 | 2026-12-19
Slab |  | 4629.31 | M2 | 27 | 2026-12-19 | 2027-01-18
MS.CO.P5.FA.146 | Beams and Slab Formwork |  |  | 3 | 2026-12-19 | 2026-12-21
MS.CO.P5.FA.147 | Beams and Slab Steel Fix |  |  | 2 | 2026-12-22 | 2026-12-23
MS.CO.P5.FA.148 | Beams and Slab Concreting work |  |  | 1 | 2026-12-24 | 2026-12-24
MS.CO.P5.FA.153 | DE shuttering for Slab |  |  | 2 | 2027-01-17 | 2027-01-18
Masonry Works |  |  |  | 25 | 2027-02-07 | 2027-03-16
MS.CO.P5.FA.160 | External Block Work |  |  | 12 | 2027-02-07 | 2027-02-23
MS.CO.P5.FA.163 | Internal Block Work |  |  | 12 | 2027-02-25 | 2027-03-16
Fifth Floor |  |  |  | 74 | 2026-12-26 | 2027-03-30
Vertical Element |  |  |  | 5 | 2026-12-26 | 2026-12-30
MS.CO.P5.FA.149 | Columns & Walls Steel Fix | 151 | Pcs | 3 | 2026-12-26 | 2026-12-28
MS.CO.P5.FA.150 | Columns & Walls Formwork | 151 | Pcs | 3 | 2026-12-27 | 2026-12-29
MS.CO.P5.FA.152 | Columns & Walls Concreting work | 151 | Pcs | 3 | 2026-12-28 | 2026-12-30
Slab |  | 4629.31 | M2 | 27 | 2026-12-29 | 2027-01-28
MS.CO.P5.FA.155 | Beams and Slab Formwork | 4629.31 | M2 | 3 | 2026-12-29 | 2026-12-31
MS.CO.P5.FA.156 | Beams and Slab Steel Fix | 4629.31 | M2 | 2 | 2027-01-02 | 2027-01-03
MS.CO.P5.FA.157 | Beams and Slab Concreting work | 4629.31 | M2 | 1 | 2027-01-04 | 2027-01-04
MS.CO.P5.FA.162 | DE shuttering for Slab | 4629.31 | M2 | 2 | 2027-01-27 | 2027-01-28
Masonry Works |  |  |  | 25 | 2027-02-24 | 2027-03-30
MS.CO.P5.FA.169 | External Block Work |  |  | 12 | 2027-02-24 | 2027-03-15
MS.CO.P5.FA.172 | Internal Block Work |  |  | 12 | 2027-03-17 | 2027-03-30
Sixth Floor |  |  |  | 66 | 2027-01-05 | 2027-03-31
Vertical Element |  |  |  | 5 | 2027-01-05 | 2027-01-10
MS.CO.P5.FA.158 | Columns & Walls Steel Fix | 151 | Pcs | 3 | 2027-01-05 | 2027-01-07
MS.CO.P5.FA.159 | Columns & Walls Formwork | 151 | Pcs | 3 | 2027-01-06 | 2027-01-09
MS.CO.P5.FA.161 | Columns & Walls Concreting work | 151 | Pcs | 3 | 2027-01-07 | 2027-01-10
Slab |  | 4086.77 | M2 | 27 | 2027-01-11 | 2027-02-10
MS.CO.P5.FA.164 | Beams and Slab Formwork |  |  | 3 | 2027-01-11 | 2027-01-13
MS.CO.P5.FA.165 | Beams and Slab Steel Fix |  |  | 2 | 2027-01-14 | 2027-01-16
MS.CO.P5.FA.166 | Beams and Slab Concreting work |  |  | 1 | 2027-01-17 | 2027-01-17
MS.CO.P5.FA.171 | DE shuttering for Slab |  |  | 2 | 2027-02-09 | 2027-02-10
Masonry Works |  |  |  | 14 | 2027-03-16 | 2027-03-31
MS.CO.P5.FA.178 | External Block Work |  |  | 14 | 2027-03-16 | 2027-03-31
MS.CO.P5.FA.179 | Internal Block Work |  |  | 14 | 2027-03-16 | 2027-03-31
Seventh Floor |  |  |  | 45 | 2027-01-18 | 2027-03-20
Vertical Element |  |  |  | 5 | 2027-01-18 | 2027-01-23
MS.CO.P5.FA.167 | Columns & Walls Steel Fix | 151 | Pcs | 3 | 2027-01-18 | 2027-01-20
MS.CO.P5.FA.168 | Columns & Walls Formwork |  |  | 3 | 2027-01-19 | 2027-01-21
MS.CO.P5.FA.170 | Columns & Walls Concreting work |  |  | 3 | 2027-01-20 | 2027-01-23
Slab |  | 4086.77 | M2 | 27 | 2027-01-23 | 2027-02-25
MS.CO.P5.FA.173 | Beams and Slab Formwork | 4086.77 | M2 | 3 | 2027-01-23 | 2027-01-25
MS.CO.P5.FA.174 | Beams and Slab Steel Fix | 4086.77 | M2 | 2 | 2027-01-26 | 2027-01-27
MS.CO.P5.FA.175 | Beams and Slab Concreting work | 4086.77 | M2 | 1 | 2027-01-28 | 2027-01-28
MS.CO.P5.FA.181 | DE shuttering for Slab |  |  | 2 | 2027-02-24 | 2027-02-25
Masonry Works |  |  |  | 14 | 2027-02-28 | 2027-03-20
MS.CO.P5.FA.187 | External Block Work |  |  | 12 | 2027-02-28 | 2027-03-17
MS.CO.P5.FA.188 | Internal Block Work |  |  | 14 | 2027-02-28 | 2027-03-20
Eight Floor |  |  |  | 43 | 2027-01-30 | 2027-03-29
Vertical Element |  |  |  | 5 | 2027-01-30 | 2027-02-03
MS.CO.P5.FA.176 | Columns & Walls Steel Fix | 140 | Pcs | 3 | 2027-01-30 | 2027-02-01
MS.CO.P5.FA.177 | Columns & Walls Formwork | 140 | Pcs | 3 | 2027-01-31 | 2027-02-02
MS.CO.P5.FA.180 | Columns & Walls Concreting work | 140 | Pcs | 3 | 2027-02-01 | 2027-02-03
Slab |  | 3632.9 | M2 | 25 | 2027-02-03 | 2027-03-11
MS.CO.P5.FA.182 | Beams and Slab Formwork |  |  | 3 | 2027-02-03 | 2027-02-06
MS.CO.P5.FA.183 | Beams and Slab Steel Fix |  |  | 2 | 2027-02-07 | 2027-02-08
MS.CO.P5.FA.184 | Beams and Slab Concreting work |  |  | 1 | 2027-02-09 | 2027-02-09
MS.CO.P5.FA.190 | DE shuttering for Slab |  |  | 2 | 2027-03-10 | 2027-03-11
Masonry Works |  |  |  | 10 | 2027-03-18 | 2027-03-29
MS.CO.P5.FA.197 | External Block Work |  |  | 10 | 2027-03-18 | 2027-03-29
MS.CO.P5.FA.198 | Internal Block Work |  |  | 10 | 2027-03-18 | 2027-03-29
Nine Floor |  |  |  | 35 | 2027-02-10 | 2027-03-31
Vertical Element |  |  |  | 5 | 2027-02-10 | 2027-02-16
MS.CO.P5.FA.185 | Columns & Walls Steel Fix | 140 | Pcs | 3 | 2027-02-10 | 2027-02-14
MS.CO.P5.FA.186 | Columns & Walls Formwork | 140 | Pcs | 3 | 2027-02-11 | 2027-02-15
MS.CO.P5.FA.189 | Columns & Walls Concreting work | 140 | Pcs | 3 | 2027-02-14 | 2027-02-16
Slab |  | 3632.9 | M2 | 24 | 2027-02-15 | 2027-03-22
MS.CO.P5.FA.191 | Beams and Slab Formwork |  |  | 3 | 2027-02-15 | 2027-02-17
MS.CO.P5.FA.192 | Beams and Slab Steel Fix |  |  | 2 | 2027-02-18 | 2027-02-21
MS.CO.P5.FA.193 | Beams and Slab Concreting work |  |  | 1 | 2027-02-23 | 2027-02-23
MS.CO.P5.FA.202 | DE shuttering for Slab |  |  | 2 | 2027-03-21 | 2027-03-22
Masonry Works |  |  |  | 10 | 2027-03-21 | 2027-03-31
MS.CO.P5.FA.203 | External Block Work |  |  | 10 | 2027-03-21 | 2027-03-31
MS.CO.P5.FA.204 | Internal Block Work |  |  | 10 | 2027-03-21 | 2027-03-31
Penthouse Floor |  |  |  | 25 | 2027-02-24 | 2027-03-30
Vertical Element |  |  |  | 4 | 2027-02-24 | 2027-03-01
MS.CO.P5.FA.194 | Columns & Walls Steel Fix | 80 | Pcs | 2 | 2027-02-24 | 2027-02-25
MS.CO.P5.FA.195 | Columns & Walls Formwork | 80 | Pcs | 2 | 2027-02-25 | 2027-02-28
MS.CO.P5.FA.196 | Columns & Walls Concreting work | 80 | Pcs | 1 | 2027-03-01 | 2027-03-01
Slab |  | 935.92 | M2 | 15 | 2027-03-02 | 2027-03-23
MS.CO.P5.FA.199 | Beams and Slab Formwork |  |  | 2 | 2027-03-02 | 2027-03-03
MS.CO.P5.FA.200 | Beams and Slab Steel Fix |  |  | 2 | 2027-03-04 | 2027-03-07
MS.CO.P5.FA.201 | Beams and Slab Concreting work |  |  | 1 | 2027-03-08 | 2027-03-08
MS.CO.P5.FA.205 | DE shuttering for Slab |  |  | 2 | 2027-03-22 | 2027-03-23
Masonry Works |  |  |  | 6 | 2027-03-24 | 2027-03-30
MS.CO.P5.FA.207 | External Block Work |  |  | 6 | 2027-03-24 | 2027-03-30
MS.CO.P5.FA.208 | Internal Block Work |  |  | 6 | 2027-03-24 | 2027-03-30
External Work |  |  |  | 22 | 2027-02-06 | 2027-03-08
MS.CO.P5.ALL.206 | Special construction works planter, cross over ,water features ,canal |  |  | 22 | 2027-02-06 | 2027-03-08
Close Out and Handing Over |  |  |  | 167 | 2026-09-08 | 2027-03-31
A1510 | Authority Inspection & Final Approval |  |  | 20 | 2027-03-04 | 2027-03-31
A1360 | Project Handing Over |  |  | 20 | 2027-03-09 | 2027-03-31
As Built |  |  |  | 165 | 2026-09-08 | 2027-03-29
Submittal |  |  |  | 159 | 2026-09-08 | 2027-03-22
MS.AS.P02.Subst.A. | As built drawing Submittal for phase 02 Building Subst |  |  | 12 | 2026-09-08 | 2026-09-21
MS.AS.P01.Subst.A. | As built drawing Submittal for phase 01 Building Subst |  |  | 12 | 2026-09-28 | 2026-10-11
MS.AS.P05.Subst.A. | As built drawing Submittal for phase 05 Building Subst |  |  | 12 | 2026-10-29 | 2026-11-11
MS.AS.P02.RB--B.A. | As built drawing Submittal for phase 02 Building RB--B |  |  | 12 | 2027-01-27 | 2027-02-09
MS.AS.P02.FB--R.A. | As built drawing Submittal for phase 02 Building FB--R |  |  | 12 | 2027-01-30 | 2027-02-11
MS.AS.P03.4FA-K.A. | As built drawing Submittal for phase 03 Building 4FA-K |  |  | 12 | 2027-01-31 | 2027-02-14
MS.AS.P01.6FA-E.A. | As built drawing Submittal for phase 01 Building 6FA-E |  |  | 12 | 2027-02-02 | 2027-02-16
MS.AS.P02.Hotel.A. | As built drawing Submittal for phase 02 Building Hotel |  |  | 12 | 2027-02-02 | 2027-02-16
MS.AS.P01.6FA-H.A. | As built drawing Submittal for phase 01 Building 6FA-H |  |  | 12 | 2027-02-03 | 2027-02-17
MS.AS.P01.6FA-F.A. | As built drawing Submittal for phase 01 Building 6FA-F |  |  | 12 | 2027-02-04 | 2027-02-18
MS.AS.P03.4FA-M.A. | As built drawing Submittal for phase 03 Building 4FA-M |  |  | 12 | 2027-02-07 | 2027-02-23
MS.AS.P04.Subst.A. | As built drawing Submittal for phase 04 Building Subst |  |  | 12 | 2027-02-07 | 2027-02-23
MS.AS.P02.FB--C.A. | As built drawing Submittal for phase 02 Building FB--C |  |  | 12 | 2027-02-08 | 2027-02-24
MS.AS.P04.FC--Q.A. | As built drawing Submittal for phase 04 Building FC--Q |  |  | 10 | 2027-02-08 | 2027-02-21
MS.AS.P04.FC--D.A. | As built drawing Submittal for phase 04 Building FC--D |  |  | 12 | 2027-02-08 | 2027-02-24
MS.AS.P05.10FAJ.A. | As built drawing Submittal for phase 05 Building 10FAJ |  |  | 12 | 2027-02-09 | 2027-02-25
MS.AS.P03.4FA-L.A. | As built drawing Submittal for phase 03 Building 4FA-L |  |  | 12 | 2027-02-10 | 2027-02-28
MS.AS.P01.6FA-I.A. | As built drawing Submittal for phase 01 Building 6FA-I |  |  | 12 | 2027-02-15 | 2027-03-03
MS.AS.P03.4FA-N.A. | As built drawing Submittal for phase 03 Building 4FA-N |  |  | 12 | 2027-02-16 | 2027-03-04
MS.AS.P03.Mosque.A. | As built drawing Submittal for phase 03 Building Mosque |  |  | 12 | 2027-02-16 | 2027-03-04
MS.AS.P03.4FA-O.A. | As built drawing Submittal for phase 03 Building 4FA-O |  |  | 12 | 2027-02-17 | 2027-03-07
MS.AS.P01.6FA-G.A. | As built drawing Submittal for phase 01 Building 6FA-G |  |  | 12 | 2027-02-25 | 2027-03-16
MS.AS.P03.Subst.A. | As built drawing Submittal for phase 03 Building Subst |  |  | 12 | 2027-03-04 | 2027-03-22
Approval |  |  |  | 159 | 2026-09-15 | 2027-03-29
MS.AA.P02.Subst.A. | As built drawing Approval for phase 02 Building Subst |  |  | 12 | 2026-09-15 | 2026-09-29
MS.AA.P01.Subst.A. | As built drawing Approval for phase 01 Building Subst |  |  | 12 | 2026-10-05 | 2026-10-18
MS.AA.P05.Subst.A. | As built drawing Approval for phase 05 Building Subst |  |  | 12 | 2026-11-05 | 2026-11-18
MS.AA.P02.RB--B.A. | As built drawing Approval for phase 02 Building RB--B |  |  | 12 | 2027-02-03 | 2027-02-17
MS.AA.P02.FB--R.A. | As built drawing Approval for phase 02 Building FB--R |  |  | 12 | 2027-02-06 | 2027-02-21
MS.AA.P03.4FA-K.A. | As built drawing Approval for phase 03 Building 4FA-K |  |  | 12 | 2027-02-07 | 2027-02-23
MS.AA.P01.6FA-E.A. | As built drawing Approval for phase 01 Building 6FA-E |  |  | 12 | 2027-02-09 | 2027-02-25
MS.AA.P02.Hotel.A. | As built drawing Approval for phase 02 Building Hotel |  |  | 12 | 2027-02-09 | 2027-02-25
MS.AA.P01.6FA-H.A. | As built drawing Approval for phase 01 Building 6FA-H |  |  | 12 | 2027-02-10 | 2027-02-28
MS.AA.P01.6FA-F.A. | As built drawing Approval for phase 01 Building 6FA-F |  |  | 12 | 2027-02-11 | 2027-03-01
MS.AA.P03.4FA-M.A. | As built drawing Approval for phase 03 Building 4FA-M |  |  | 12 | 2027-02-15 | 2027-03-03
MS.AA.P04.Subst.A. | As built drawing Approval for phase 04 Building Subst |  |  | 12 | 2027-02-15 | 2027-03-03
MS.AA.P02.FB--C.A. | As built drawing Approval for phase 02 Building FB--C |  |  | 12 | 2027-02-16 | 2027-03-04
MS.AA.P04.FC--Q.A. | As built drawing Approval for phase 04 Building FC--Q |  |  | 12 | 2027-02-16 | 2027-03-04
MS.AA.P04.FC--D.A. | As built drawing Approval for phase 04 Building FC--D |  |  | 12 | 2027-02-16 | 2027-03-04
MS.AA.P05.10FAJ.A. | As built drawing Approval for phase 05 Building 10FAJ |  |  | 12 | 2027-02-17 | 2027-03-07
MS.AA.P03.4FA-L.A. | As built drawing Approval for phase 03 Building 4FA-L |  |  | 12 | 2027-02-18 | 2027-03-08
MS.AA.P01.6FA-I.A. | As built drawing Approval for phase 01 Building 6FA-I |  |  | 12 | 2027-02-24 | 2027-03-15
MS.AA.P03.4FA-N.A. | As built drawing Approval for phase 03 Building 4FA-N |  |  | 12 | 2027-02-25 | 2027-03-16
MS.AA.P03.Mosque.A. | As built drawing Approval for phase 03 Building Mosque |  |  | 12 | 2027-02-25 | 2027-03-16
MS.AA.P03.4FA-O.A. | As built drawing Approval for phase 03 Building 4FA-O |  |  | 12 | 2027-02-28 | 2027-03-17
MS.AA.P01.6FA-G.A. | As built drawing Approval for phase 01 Building 6FA-G |  |  | 12 | 2027-03-07 | 2027-03-23
MS.AA.P03.Subst.A. | As built drawing Approval for phase 03 Building Subst |  |  | 12 | 2027-03-16 | 2027-03-29